
MONTREAL PROTOCOL

ON SUBSTANCES THAT DEPLETE

THE OZONE LAYER

[image: image21.emf]Year

Business Plan Approvals Difference %approvals Cumulative

2016 175,906,212 134,886,955 41,019,257 77%

2015 172,925,384 185,521,702 -12,596,318 107%

2014 150,349,262 109,636,438 40,712,824 73% 2014-2016

2014-2016 499,180,858 430,045,095 69,135,763 86.15% 86.15%

2013 163,058,422 143,350,645 19,707,777 88%

2012 158,193,207 118,099,916 40,093,291 75%

2011 251,685,220 227,553,662 24,131,558 90% 2011-2016

2011-2013 572,936,849 489,004,223 83,932,626 85.35% 85.72%

2010 205,296,416 103,360,124 101,936,292 50%

2009 106,014,427 87,689,407 18,325,020 83%

2008 145,296,562 142,226,527 3,070,035 98% 2008-2016

2008-2010 456,607,405 333,276,058 123,331,347 72.99% 81.92%

2007 171,419,512 135,794,742 35,624,770 79%

2006 161,412,541 136,961,591 24,450,950 85%

2005 226,796,158 213,353,085 13,443,073 94% 2005-2016

2005-2007 559,628,211 486,109,418 73,518,793 86.86% 82.33%

2004 221,409,010 186,227,602 35,181,408 84%

2003 226,732,762 173,814,977 52,917,785 77%

2002 195,635,529 185,628,199 10,007,330 95% 2002-2016

2002-2004 643,777,301 545,670,778 98,106,523 84.76% 83.24%

2001 166,859,265 144,052,417 22,806,848 86%

2000 131,542,713 125,740,663 5,802,050 96%


UNEP

Report of the
Technology and Economic Assessment Panel

October 2017 
Volume II
Supplement to the May 2017 

TEAP Replenishment Task Force Report

“Assessment of the Funding Requirement for the Replenishment of the Multilateral Fund 

for the Period 2018-2020”
TEAP October 2017 Report

Volume II

Supplement to the

May 2017 TEAP Replenishment 

Task Force Report

“Assessment of the Funding Requirement 

for the Replenishment of the Multilateral Fund 

for the Period 2018-2020”
October 2017
Montreal Protocol

On Substances that Deplete the Ozone Layer

Report of the

UNEP Technology and Economic Assessment Panel

Replenishment Task Force

October 2017
TEAP October 2017 Report

Volume II

Supplement to the May 2017 TEAP Replenishment
Task Force Report

"Assessment of the Funding Requirement for the 
Replenishment of the Multilateral Fund for

the Period 2018-2020"

The text of this report is composed in Times New Roman.

Co-ordination:
TEAP and its Replenishment Task Force
Composition:
Lambert Kuijpers, Bella Maranion, Shiqiu Zhang 

Layout:
Lambert Kuijpers

Reproduction:
UNON Nairobi

Date:
October 2017
No copyright involved.  This publication may be freely copied, abstracted and cited, with acknowledgement of the source of the material.
Printed in Nairobi, Kenya, 2017
TEAP October 2017 report

Volume II

Supplement to the

May 2017 TEAP Replenishment 

Task Force Report

“Assessment of the Funding Requirement 

for the Replenishment of the Multilateral Fund 

for the Period 2018-2020”
October 2017
DISCLAIMER

The United Nations Environment Programme (UNEP), the Technology and Economic Assessment Panel (TEAP) co-chairs and members, the Technical Options Committees chairs, co-chairs and members, the TEAP Task Forces co-chairs and members, and the companies and organisations that employ them do not endorse the performance, worker safety, or environmental acceptability of any of the technical and economic options discussed.

UNEP, the TEAP co-chairs and members, the Technical Options Committees chairs, co-chairs and members, and the Technology and Economic Assessment Panel Task Forces co-chairs and members, in furnishing or distributing the information that follows, do not make any warranty or representation, either express or implied, with respect to the accuracy, completeness, or utility; nor do they assume any liability of any kind whatsoever resulting from the use or reliance upon any information, material, or procedure contained herein.

ACKNOWLEDGEMENTS

The UNEP Technology and Economic Assessment Panel and the Replenishment Task Force co-chairs and members wish to express thanks to all who contributed from governments, both Article 5 and non-Article 5, to the Multilateral Fund Secretariat, to the Ozone Secretariat, to all Implementing Agencies, as well as to a large number of individuals involved in Protocol issues, without whose involvement this supplementary report to the original assessment would not have been possible.

The opinions expressed are those of the Panel and its Task Force and do not necessarily reflect the reviews of any sponsoring or supporting organisation.

Foreword
 The October 2017 TEAP Report

The October 2017 TEAP Report consists of the following volumes:

Volume I:    October 2017 TEAP Critical Use Nominations Report – Final Report
Volume II:   Supplement to the May 2017 TEAP Replenishment Task Force Report
Volume III: TEAP Decision XXVIII/3 Working Group Report on Energy Efficiency
This is Volume II.
The UNEP Technology and Economic Assessment Panel (TEAP):
	Bella Maranion , co-chair
	USA
	Kei-ichi Ohnishi
	J

	Marta Pizano, co-chair
	COL
	Fabio Polonara
	I

	Ashley Woodcock, co-chair
	UK
	Roberto Peixoto
	BRA

	Paulo Altoe
	BRA
	Ian Porter
	AUS

	Mohamed Besri
	MOR
	Helen Tope
	AUS

	Suely M. Carvalho
	BRA
	Rajendra Shende
	IN

	Adam Chattaway
	UK
	Dan Verdonik
	USA

	Marco Gonzalez
	CR
	Shiqiu Zhang
	PRC

	Sergey Kopylov
	RF
	Jianjun Zhnag
	PRC


For this, the Replenishment Task Force under TEAP
	Lambert Kuijpers, co-chair
	NL
	Sukumar Devotta
	IND

	Bella Maranion , co-chair
	USA
	Horace Nelson
	JAM

	Shiqiu Zhang, co-chair
	PRC
	Fabio Polonara
	I

	Paulo Altoe
	BRA
	Helen Tope
	AUS

	Suely M. Carvalho
	BRA
	Dan Verdonik
	USA

	Daniel Colbourne
	UK
	Helen Walter-Terrinoni 
	USA


Table of Contents

ixTable of Contents

Executive Summary
1
1
Introduction
5
1.1
The Process
5
1.2
The Contact Group on Replenishment
5
Summary of suggestions for elaboration in the supplementary Technology and Economic Assessment Panel task force report
5
1.3 
Structure and procedure for the completion of the Supplement Report
7
2  
Overall questions to the report
9
2.1 
Paragraph 3 in the Terms of Reference in Decision XXVIII/5
9
2.2 
Cost effectiveness figures in various units
10
2.2.1 
Non-LVC countries
10
2.2.2 
LVC countries
12
2.2.3 
Different way of determining CE values
14
2.2.4 
Determining CE values on the basis of including or excluding agency support costs
14
2.2.5 
Determining CE values on the basis of amounts determined for various LVC country sizes by the ExCom
15
2.3 
Distinction between costs associated with HCFC and HFC related activities
16
2.4 
Schedule comparing previously approved activities with business plan estimates
17
2.5 
Taking into account recent ExCom decisions
18
3  
Elaboration on the funding components for HPMPs
21
3.1
Scenarios considering HPMP stage III
21
3.2
Scenarios considering the deferral of stage III activities
21
3.3
Deferral of planned activities not needed for 35% reduction to the next triennium
22
3.3.1
Recalculating the HPMP funding requirement
23
3.3.2
Impact of ExCom-79 decisions
24
3.3.3
Planned approach for countries that have no approvals to achieve 35% reduction
24
4  
Accounting for the HCFC production phase-out
29
4.1   
China HPPMP stage II plan and related assumptions in the upcoming ExCom-80 meeting
29
4.2   
Various tranches in the 2018-2020 triennium
29
5
Non-investment and supporting activities
31
5.1  
How to account for parties with an accelerated phase-out in HPMP stage II implementation
31
5.2.  
Taking into account HPMPs stage III to achieve early reduction steps
31
5.3
Deferring HPMPs stage III to the 2021-2023 triennium
31
5.4
The funding for CAP with various annual increases
31
5.5
No HCFC demonstration projects
32
5.6
HPMP stage III project preparation activities
32
6   
HFC phase-down enabling activities
33
7   
HFC-23 mitigation
35
8   
Summary of funding amounts calculated for various items
37
Annex 1
39
Summary of suggestions for elaboration in the supplementary Technology and Economic Assessment Panel task force report
39
Annex 2 Calculation of planned amounts up to 35%
41


Executive Summary

· On the basis of the discussions in the Contact Group, the Open-ended Working Group at its thirty-ninth meeting (OEWG-39) requested the TEAP to elaborate on specific groups of elements in the form of a supplementary report to its May 2017 Replenishment Task Force (RTF) Report.  The specific elements, for which elaboration was requested, are given in the report of OEWG-39 and are attached to this document as Annex 1.

· At the OEWG-39, the following overall questions were raised:

· Elaboration on paragraph 3 of the Terms of Reference as expressed in decision XXVIII/5;
· To present cost effectiveness figures in ODP-tonnes, metric tonnes and tonnes CO2 equivalent;

· To give a clearer distinction between costs associated with HCFC-related and HFC-related activities;

· To present a scenario comparing previously approved projects with business plan estimates on an annual basis in relation to determining uncertainty for planned activities; and

· To account for recent ExCom (ExCom-79) decisions. 
In addition, OEWG-39 requested specific elaboration on the following elements of the total funding requirement:

· The funding components for HCFC Phase-out Management Plans; 

· The HCFC production phase-out;
· Non-investment and supporting activities;
· HFC phase-down enabling activities; and
· HFC-23 mitigation.

· The above elements are elaborated and addressed in this Supplement Report. Based on certain requests from OEWG-39, below is a summary of elaborations for specific elements of the total funding requirement for the MLF for the triennium 2018-2020: 

1) Approved versus planned funding for HPMPs

The average percentage of funding for approvals for all years from 2005 through 2016 equals 83.24% of the funding for planned activities from the Business Plan. This implies that the average funding agreed to by the Executive Committee for each activity was at a level that is 16.76% lower than the amount in the Business Plan. The RTF has also looked at the uncertainty of the average value. By taking all the differences between planned and approved funding for the years 2005-2016, an average deviation of 13.5% can be calculated for the uncertainty range. Using this value, a rescaling is applied, i.e., funding for (HPMP) activities is, in principle, approved, for a range of about 70-97% of the funding for planned activities.
2) Accounting for ExCom-79 decisions on HPMP approvals

Funding decisions from ExCom-79 reduced the funding requirement for the planned activities for non-LVC countries from a total of US$ 97.1 to US$ 74.1 million for the triennium 2018-2020, a reduction of US$ 23.0 million, and of US$ 0.23 million for LVC countries, by bringing the latter amount to the approved funding amount for 2017. Due to approvals, the funding requirement for approved HPMP activities for non-LVC countries increased from US$ 289.4 to US$ 296.2 million (i.e., a difference of US$ 6.8 million). It did not change for LVC countries, because the planned funding became approved funding for the year 2017, a year outside the 2018-2020 triennium. 

Taking into account the decisions from ExCom-79 compared to the rescaled activities, the average total funding requirement for HPMPs (excluding any HPMPs stage III) in the triennium 2018-2020 has decreased by US$ 12.5 million from US$ 388.4 to US$ 375.9 million.
3) Deferring stage III HPMPs

Deferring HPMP stage III activities to the triennium 2021-2023 would reduce the funding requirement presented in the May 2017 report (US$ 0-70.95 million) to zero. 
4) Cost effectiveness values of HPMPs (including agency support costs)
An average (country-weighted) cost effectiveness value has been calculated based on the ODP-tonnes approvals for a representative number of non-LVC countries (where the approvals usually concern one, or a mix of two or three HCFCs). This value is US$ 5.18 per kg ODS for non-LVC countries when including China, and US$ 5.79 per kg ODS when excluding China. The calculated cost effectiveness value of a representative sample of LVC countries is US$ 9.23 per kg ODS. In climate terms, the cost effectiveness value is US$ 3.75 t CO2-eq. for non-LVC countries when including China, and US$ 5.05 t CO2-eq. when excluding China. For a representative sample of LVC countries it is US$ 7.08 t CO2-eq.
5) Various tranches for HCFC Production Phase-out Management Plans (HPPMPs)
In the May 2017 report, the RTF assumed equal funding tranches for the 14 years for the Chinese HPPMP in the period 2017-2030, leading to a funding requirement of US$ 65.62 million (US$ 21.87 million for each of the three years) for the triennium 2018-2020. This assumes a first tranche of US$ 21.87 in the year 2017. In considering two funding tranches for the Chinese HPPMP in the triennium 2018-2020, the total funding for the next triennium is estimated at US$ 47.15 or US$ 51.04 million, depending on when the approval decision would be taken and on how the funding tranches would be specified.

6) Funding for the Compliance Assistance Programme (CAP) dependent on annual increase
The CAP funding (including support costs) in the May 2017 report was estimated at US$ 34.8 million for the triennium 2018-2020, based on an annual 3% increase. CAP funding for the triennium 2018-2020 would be US$ 32.8 million with zero percent increase per annum, and US$ 36.9 million with 6% increase per annum, i.e., each 3% increase in CAP funding would add about US$ 2 million to the total funding requirement

· Based on the specific requests for scenarios from OEWG-39, the RTF estimated the cumulative impacts of the following scenarios to the total funding requirement for the period 2018-2020:

· For HPMPs/HPPMPs:

· Planned versus actual funding reduction

· ExCom-79 decisions

· Planned HPMPs exceeding 35% reduction target cancelled

· For Non-Investment and Supporting Activities:

· Deferring any further HCFC demonstration projects

· Varying CAP increases

The financial implications of a number of changes for the total funding requirement range are given in the table below, starting with the total funding requirement determined in the May 2017 report. In a first instance certain activities are subtracted, resulting in a different total funding requirement range. This is followed by a number of steps or scenarios (1, 2, 3 and 4) for HPMP stage II activities (with the average value for HPMP funding and the decrease in comparison to the May 2017 HPMP funding also given in the table).
	Sequential, cumulative impacts of requested funding scenarios from OEWG-39 to the May 2017 RTF report estimates
	HPMP funding

(US$ million)
(reduction compared to          May 2017 report)
	Range of  total funding requirement

(US$ million)

	Funding determined in the May 2017 report
	406.3
	602.7-748.9

	Various changes compared to May 2017 report
(no stage III, no demo HCFC, 2 tranches HPPMP)
	
	584.2-653.4

	1) Rescaling of planned activities as determined in the May 2017 report
	388.4
(17.9)
	568.7-632.8

	2) Impact of ExCom-79 on the (rescaled) funding as determined in the May 2017 report
	375.9
(30.4)
	558.9-617.8

	3) Maintain sets of planned activities for countries with approvals not achieving 35% reduction
	341.4
(64.9)
	529.0-578.5

	4) Additional planned activities for a precise 35% reduction for these countries (in row above)
	325.0
(81.3)
	514.7-560.0


1
Introduction

1.1
The Process 



Decision XXVIII/5 of the Twenty-eighth Meeting of the Parties requested the Technology and Economic Assessment Panel (TEAP) to prepare a report for submission to the 39th Meeting of the Open Ended Working Group (Bangkok, July 2017). Decision XXVIII/5 specified the issues the Panel should take into account and directed the TEAP, in undertaking this task, to consult widely with relevant persons and institutions and other relevant sources of information deemed useful.  The TEAP established the Decision XXVIII/5 (Replenishment) Task Force to prepare the report on the 2018-2020 replenishment of the Multilateral Fund, in consultation with the full TEAP membership. 

The final TEAP Replenishment Report was published by UNEP in May 2017 as part of the TEAP Progress Report (i.e., Volume 4 of the May 2017 Progress Report). At the 39th Meeting of the Open Ended Working Group (Bangkok, July 2017), parties requested a Supplement Report to be presented at the MOP-29 Meeting (Montreal, November 2017), to enable the 29th Meeting of the Parties to take a final decision on the appropriate level of the 2018-2020 Replenishment of the Multilateral Fund (MLF).

1.2
The Contact Group on Replenishment

During the OEWG-39, the TEAP Replenishment Task Force (RTF) presented its report “Assessment of the Funding Requirement for the Replenishment of the Multilateral Fund for the period 2018-2020”. A Contact Group was established to consider the report, and to formulate any additional requests for a supplementary study.

The Contact Group included representatives of many non-Article 5 and Article 5 Parties and was co-chaired by Mr. Davinder Lail (United Kingdom) and Mr. Augustin Guevara Sanchez (Mexico). The Contact Group held a number of sessions, which were attended by members of the TEAP RTF and by representatives of the MLF Secretariat, as resource persons.

During the discussions, the members of the Contact Group received clarification and additional information from TEAP Task Force members. The Contact Group then discussed a number of topics and agreed on a number of issues that it believed should be clarified and elaborated in a supplementary report.

On the basis of the discussions in the Contact Group, the OEWG-39 agreed to ask the TEAP to elaborate on a specific group of issues in a Supplement Report to its May 2017 RTF Report, to be presented at MOP-29. The specific elements, for which elaboration was requested, were given in the report of OEWG-39 and are given below (as well as in Annex 1 of this document):
Summary of suggestions for elaboration in the supplementary Technology and Economic Assessment Panel task force report

The Open-ended Working Group at its thirty-ninth meeting agrees to request the Technology and Economic Assessment Panel, in presenting its supplementary report to the Twenty-Ninth Meeting of the Parties:

(a)
To discuss and present results related to the following overall questions: 

1. Elaboration on paragraph 3 of the Terms of Reference as expressed in decision XXVIII/5: “That the Technology and Economic Assessment Panel should provide indicative figures of the resources within the estimated funding required for phasing out HCFCs that could be associated with enabling Article 5 parties to encourage the use of low-GWP or zero-GWP alternatives and indicative figures for any additional resources that would be needed to further encourage the use of low-GWP or zero-GWP alternatives”;

2. To present cost effectiveness figures in MT, ODP-tonnes and CO2 equivalent

3. To give a clearer distinction between costs associated with HCFC-related and HFC-related activities;
4. To present a scenario comparing previously approved projects with business plan estimates on an annual basis in relation to determining uncertainty for planned activities;
5. To account for recent ExCom decisions. 

(b) 
To elaborate on the funding components for HPMPs (Chapter 3):

6. With scenarios considering:
a. HPMP stage III implementation activities in particular according to existing commitments in the servicing sector;
b. The deferring of stage III activities to the next triennium.
7. The deferring to the next triennium of non-LVC and LVC planned activities which are not necessary to meet the 35% phase-out target. 

(c)
To take into account the HCFC production phase-out (chapter 4):

8. Concerning the China HPPMP stage II plan and the related ExCom assumptions in the upcoming ExCom-80 meeting;
9. In case of different scenarios involving 2 tranches in the 2018-2020 triennium.
 (d) 
Regarding the non-investment and supporting activities (chapter 5):

10. To give further thought on how to account for parties with an accelerated phase-out in the HPMP stage II implementation;
11. To give further thought on taking into account HPMPs stage III (for parties wishing to achieve the 67.5% and further reductions steps earlier);
12. To consider a scenario deferring stage III activities to the next triennium;
13. To consider (1) a scenario where there is no annual increase to CAP and (2) a scenario where there is an increase of more than 3% to CAP;
14. To consider a scenario where there are no HCFC demonstration projects;
15. To consider scenarios where HPMP stage III preparation activities in particular are undertaken according to existing commitments in the servicing sector.

(e)
Regarding HFC phase-down enabling activities (chapter 6)

16. To further disaggregate the cost of enabling activities with respect to the different elements addressed.
(f) 
Regarding HFC-23 mitigation (chapter 7)

17. To develop a scenario involving the closure of HCFC-22 production plants to deal with HFC-23, with or without existing incineration facilities, taking into account (closure of) swing plants as one of the possible alternatives to control HFC-23 emissions. 
1.3 
Structure and procedure for the completion of the Supplement Report

The TEAP RTF has prepared this Supplement Report to address the specific questions agreed by the OEWG-39. This report has been structured in such a way that the questions have been sorted in specific groups, which are dealt with in the chapters of this report as outlined below:
Chapter 2
Overall questions to the report

Chapter 3
Elaboration on the funding components for HCFC Phase-out Management Plans (HPMPs)

Chapter 4
Accounting for the HCFC Production Phase-out

Chapter 5
Non-investment and supporting activities

Chapter 6
HFC phasedown enabling activities

Chapter 7
HFC-23 mitigation
Chapter 8
Summary of funding amounts calculated for various scenarios
Annex 1 
Summary of suggestions for elaboration in the supplementary Technology and Economic Assessment Panel Replenishment Task Force report
Annex 2
Calculation of planned amounts up to 35%
After the report had been drafted it was reviewed by the RTF in the period 15-19 September 2017; the MLF Secretariat was also requested to review the report in this period, for the purpose of the consistency of the report with ExCom approvals, related data and business planning. A second order draft of the report was then sent out for TEAP review (21-26 September 2017). The final report was subsequently submitted to the UNEP’s Ozone Secretariat during the last week of September 2017 for posting on its web site (first as an advance, then as a final version). 
2  
Overall questions to the report
This chapter discusses and presents results related to the following overall questions:

1. Elaboration on paragraph 3 of the Terms of Reference as expressed in decision XXVIII/5;
2. To present cost effectiveness figures in ODP-tonnes, metric tonnes and tonnes CO2 equivalent;

3. To give a clearer distinction between costs associated with HCFC-related and HFC-related activities;

4. To present a schedule comparing previously approved projects with business plan estimates on an annual basis in relation to determining uncertainty for planned activities; and

5. To account for recent ExCom (ExCom-79) decisions
. 

2.1 
Paragraph 3 in the Terms of Reference in Decision XXVIII/5
The TEAP RTF, in request (1), was asked to elaborate on paragraph 3 of the Terms of Reference as described in decision XXVIII/5, which says: “That the Technology and Economic Assessment Panel should provide indicative figures of the resources within the estimated funding required for phasing out HCFCs that could be associated with enabling Article 5 parties to encourage the use of low-GWP or zero-GWP alternatives and indicative figures for any additional resources that would be needed to further encourage the use of low-GWP or zero-GWP alternatives”.
When dealing with HCFCs, the RTF has taken into account the approved and planned HPMP activities and the data published by the MLF Secretariat. In the case of approved activities, the RTF did not analyse the specific choice of alternatives in the scheduled conversion away from HCFCs, but rather, it only looked at the overall funding obligations for HPMPs after 2016 and specifically in the triennium 2018-2020. From information gained, a minor (small) percentage concerned conversion to hydrofluorocarbons (HFCs), e.g., HFC-245fa in foams, which is not significant from an overall impact point of view. There will also be certain small funding disbursements planned that are related to choices to non-low GWP alternatives in HPMPs stage I made in earlier years. 
It would be very likely that significant investments have already been made by industry to convert manufacturing processes to the original agreed technologies. Therefore, the RTF did not analyse how a change of these earlier choices may have further encouraged the use of low-GWP alternatives. 
The “Business Plan”
 already accounts for a variety of decisions designed to encourage the use of low-and zero-GWP alternatives (e.g., decision 74/50 (b) (i) c, 74/50(c)(iii), 74/50(c)(iv), 74/50(c)(vii), decision 60/44(f)(iv), 60/44(f)(vii), decision 72/41, and other relevant decisions). Where it concerns planned activities, the RTF has studied the Business Plan; it is impossible to derive CE values on the basis of a certain portion of phase-out of one chemical in a HPMP (see section 2.2 for details). The RTF, therefore, was unable to quantify and provide indicative figures for additional resources that may be needed in the triennium 2018-2020. In principle one can say that further encouraging might mean that more non-investment type of support would be needed for certain countries (industries) regarding the choice for certain low or zero-GWP conversions, so that other (high-GWP) alternatives can be avoided. On the basis of the above, the RTF estimated a range of US$ 0-10 million for additional HPMP demonstration projects in the May 2017 RTF Report, and an estimated range of US$ 13.5-20.2 million in Chapter 6 of this report on HFC enabling activities which included a certain amount for demonstration projects.

2.2 
Cost effectiveness figures in various units

Request 2 above says: “to present cost effectiveness figures in MT (tonnes), ODP-tonnes and tonnes CO2 equivalent”. When this request was formulated as such in the Contact Group, it was not defined exactly which cost effectiveness (CE) values it would concern, whether it would refer to HPMPs that have been approved, whether it would refer to planned activities as in the May report, or whether it would refer to an overall estimate.

The RTF has considered this request, noting that the May report, in fact, did not use the CE as a parameter for determining certain amounts of funding. In its May 2017 report, the RTF noted that the applicable CE values for the period 2017-2020 from HPMPs approved in principle varied substantially depending on the country and the specific activity. Furthermore, the CE value used in the Business Plan (where these funding values were based on CE values from approved HPMP activities) could be higher or lower once the planned activities were approved. Given sufficient funding information was available through the year 2020, the RTF did no further analysis on the CE values for the approved in principle and planned activities. Similarly, the overall funding requirements for the period 2018-2020 (combined with the amounts approved in principle or planned) provided sufficient information for estimating indicative funding for future triennia, i.e., 2021-23 and 2024-26.
Nevertheless, to respond to the request and for information purposes, the RTF took the approach of deriving overall, averaged, CE values from HPMPs stage I and stage II as approved for either non-LVC or LVC countries, noting that it is impossible to derive CE values on the basis of a certain portion of phase-out of one chemical in a HPMP. For this reason, CE values were derived for non-LVC and LVC countries from the HPMPs stage I and II, and averaged.

2.2.1 
Non-LVC countries

A number of large size and smaller size non-LVC countries were analysed for funding approved in HPMP stages I and II. Table 2-1 presents the results for the CE values for a large number of non-LVC countries, all expressed in US$ per ODP-tonne (as in MLFS documents), US$ per kg, and US$ per t-CO2-eq. The latter values have been determined using the direct effect of the GWP (using AR4 GWP values) for the HCFCs concerned (where any residual GWP of the alternative was not subtracted). CE values have been calculated on the basis of total funding, i.e., it includes agency support costs (where the support costs vary from 7.5% to a maximum of 13% for UNEP and particularly bilaterals). The mix of countries selected, however, results in good indicative values. 
 Table 2-1 CE values for a number of non-LVC countries in US$ per ODP-kg, per kg and per t-CO2-eq. The average CE values are calculated on a weighted basis, with and without taking into account the HPMPs for China

[image: image2.emf]ARGENTINA Funding ODP-t  tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Phase I 11597593 83.53 1300.91 2118.31 138.843 8.915 5.475

Funding ODP-t  kt CO2 eq

Phase II 10652124 115.19 1447.59 1937.05 92.474 7.359 5.499

Combined 22249717 198.72 2748.50 4055.36 111.965 8.095 5.486

BRAZIL Funding ODP-t  tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Phase I 21027388 220.3 2470.91 2807.36 95.449 8.510 7.490

Funding ODP-t  kt CO2 eq

Phase II 38815539 464.06 5702.00 7352.65 83.643 6.807 5.279

Combined 59842927 684.36 8172.91 10160.02 87.444 7.322 5.890

CHINA Funding ODP-t  tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Phase I 289831680 3445.6 46463.74 69403.89 84.116 6.238 4.176

Funding ODP-t  kt CO2 eq

Phase II 533883629 8714.65 118662.22 178213.73 61.263 4.499 2.996

Combined 823715309 12160.25 165125.97 247617.61 67.738 4.988 3.327

INDIA Funding ODP-t  tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Phase I 22969344 341.77 3391.00 3074.76 67.207 6.774 7.470

Funding ODP-t  kt CO2 eq

Phase II 48315260 769.49 8190.55 8531.69 62.789 5.899 5.663

Combined 71284604 1111.26 11581.55 11606.45 64.148 6.155 6.142

EGYPT Funding ODP-t  tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Phase I 9164414 174 1637.55 1308.15 52.669 5.596 7.006

Funding ODP-t  kt CO2 eq

Phase II 11786341 146.97 2080.24 3298.47 80.196 5.666 3.573

Combined 20950755 320.97 3717.78 4606.62 65.273 5.635 4.548

INDONESIA Funding ODP-t  tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Phase I 13378896 135 1637.27 2076.72 99.103 8.171 6.442

Funding ODP-t  kt CO2 eq

Phase II 8883314 84.33 1145.09 1651.44 105.340 7.758 5.379

Combined 22262210 219.33 2782.36 3728.16 101.501 8.001 5.971

IRAN Funding ODP-t  tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Phase I 10869327 101.3 1271.82 1683.54 107.298 8.546 6.456

Funding ODP-t  kt CO2 eq

Phase II 12279535 225.47 2697.64 3361.75 54.462 4.552 3.653

Combined 23148862 326.77 3969.45 5045.29 70.841 6.427 4.969

MEXICO Funding ODP-t  tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Phase I 19421177 417.3 4019.09 3403.08 46.540 4.832 5.707

Phase II ODP-t  kt CO2 eq

Phase II 11786341 560.53 6590.19 6915.58 21.027 1.788 1.704

Combined 31207518 977.83 10609.28 10318.66 31.915 2.942 3.024

LEBANON Funding ODP-t  tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Phase I 2682242 20 226.36 260.78 134.112 11.849 10.286

Funding ODP-t  kt CO2 eq

Phase II 4498093 41.16 544.45 764.22 109.283 8.262 5.886

Combined 7180335 61.16 770.82 1025.00 117.402 9.315 7.005

PERU Funding ODP-t  tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

310111 3.74 51.73 75.97 82.917 5.995 4.082

TOGO Funding ODP-t  tonnes kt CO2 eq

692650 7 127.27 230.36 98.950 5.442 3.007

ALL NON-LVC CTRS fundingODP-tonnes tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Total 1082844998 16071.39 209657.62 298469.49 67.377 5.183 3.747

ALL MINUS CHINA fundingODP-tonnes tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Total 259129689 3911.14 44531.65 50851.88 66.254 5.786 5.053


The following observations can be made from Table 2-1:

· For a number of non-LVC countries the various types of CE values have been determined for HPMP stage I and HPMP stage II, as well as the average CE values for HPMP stages I and II combined. The range of CE values varies from US$ 1.78 to 11.85 per kg or US$ 1.70 to 10.29 per tonne of CO2-eq.It can be observed that the range for the CE values is very wide, which is related to the very different levels of HCFC consumption in the various non-LVC countries.
· In estimating the CE values, it was not possible to differentiate for the individual HCFCs per country (as contained in HPMP plans), for which reason it is difficult to derive CE values for each specific chemical, in particular for HCFC-141b, -142b and -22.

· The final rows in the table give the determined average CE values for all the non-LVC countries together on a weighted basis (i.e., the amount of ODP tonnes for each country as a proportion of the overall total was used to apply weighting ratios). In this case, one row shows the average CE values for stages I and II HPMPs for all non-LVC countries including China, and the final row the average CE values for all non-LVC countries excluding China.    

· A preliminary average CE value for non-LVC countries is around US$ 67.4 per ODP-kg, US$ 5.18 per kg and 3.75 per t CO2-eq. Excluding China yields slightly different values the CE per ODP-kg and per kg, a much higher value for the CE per t CO2-eq., i.e., US$ 66.3 per ODP-kg (a small decrease), US$ 5.79 per kg and US$ 5.05 per t CO2-eq., which is about a 12% increase in US$ per kg and a 35% increase in US$ per t CO2-eq. The reason for the difference is the differences in GWPs for the different HCFC chemicals in the “country mix” per kg.     

2.2.2 
LVC countries

A number of LVC countries were analysed concerning the funding approved in HPMPs stage I (and for some, also in HPMPs stage II).

Table 2-2 presents the results for a large number of these LVC countries, as well as the average, weighted CE value for the stages I (and II) of HPMPs expressed in US$ per ODP-kg, US$ per kg, and US$ per t CO2-eq. CE values have been calculated on the basis of total funding, i.e., it includes agency support costs (which vary from 7.6% to a maximum of 13% for UNEP and in particular for bilateral projects). The mix of countries selected provides good, indicative values.  

Table 2-2 CE values for a number of LVC countries in US$ per ODP-kg, per kg and per t CO2-eq., as well as the average calculated on an ODP tonnes weighted basis

[image: image3.emf]COST EFFECTIVENESS LVCs (with agency support costs included)

ANGOLA Funding ODP-t  tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Phase I 191840 1.59 28.91 52.33 120.654 6.636 3.666

Funding

Phase II 967280 9.18 166.91 302.11 105.368 5.795 3.202

Combined 1159120 10.77 195.82 354.43 107.898 5.934 3.279

ARMENIA Funding ODP-t  tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Phase I 649121 2.23 33.00 51.54 291.086 19.670 12.594

Funding

Phase II 238196 3.26 59.27 107.28 73.066 4.019 2.220

Combined 887317 5.49 92.27 158.83 232.559 15.469 9.809

CAMBODIA ODP-t tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Phase I 1772250 15 272.73 493.64 118.150 6.498 3.590

COSTA RICA

Phase I 1240037 18.93 205.97 214.65 65.506 6.020 5.777

CUBA

Phase I 1878592 19.26 205.18 214.05 97.539 9.156 8.776

JAMAICA

Phase I 708844 8.13 114.82 172.02 87.189 6.174 4.121

MALDIVES Phase I

Phase I 1219900 3.7 67.27 121.76 329.703 18.134 10.019

MONGOLIA Phase I

Phase I 413580 1 18.18 32.91 413.580 22.747 12.567

RWANDA Phase I

Phase I 312000 1.44 26.27 41.78 216.667 11.875 7.468

SERBIA Phase I

Phase I 1050408 2.94 53.45 96.75 357.282 19.650 10.857

SWAZILAND Phase I

Phase I 955344 6.19 61.64 56.33 154.337 15.500 16.961

UGANDA Phase I

Phase I 182685 0.07 1.27 2.30 2609.786 143.538 79.303

Funding ODP-t tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Total 92.92 1314.88 1959.45 130.999 9.229 7.079


The following observations can be made from Table 2-2:
· For a number of LVC countries the various types of CEs have been determined for HPMP stage I (and HPMP stage II in two cases). The range of the CE values varies from US$ 5.93 to 143.54 per kg or US$ 3.28 to 79.30 per t CO2-eq.  It can be observed that there is a very wide range for the CE values, which is directly related to the HCFC consumption in LVC countries that can range from a few tonnes to 360 tonnes.
· The final row derives the average CE values for all the LVC countries considered on a weighted basis (i.e., based on the amount of ODP tonnes approved for a country). The average CE values calculated for these LVC countries are US$ 131 per ODP-kg, US$ 9.23 per kg and US$ 7.08 per t CO2-eq.       

2.2.3 
Different way of determining CE values
In the above method, CE values have been derived on the basis of averaging, using the amounts of ODP tonnes approved. However, CE values can also be derived using the amounts of funding approved for a country, which would give (quite) different results because funding is a “negotiated derivative” of the ODP tonnes approved for an HPMP.

Table 2-3 shows the results, where the ODP weighted results have been taken from Tables 2-1 and 2-2. CE values increase by 3-12% for non-LVC countries, by 45% in the case of LVC countries compared to the earlier method of determining CE values. Due to the fact that the funding weighted results are somewhat sensitive to other factors that are not related to the percentage reduction approved in ODP tonnes, these values also seem to be suitable for determining CE values while considering the HPMPs approved so far for non-LVC countries. For LVC countries, the weighted CE value derived is about 30% higher (i.e., higher costs per unit phased out), however, it is difficult for the RTF to derive recommendations for LVC countries taking into account the funding guidance given for LVC countries of specific sizes (see also Table 2-5). 
Table 2-3  Average CE values for non-LVC and LVC countries in US$ per ODP-kg, per kg and per t CO2-eq., weighted on the basis of ODP tonnes approved and on the basis of the funding amounts approved. 


[image: image4.emf]ALL NON-LVC COUNTRIES funding tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Total 1082844998 209657.62 298469.49 67.377 5.183 3.747

Total (funding wtd.) 69.534 5.334 3.827

ALL NON-LVC MINUS CHINA funding tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Total 259129689 44531.65 50851.88 66.254 5.918 5.094

Total (funding wtd.) 75.241 6.431 5.417



[image: image5.emf]LVC COUNTRIES funding tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Total     ODP-t wtd 1314.88 1959.45 130.999 9.229 7.079

Total     Fund wtd 11780077 212.854 13.418 9.107


2.2.4 
Determining CE values on the basis of including or excluding agency support costs

In principle, once CE values started to be derived in the 1990s on a project- by- project basis, they were derived without considering agency support costs. In the above analysis, CE values have been derived on the basis of averaging, using as a basis the amounts of ODP tonnes per country. The CE values were all determined including agency support costs. However, one can also average using the various amounts of funding approved for countries, while excluding agency support costs. This would be expected to give roughly 7-13% lower cost effectiveness values (as per the percentage agency support costs). 
Table 2-4 shows the results for CE values excluding agency support costs (where the ODP weighted results have been taken from Tables 2-1 and 2-2). By excluding agency support costs, the CE values decrease by 3-12% for non-LVC countries, and by 45% in the case of LVC countries, compared with CE values derived on an ODP weighted basis and including agency support costs.  
Table 2-4  Average CE values for non-LVC and LVC countries in US$ per ODP-kg, per kg and per t CO2-eq., for the two cases (1) with and (2) without agency support costs


[image: image6.emf]ALL NON-LVC COUNTRIES funding tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Total with support costs 1082844998 208988.94297942.2699 67.377 5.183 3.747

w/o support costs 1010975606 62.741 4.826 3.489

ALL NON LVC MINUS CHINA funding tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Total with support costs 548961369 43862.97650324.65751 66.254 5.918 5.094

w/o support costs 477091977 61.205 5.467 4.706


[image: image7.emf]ALL LVC funding tonnes kt CO2 eqUS$/ODP-kg US$/kg US$/t CO2

Total with support 11780077 1314.88 1959.45 130.999 9.229 7.079

Total w/o support 10816046 120.261 8.489 6.524


In Table 2-4 results are presented for both non-LVC (including and excluding China) and LVC countries. One can see that the cost effectiveness values decrease by 7-8% for non-LVC countries, by about 8% for LVC countries (i.e., lower costs per ODP-kg, per kg etc.). These are percentages that can be expected on the basis of the percentages support for the different implementing agencies as well as the (percentage) involvement of various agencies in the different HPMPs. 
2.2.5 
Determining CE values on the basis of amounts determined for various LVC country sizes by the ExCom

It is interesting also to look at the (ExCom guidance for) CE values, excluding agency support costs, as used by the ExCom for the various sizes of LVC countries, which can be added together (multiplied by the number of countries in each consumption class, see Table 2-5) and averaged. 
Since the values per country in t CO2-eq. are lacking from the available information, only values in US$ per ODP kg and per kg can be derived. The value of US$ 9.72 per kg is 14% higher than the value derived on the basis of a number of LVC countries, but this will be due to the higher percentage of very low volume LVCs (consumption is generally in the order of a few tons only) in the total in Table 2-5.
Table 2-5  CE values for LVC countries in US$ per ODP-kg and per kg based on the ExCom guidance numbers for the different sizes of LVC countries, multiplied by the number of countries and averaged (values from ExCom 74/50)

[image: image8.emf]Consumption 

(mt)

Funding total 

phase-out

Number of 

countries

Total 

funding

Total baseline 

(HCFC-22) 

(mt)

CE ($/kg) CE ($/ODP 

kg

>0 <15 587,500 21 12,337,500      97.81                126.13          2,293.30     

15 <40 750,000 16 12,000,000      419.44               28.61            520.17        

40 <80 800,000 14 11,200,000      910.91               12.30            223.55        

80 <120 900,000 11 9,900,000        1,100.48            9.00             163.57        

120 <160 950,000 9 8,550,000        1,280.19            6.68             121.43        

160 <200 1,000,000 3 3,000,000        567.21               5.29             96.16          

200 <320 1,600,000 12 19,200,000      3,157.95            6.08             110.54        

320 <360 1,800,000 2 3,600,000        677.71               5.31             96.58          

Total 79,787,500   8,211.71         9.72            176.66      


In conclusion, the average rounded CE values vary between US$ 5.2 and 5.9 per kg for non-LVCs, and between US$ 9.3 and 9.7 per kg for LVC countries. Translated into climate terms (not contained in Table 2-5), they vary between US$ 3.8 and 5.1 per t CO2-eq. for non-LVC countries, and are about US$ 7.0 per t CO2-eq. for LVC countries.

It should be emphasized that the CE value is dependent on specific country circumstances and for specific stages of the phase-out process. This implies that the considerations on CE as given above have relative value for the future. As HPMPs focus more and more on dealing with refrigeration and AC servicing only, the more that  CE values (at least for non-LVC countries) will settle in the range of US$ 3.5-5.1 per kg (based on the ExCom established value of US$ 4.8 per kg for servicing as per ExCom decision 74/50), and dependent on the specific country circumstances. 
2.3 
Distinction between costs associated with HCFC and HFC related activities

At OEWG-39, parties requested that the RTF give a clearer distinction between costs associated with HCFC-related and HFC-related activities in its supplementary report. 
In its May 2017 report, the RTF attempted to make clear by the organisation of the chapters within its report the distinction between HCFC- and HFC-related activities related to the various components that make up the total funding requirement for the 2018-2020 triennium as follows:

· Funding for HCFC consumption phase-out activities;

· Funding for HCFC production phase-out;

· Funding for non-investment components and supporting activities;

· Funding for HFC phasedown enabling activities; and 

· Funding for HFC-23 mitigation activities.

The above funding components were then discussed in separate chapters in the May 2017 report. Chapter 5 of that report, “Funding requirements for non-investment and supporting activities for the 2018-2020 replenishment period and beyond,” specifically focused on HCFC-related activities, noting that HFC-related activities (e.g., project preparation, demonstration projects, supporting activities) for the 2018-2020 triennium and future triennia, 2021-2023 and 2024-2026, would be considered in Chapter 6 on HFC enabling activities.

Chapter 6 provided a range of funding for HFC activities in the 2018-2020 triennium for:

· Non-investment projects including: 
1) project preparation requests for HFC management plans/national strategies, and 
2) demonstration projects for countries aiming to fast-track the phase-down of HFCs; and 

· Investment projects that encourage the use of low-GWP or zero-GWP alternatives.

Chapter 9, “Indicative funding requirements for 2021-2023 and 2024-2026,” provides funding estimates after 2020 for HCFC- and HFC-related activities, following essentially the same funding components used for the triennium 2018-2020. However, given that cost guidelines for HFC phasedown activities are still to be developed by the ExCom, the funding requirements for HFC phasedown remain uncertain. Therefore, the RTF did not include estimated costs for related activities in the next two triennia 2021-2023 and 2024-2026. Examples of probable funding considerations for HFC phasedown in future triennia include:

· strengthening of the regional networks and NOUs in the development of their institutional framework for future ratification, implementation, and compliance of the Kigali Amendment;

· funding for additional implementing agencies’ support to Article 5 countries regarding the phasedown of HFCs while HPMPs are still under implementation; and

· funding for any additional meetings or related work to support the ExCom’s activities related to the Kigali Amendment.
2.4 
Schedule comparing previously approved activities with business plan estimates

At OEWG-39, parties requested the RTF in its supplementary report “to present a schedule comparing previously approved projects with business plan estimates on an annual basis in relation to determining uncertainty for planned activities.” In order to respond to this request, the RTF obtained information from the MLF Secretariat on the total approved funding for specific activities in a certain year, as well as the total planned funding for these activities in the Business Plan. 
This information was available for each year from 2016 going back to 2000. From the numbers obtained in this way, ratios can be calculated between the funded or approved amounts and “planned for funding” amounts for these activities, and these ratios can be averaged per period of three years (e.g., 2014-2016, 2011-2013 etc. through 2002-2004) to provide a comparison. The various results are shown in Table 2-6.  

Table 2-6 Values for approved and planned activities, ratio of approvals and planned activities and percentages per three year periods (US$)
[image: image1.emf]








The average percentage of approved funding compared to the planned funding for all years from 2005 through 2016 is 83.24% (see Table 2-6). This implies that, overall and on average, the approved funding for activities is about 17% less than the amounts estimated in the Business Plan. The RTF has also looked at the uncertainty in this average value. By taking all the differences in planned and approved funding for activities for the years 2005-2016, an average deviation of 13.5% can be calculated . Using the latter value, the range of percentages difference in the approved, in principle, funding for activities as compared to the funding for planned activities is between about 70% and 97%. This range will be used in the calculations described in section 3.2 below.

2.5 
Taking into account recent ExCom decisions

At OEWG-39, parties requested the RTF in its supplementary report to account for recent ExCom decisions. During the 79th meeting of the ExCom in July in Bangkok, a number of HPMPs stage II were approved for Argentina, Egypt and Angola, with funding tranches approved for the first two countries in the period from 2017 until a year in the triennium after 2020. The May 2017 RTF report estimated the total funding requirement for HPMPs (see Table 3.5 in that report), excluding HPMP stage III funding for the period 2018-2020. Both the May 2017 estimate and the updated estimate based on the decisions made at ExCom-79 are provided in Table 2-7 below. While the estimations for the funding requirement for 2017 have also been determined, only estimations related to the 2018-2020 triennium have been further studied and are analysed below. 

In Table 2-7, the upper and lower value of the funding range for the planned activities has been given, which is the value determined +/- 15% uncertainty, consistent with the procedure in the May 2017 RTF report. The range of total HPMP funding requirements is also given in Table 2-7, using the uncertainty in the funding for planned activities.  

Table 2-7 (a) (b) HPMP funding values calculated without ExCom decisions taken at ExCom-79 (May 2017 report, see first table (a)) and with the decisions taken at ExCom-79 (see second table (b))

[image: image9.emf]Status May 2017 (US$ million)

2018-20 2017

min max

Non-LVCs approved 289.408 84.003

Non-LVCs planned 82.534 97.099 111.664 13.507

Non-LVCs total 371.942 386.507 401.072 97.510

LVCs approved 6.132 2.727

LVCs planned 10.023 0.890

LVCs total 16.155 3.617

Extra amount countries  1.904

HPMP verification 1.766

Total (range) 391.767 406.332 420.897 101.127


                  Uncertainty applied of +/- 14.565 US$ million


[image: image10.emf]Status after ExCom July 2017 (US$ million)

2017

min max

Non-LVCs approved 296.239 91.046

Non-LVCs planned 63.007 74.126 85.245 9.439

Non-LVCs total 359.246 370.365 381.484 100.485

LVCs approved 6.132 3.209

LVCs planned 9.797 0.649

LVCs total 15.929 3.617

Extra amount countries  1.904

HPMP verification 1.766

Total (range) 378.845 389.964 401.083 101.127

2018-20


                  Uncertainty applied of +/- 11.119 US$ million

Funding decisions from ExCom-79 reduced the funding for the planned activities for non-LVC countries from a total of US$ 97.1 million to US$ 74.1 million for the triennium 2018-2020, a reduction of US$ 23.0 million. 
For the LVC countries, decisions from ExCom-79 reduced the funding for planned activities by US$ 0.23 million for after 2017, by moving this planned funding amount into the approved funding for the year 2017.

The above means that by taking into account the decisions from ExCom-79, the total funding requirement for HPMPs (excluding any HPMPs stage III) in the triennium 2018-2020 has decreased from an estimated range of US$ 391.8-420.9 million to US$ 378.9-401.1 million (total averages are given in Table 2-7 as well), a decrease of US$ 12.9 to 19.8 million, or US$ 16.4 million on average.

As discussed in section 2.4 above, approved funding for activities has historically been lower than the planned funding for the same activities. The impact of this on the overall funding (including on the status after ExCom-79 as given in Table 2-7) is further considered in section 3.2 below. This (rescaling) will also have consequences for the reduction of the funding for HPMP activities as a result of ExCom-79 decisions. 
3  
Elaboration on the funding components for HPMPs
This chapter elaborates on the funding components for HPMPs, in particular:

1. With scenarios considering
a. HPMP stage III implementation activities in particular according to existing commitments in the servicing sector;

b. The deferral of stage III activities to the next triennium; and
2. The deferral to the next triennium of non-LVC and LVC planned activities to the next triennium, not necessary to meet the 35% phase-out target.
3.1
Scenarios considering HPMP stage III 
At OEWG-39, parties requested that the TEAP RTF in its supplementary report consider scenarios and potential impacts to the funding components for HPMPs stage III implementation activities, in particular according to existing commitments in the servicing sector.

In many non-LVC countries the only activities still to be funded after HPMP stage II relate to the servicing sector. Existing commitments could be considered as keeping equipment running during its normal lifetime. Stage II HPMPs have been approved to achieve a reduction in consumption from about 10-15% to around 67.5% of the baseline consumption (the latter reduction percentage being the one for 2025), and to even higher percentage than 80% for a number of countries. However, the servicing of equipment using HCFC-22 still to be funded varies from 10% to more than 50% of a country’s consumption of HCFC-22. Assuming that funding of servicing would have a CE of US$ 4.8 per kg (as per current ExCom guidance, excluding agency support costs, i.e., at least US$ 5.1 per kg including agency support costs) this would in principle cost about the same as the approved HPMPs stages I and II at a CE of US$ 5.2 per kg about the same (including agency support costs). Therefore, parties may wish to consider further investigating the phase-down of servicing activities, and whether these activities could be performed at a different, lower, CE value in the future than the one currently prescribed of US$ 4.8 per kg (taking into account that the CE for the servicing sector increased from US$ 4.5 to US$ 4.8 per kg for stage II HPMPs).      
3.2
Scenarios considering the deferral of stage III activities
OEWG-39 requested the TEAP RTF “to elaborate on the funding components for HPMPs with scenarios considering the deferring of stage III activities to the next triennium.” 
In the May 2017 report, the RTF considered a few HPMP stage III activities as they were given in the Consolidated Business Plan for the triennium 2018-2020. It concerns an amount of US$ 136,000 for Armenia and Moldova for a first part of a stage III HPMP, as well as an amount for 2020 for China of US$ 70.8 million. In both cases the remainder of the HPMP stage III funding was expected to be approved after 2020, i.e., US$ 295,000 for Armenia and Moldova, and US$ 283.2 million for China. The HPMP stage III planned funding was presented in the May 2017 RTF report as a range between zero to US$ 70.95 million, and not as a fixed amount. This amount does not appear in the consideration of funding scenarios described in section 3.3 below.

Deferral of HPMP stage III activities to the triennium 2021-2023 would lower the high end of the range of the funding requirement from US$ 70.95 million to zero.
3.3
Deferral of planned activities not needed for 35% reduction to the next triennium
In order to calculate the impact on the estimated funding requirements in the 2018-2020 triennium of deferring planned activities that are not necessary to meet the phase-out target of a 35% reduction from baseline, i.e., that would yield larger reductions than 35%, the RTF decided on the following approaches:

1. To re-calculate the funding amount required during the triennium 2018-2020 for the planned activities, taking into account the reduction percentage and the uncertainty range as determined in section 2.4. In a first instance, this means that the total HPMP funding requirement calculated in the May 2017 report will change. The impact of ExCom-79 decisions on the HPMP funding as given in section 2.5 (Table 2-7) will also further change by applying the uncertainty range to estimate actual funding requirements (see section 3.3.1).   

2. To calculate the impact of the decisions on HPMP funding taken at ExCom-79. As mentioned, a first description can be found in section 2.5 (a decrease of US$ 12.9 to 19.8 million, i.e., US$ 16.4 million averaged, was calculated for the funding requirement for HPMPs in the next triennium, compared to the funding calculated in the May 2017 report). 
3. Taking the “after ExCom-79” HPMP funding requirement (as under (2)), calculations have been made to estimate the deferral of the “activities not needed for a 35% reduction to the next triennium”. A two-step approach was followed: 
a. In a first instance, all planned activities for countries that already had approved activities resulting in a 35% reduction or more were removed from the calculation. Here one should take into account that the 35% reduction should be achieved by 1 January 2020 and that, under normal circumstances, funding for higher reductions could take place in the year 2020. However, the request is to calculate what it means to defer all the activities (interpreted in this report to refer to “funding”) not needed for the 35% reduction to the next triennium. The planned activities (including the funding requirement) for individual countries that had no approved reduction percentage of 35% were kept as a whole (for all years, 2017 through 2020) even when the total of these planned activities would result in a reduction (much) higher than 35%, assuming that the whole of these planned activities could not be simply split in parts (section 3.3.3). 
b. In a second instance, for the countries with the planned activities as considered in the first step, the RTF determined the amount of ODP tonnes that would strictly be needed to achieve the 35% reduction. The ODP tonnes for the planned activities, which would result in a certain reduction after the 2018-2020 triennium include the ODP tonnes planned for 2017. Taking the reduction percentage following the planned activities and the consumption reduction percentage of 35%, the necessary funding requirement for achieving exactly 35% was calculated by determining the part of the planned 2017-2020 funding requirement using the ratio of reduction percentages (section 3.3.4).
The steps described under 3(a) and 3(b) are demonstrated in Annex 2, using the approved and planned reduction percentages (and funding) for a number of non-LVC countries, which show the procedure followed in individual country “cases”.   
3.3.1
Recalculating the HPMP funding requirement
Table 3-1 Funding for HPMPs as calculated in the May 2017 report (Table 3-5 in that report and Table 2-7 (a) in the present report); small differences in funding distribution between non-LVCs and LVCs)

[image: image11.emf]Status May 2017 (US$ million)

2018-20 2017

min max

Non-LVCs approved 289.408 84.003

Non-LVCs planned 82.534 97.099 111.664 13.507

Non-LVCs total 371.942 386.507 401.072 97.510

LVCs approved 6.132 2.727

LVCs planned 10.023 0.890

LVCs total 16.155 3.617

Extra amount countries  1.904

HPMP verification 1.766

Total (range) 391.767 406.332 420.897 101.127


        Uncertainty applied of +/- 14.565 US$ million

Table 3-2 Funding for HPMPs as calculated in the May 2017 report, incorporating reduction percentages for the funding for planned activities

[image: image12.emf]May 2017 with difference approach for planned funding

(US$ million) 2017

min max

Non-LVCs approved 289.408 84.003

Non-LVCs planned 69.911 80.835 91.758 11.245

Non-LVCs total 359.319 370.243 381.166 95.248

LVCs approved 6.132 2.727

LVCs planned 7.217 8.345 9.472 0.741

LVCs total 13.349 14.477 15.604 3.468

Extra amount countries  1.904

HPMP verification 1.766

Total (range) 376.338 388.389 400.440 98.716

2018-20


        Uncertainty applied of +/- 12.051 US$ million

Table 3-1 lists the funding estimates as given in the May 2017 report. It gives a range for the planned activities around the amount of US$ 97.1 million. Table 3-2 gives the planned activities for both non-LVC and LVC countries, taking into account the ratio in funding between approved and planned activities as derived in section 2-4. 
The funding for planned activities for non-LVC countries decreases by about US$ 16 million, and decreases for the planned activities for LVC countries by about US$ 1.7 million compared with the May 2017 report. As a result, the total funding requirement for HPMP activities is calculated about US$ 18 million lower than in the May 2017 report.

3.3.2
Impact of ExCom-79 decisions 
Table 3-3 Funding for HPMPs, including the reduction in funding for planned activities (Table 3-2), and incorporating the impact of ExCom-79 decisions

[image: image13.emf]Status after ExCom July 2017 (US$ million)

2017

min max

Non-LVCs approved 296.238 91.046

Non-LVCs planned 53.370 61.710 70.049 7.858

Non-LVCs total 349.608 357.948 366.287 98.904

LVCs approved 6.132 3.209

LVCs planned 7.054 8.157 9.258 0.540

LVCs total 13.186 14.289 15.390 3.749

Extra amount countries  1.904

HPMP verification 1.766

Total (range) 366.465 375.906 385.347 102.653

2018-20


      Uncertainty applied of +/- 9.941 US$ million
In section 2.5, the impact on HPMP funding of ExCom-79 decisions has been calculated compared to the May 2017 report. Table 3-3 gives comparable results but also including the modified approach with the reduced funding for planned activities as given in section 3.3.1. The planned activities funding requirement for both non-LVC and LVC countries is decreased, as can be concluded from a comparison of Table 3-2 and 3-3. The non-LVC approved activities are increased by about US$ 7 million due to the approvals at ExCom-79. The overall result is that the total HPMP funding requirement is about US$ 13 million lower than in section 3.3.1 (with no ExCom-79 approvals) (Note: the total in Table 3-3 is about US$ 30.4 million lower than the HPMP total funding requirement in the May 2017 report, Table 3-1).
3.3.3
Planned approach for countries that have no approvals to achieve 35% reduction
The request to elaborate on the impact of planned funding, and specifically on the amount of planned funding necessary to achieve a 35% reduction from baseline by those countries that had not yet received approvals for funding to achieve 35% or more reduction from the baseline, involved two calculation steps, eventually resulting in the estimated funding to achieve a precise 35% reduction.

All the planned activities for non-LVC countries assumed to have already achieved the 35% reduction or more with the activities approved for them, have been removed from the calculations. The complete set of planned activities was maintained in case activities for a non-LVC country were approved at a value < 35%; this reduces the originally estimated non-LVC amount by about US$ 34.3 million. There is no impact on the planned activities for LVC countries, because planned activities in totality are needed here to achieve the 35% reduction. Also, as can be seen in table 3-4, the funding requirement for approved activities for both non-LVC and LVC countries does not change compared to Table 3-3.
As mentioned, the result is that the total HPMP funding requirement, compared to the funding requirement given in section 3.3.2 is lower again by about US$ 34 million (Note: the total funding requirement for HPMP activities is now about US$ 65 million lower compared to the requirement as determined in the May 2017 report).   
Table 3-4 Funding for HPMPs with only planned activities for countries that would not achieve 35% reduction with their approved activities after ExCom-79 


[image: image14.emf]Status after ExcCom July 2017 

Only for Plans with <35% reduction, sets of activities (US$ million)

min max

Non-LVCs approved 296.238

Non-LVCs planned 23.703 27.407 31.110

Non-LVCs total 319.941 323.645 327.348

LVCs approved 6.132

LVCs planned 7.054 7.922 8.992

LVCs total 13.186 14.054 15.124

Extra amount countries  1.904

HPMP verification 1.766

Total (range) 336.594 341.368 346.142

2018-20

   
      Uncertainty applied of +/- 4.474 US$ million
3.3.4
Funding strictly needed for countries that have not enough approvals to reach the 35% reduction 
The funding requirement for planned activities can be further decreased, although not significantly, if the value for the planned activities, considered in section 3.3.3, is changed in such a way that for the countries “selected” in section 3.3.3, the total planned funding for the years 2017 and the triennium 2018-2020 (which is assumed to yield a certain reduction percentage larger than 35% by 2020) is reduced in such a manner that it exactly results in a 35% reduction below baseline. As mentioned above, this is done by calculating the percentage difference between approved activities and “approved plus planned” activities and reducing this percentage to result in a 35% reduction from “the approved percentage”. When performing the calculation, it is important to take into account possible planned funding for the year 2017 because this funding directly contributes to the total reduction. 
The planned funding for non-LVC countries is thereby reduced, and this by a further amount of US$ 8.6 million. Compared to the reduction achieved going from the cases in section 3.3.2 to 3.3.3 this is a lower amount, because it only concerns a limited number of non-LVC countries, where only a certain part of the planned activities is removed. 

In the case of LVC countries, the impact is substantial, relative to the importance of a typical HPMP for these countries. This is because HPMPs for many LVC countries were maintained (they were not removed) by the RTF in the calculations presented in section 3.3.3, because they would not be able to achieve the full 35% for compliance with the existing approved HPMP activity. That is to say, most of them almost achieve the 35% reduction target by 2020. As described in that section, these countries are supposed to get a total package of activities that would often achieve much more than a 35% reduction. It is assumed that an activity (a project) cannot be split into separate (small) amounts. Where this has been done (based on calculations) in this section, it is likely that an implementation of this approach will, in practice, be difficult to realise. 
Table 3-5 Funding for HPMPs with only planned activities for countries that would not achieve 35% reduction with their approved activities, and that would (with the funding given in the table) achieve an exact 35% reduction


[image: image15.emf]Status after ExCom July 2017 

Only for Plans with <35% reduction, activities up to 35% (US$ million)

min avrg max

Non-LVCs approved 296.238

Non-LVCs planned 16.249 18.788 21.327

Non-LVCs total 312.487 315.026 317.565

LVCs approved 6.132

LVCs planned 0.051 0.164 0.277

LVCs total 6.183 6.296 6.409

Extra amount countries  1.904

HPMP verification 1.766

Total (range) 322.340 324.992 327.644

2018-20


      Uncertainty applied of +/- 2.562 million
In this way, for both non-LVC and LVC countries, a further reduction in the HPMP funding requirement for 2018-2020, compared to the case described in section 3.3.3, is possible. This at about US$ 16.4 million, and at about US$ 51 million compared to the “after ExCom-79” case given in section 3.3.2 (Note: The total funding requirement for HPMP activities is now about US$ 81 million lower compared to the requirement as determined in the May 2017 report).    
The upper and lower values of the ranges from Tables 2-7 (a) and (b) and Tables 3-1, 3-2, 3-3, 3-4 and 3-5 are once more given in the graphs in Figure 3-1. The ranges in Table 2-7 are based upon the 15% uncertainty in planned activities for  non-LVC countries only, as assumed in the May 2017 RTF report (given by the first two curves in Fig. 3-1). Once the planned activities as well as their uncertainty ranges are rescaled using the data from Table 2-6, the values for the total funding requirement decrease as shown by the two lower curves in Fig. 3-1 (please note that here the values for the May 2017 case are related to the rescaled planned activities). In these cases, the uncertainty range changes (to about 13.5% in HPMP activities, this now for both the HPMP activities for non-LVC and for LVC countries). 

Where the difference between the upper and lower value of the uncertainty range in the May 2017 and ”after ExCom-79” rescaled activities are still substantial, they become much smaller in the cases “towards” the 35% reduction (first for a set of activities, then for some activities to only achieve the precise 35% reduction). The range is rather small in the last case, where it relates to a precise 35% reduction for non-LVC and LVC countries that would then still need additional activities.
[image: image16.png]Upper and lower funding for HPMP scenarios
440

420 \
< 400

320
300

May estim.  May +ExCom  Countries with  Planned up to
appr<3s% 35%

e Planned actvts as in May Rep (upper) === Planned actvts as in May Rep (lower)

e Planned actvts rescaled (upper) e Planned actvts rescaled (lower)




Fig. 3-1 Upper and lower values for the funding requirement range for HPMP activities (starting (based on) with the original May 2017 report HPMP funding range) for the May 2017 and July 2017 cases described in chapter 2, and the cases based on the rescaling of planned activities described in sections 3.3.1 through 3.3.4   
4  
Accounting for the HCFC production phase-out
This chapter takes into account the HCFC production phase-out management plans (HPPMPs), in particular:

1. Concerning the China HPPMP Stage II plan and the related ExCom assumptions in the upcoming ExCom-80 meeting; and

2. In case of a different scenario involving 2 tranches in the 2018-2020 triennium.

4.1   
China HPPMP stage II plan and related assumptions in the upcoming ExCom-80 meeting 
It is difficult to forecast whether a decision will be taken at ExCom-80 on the funding of the China HPPMP stage II plan. The impact of possible decisions cannot be calculated until then (ExCom-80, November 2017, Montreal).
4.2   
Various tranches in the 2018-2020 triennium 

The second request with regard to the HCFC production phase-out was to look at the possibility of two tranches in the next triennium (2018-2020). This question cannot be answered in a very straightforward way.

In the May 2017 report the RTF assumed equal tranches for the 4 years in the period 2017-2020, consistent with the business plan, and leading to a funding requirement of (3 times US$ 21.874 million) US$ 65.6 million. It also assumed a first tranche of a similar size in the year 2017.  

If the China HPPMP stage II plan would be approved at ExCom-80, then there could likely be one tranche in 2017 (the case described in the May 2017 RTF report). In that case, there would be one tranche in 2017 as well as two tranches in the triennium 2018-2020, e.g., in years 2018 and 2020. Assuming tranches every year after 2020, this would imply a total of 13 tranches. In this case, each tranche would be US$ 23.6 million (including agency support costs), which would total at US$ 47.2 million for the next triennium.

It could also be that the China HPPMP stage II plan would be approved in 2017, or in 2018, and that only two tranches would be approved in the next triennium 2018-2020, implying no funding tranche in the year 2017. In this case, there could be 12 funding tranches until 2030, each at US$ 25.5 million (including agency support costs). This would then imply a total funding for the China HPPMP stage II plan at US$ 51.0 million for the next triennium.

In response to the request to consider two funding tranches for the China HPPMP stage II plan in the triennium 2018-2020, depending on when the approval decision would be taken and on how the funding tranches would be specified, the total funding for the next triennium is estimated at US$ 47.2 or 51.0 million (these values have also been used in the overview table in chapter 8).
5
Non-investment and supporting activities
This chapter further considers the non-investment and supporting activities, in particular:

1. To give further thought on how to account for parties with an accelerated phase-out in the HPMP stage II implementation;
2. To give further thought on taking into account HPMPs stage III (for parties wishing to achieve the 67.5% and further reductions steps earlier);

3. To consider a scenario deferring stage III activities to the next triennium;

4. To consider (1) a scenario where there is no annual increase to CAP and (2) a scenario where there is an increase of more than 3% to CAP;

5. To consider a scenario where there are no HCFC demonstration projects;

6. To consider scenarios where HPMP stage III preparation activities in particular are undertaken according to existing commitments in the servicing sector.

5.1  
How to account for parties with an accelerated phase-out in HPMP stage II implementation
Request (1) as given above asks to give thoughts on how to account for parties with an accelerated phase-out in the HPMP stage II implementation. Accelerated implementation could always be possible; however, if it could be applied to consider the accelerated approval of a next HPMP stage III plan will very much depend on when and how the next activities can be initiated in case of accelerated progress of the HPMP II and/or undertaken together with those ongoing under the stage II HPMP. This issue has been dealt with in the relevant chapter in the May 2017 report, and there is not much that one can say that can be covered under non-investment and supporting activities here. 
5.2.  
Taking into account HPMPs stage III to achieve early reduction steps
Suggestion (2) given above asks to give further thoughts on taking into account stage III HPMPs. If stage III HPMPs would start early, that is to say, in the years 2019 or 2020, project preparation would have to be done in 2018 or 2019.  In principle, that project preparation funding has already been taken into account in the total funding requirement for non-investment and supporting activities for the triennium 2018-2020 as presented in the May 2017 report.
5.3
Deferring HPMPs stage III to the 2021-2023 triennium

If stage III HPMP activities would be deferred to the next triennium, it could or would likely be that project preparation would nonetheless have to be done in the 2018-2020 triennium. Where it concerns this timing and project preparation funding, the RTF does not see any difference with the scenario for project preparation funding at US$ 4.35 million for the 2018-2020 triennium presented in the May 2017 report. 
5.4
The funding for CAP with various annual increases 

The CAP funding in the May 2017 report has been estimated at US$ 34.799 million including support costs for the triennium 2018-2020. It implies funding at US$ 11.9 million for 2020, US$ 11.6 million for 2019 and US$ 11.3 million for 2018 (as a starting point, the funding for CAP in 2017 at US$ 10.93 million was taken). 
Assuming a value for 2017 of US$ 10.93 million, the following can be calculated as CAP funding for the triennium 2018-2020:

a. 0% increase per year:  US$ 32.8 million
b. 3% increase per year:  US$ 34.8 million (as in May 2017 report) 
c. 4.5% increase per year:  US$ 35.8 million

d. 6% increase per year:  US$ 36.9 million

(i.e., about US$ 2 million difference for the next triennium per 3% increase per year). 

5.5
No HCFC demonstration projects

The May 2017 RTF report assumes funding for HCFC demonstration projects in the range of zero to US$ 10 million for the triennium 2018-2020. In case no funding would be required for HCFC demonstration projects, the upper range of the funding requirement for 2018-2020 as presented in the May 2017 RTF report would be reduced by US$ 10 million to zero.
5.6
HPMP stage III project preparation activities 

HPMP stage III project preparation activities were estimated at US$ 4.35 million in the May 2017 RTF report. In all HPMP stage III projects the emphasis would be on servicing. It is difficult to give concrete indications why the project preparation funding should be increased or decreased if the emphasis would have to be more on the servicing sector. 
6   
HFC phase-down enabling activities
This chapter further considers the HFC phase-down enabling activities, in particular, the request by parties at OEWG-39 for the TEAP RTF in its supplementary report to “further disaggregate the cost of enabling activities with respect to the different elements addressed.”
Paragraph 4 of Decision XXVIII/5 requested TEAP to take into account the “need for additional resources to enable Article 5 parties to carry out initial activities related to the phase-down of HFCs listed under Annex F and controlled under Article 2J.” Decision XXVIII/2 requested the Executive Committee to develop, within two years of the adoption of the Kigali Amendment, guidelines for financing the phase-down of HFC consumption and production in Article 5 parties; paragraph 20 of that decision further requested the Executive Committee to include the following enabling activities to be funded in relation to the HFC phase-down:
(a) Capacity-building and training for the handling of hydrofluorocarbon alternatives in the servicing, manufacturing and production sectors; 

(b) Institutional strengthening; 

(c) Article 4B licensing; 

(d) Reporting; 

(e) Demonstration projects; and 

(f) Development of national strategies; 

Chapter 6 of the May 2017 RTF report defined initial, enabling activities as those outlined above. In providing the range of funding for HFC phasedown enabling activities in the 2018-2020 triennium, the RTF based its estimate primarily on project preparation, including preparation of proposals for demonstration projects, in this early period. The range of funding was estimated as follows:

  Table 6-1 Funding for HFC phase-down enabling activities (US$ million)
	HFC phase-down enabling activities
	2018-2020

	Non-investment projects (including project preparation and demonstration projects)
	13.5-20.2

	Investment projects
	8.0-24.0

	Total
	21.5-44.2


Since the HFC phase-down funding guidelines were still being discussed and developed by the ExCom during the preparation of the May 2017 Task Force report, the RTF took the approach of considering two categories of funding for HFC phase-down enabling activities: 1) non-investment projects and 2) investment projects. The RTF considered that in the period 2018-2020, the primary funding for enabling activities for non-investment projects would be project preparation, including preparation of proposals for potential demonstration projects, as well as those activities identified in decision 79/46. Specifically, decision 79/46(b)(ii) states:

Enabling activities could consist of, but were not limited to:

a. Activities to facilitate and support the early ratification of the Kigali Amendment;
b. Initial activities identified in paragraph 20 of decision XXVIII/2,including country-specific activities aimed at initiating supporting institutional arrangements, the review of licensing systems, data reporting on HFC consumption and production, and demonstration of non-investment activities, and excluding institutional strengthening, as addressed in decision 78/4(b);
c. National strategies that contained the activities in sub-paragraphs a. and b. above.
The range of funding for non-investment projects were derived using two approaches:

1) Funding for project preparation and HFC stand-alone investment projects based on HCFC stage I HPMPs during 2008-2016: Over 400 project preparation activities for HCFC phase-out have been funded under the MLF giving a total of US $40.4 million (including agency support costs) over the period 2008-2016 or an average of about US$ 4.5 million per year. 

This provides the lower end of the range at US$13.5 million for the three-year period 2018-2020 for primarily project preparation including preparation of demonstration project proposals.

2) Funding per Article 5 party depending on its HCFC baseline and historical funding: The RTF considered the document from ExCom-78 (UNEP/OzL.Pro/ExCom/78/10) describing possible funding modalities for enabling activities to be implemented in Article 5 countries based on HCFC baseline and historical funding as indicators of the effort needed for HFC phase-down enabling activities; based on calculated funding levels, Article 5 countries would be able to prepare HPMPs that included: a description of ODS regulations including the licensing system; HCFC consumption data by substance and sector, and the estimated baseline for compliance and starting point for aggregate reduction in HCFC consumption, the HCFC overarching strategy for the period 2013 (the freeze year) to 2030 and the strategy and phase-out plan for stage I of the HPMP including specific activities. 

Based on this proposal, the estimated indicative level of funding for enabling activities in Article 5 countries at a total of US$ 20.2 million, which provides the upper end of the range provided for non-investment projects of US$ 20.2 million, again primarily for project preparation including preparation for demonstration project proposals.

7   
HFC-23 mitigation

This chapter further considers HFC-23 mitigation, in particular, the request from parties at OEWG-39 for the RTF in its supplementary report to develop a scenario involving the closure of HCFC-22 production plants, with or without existing incineration facilities in order to deal with HFC-23 emissions. It specifically mentions to take into account the closure of HCFC-22 swing plants as one of the possible alternatives to control HFC-23 emissions.
In the May 2017 RTF report, it was analysed which HCFC-22 plants were equipped with incineration facilities, which plants were not, and what the funding would be to equip all plants with incineration facilities, for a range of operational costs (US$ per kg of HFC-23 mitigated). This analysis made clear which amounts could be covered with existing incineration plants and where plants would have to be installed. The installing of new plants was actually not a major issue, it would only concern a few countries (a few countries where an incineration plant would have value to be installed, also facilities where the collection and storage and incineration elsewhere would “do the job”). The analysis also mentioned an incineration plant in Argentina (installed under the CDM), which had not been in operation lately, but could be brought back to operation again, which would involve a certain amount of funding.
If one considers the fact that all HCFC production plants are equipped with incineration equipment, a closure of certain plants, with the decreasing needs for the production of HCFC-22, rather than a continuing operation with the funding by the MLF of operational costs for mitigating HFC-23 emissions, might make sense. However, it is difficult for the RTF to judge where plants, i.e., HCFC-22 production capacity, would be not needed, taking into account the fact that HCFC-22 production plants may be used for a decreasing amount of HCFC-22 production for dispersive uses, however, may continue to be used switching to HCFC-22 production for feedstock, which demand is definitely not decreasing at present, globally. Certain Article 5 countries may consider rescheduling their total HCFC-22 production capacity, and may even be considering a transfer of production rights from one country to another, however, the RTF lacks enough insight in national plans how to deal with this matter in the near future.

It may certainly be so, in the case of anticipated over-capacity of production for dispersive uses, and not enough needs for the production of feedstock material in the foreseeable future, that one may consider closure. This would also involve closure and avoidance of operational costs for incineration facilities. In the case of a 5,000 tonnes HCFC-22 production plant it may concern compensation for closure in the order of US$ 4-6 million, to be paid during 1-2 years, where continuing mitigation of HFC-23 emissions (assumed at 3% of the HCFC-22 output) would imply operational cost funding in the order of US$ 0.2-0.3 million per year (dependent on the type of facility and the HFC-23 emissions profile). In this case, considering the closure of the plant at the assumed compensation funding could be comparable to the costs for e.g. 15 years of mitigation. The main issue therefore will be how long a production plant would be assumed to remain in operation (and the agreed closure funding at some moment in time) versus the (total) HFC-23 mitigation costs. It is too difficult for the RTF to derive any meaningful recommendations or conclusions at the moment here.

The request asks to consider the closure of HCFC-22 swing production plants as a means to deal with the avoidance of HFC-23 mitigation costs. In principle this request seems reasonable, however, it needs to be emphasized that funding for the closure of HCFC-22 swing plants is currently not eligible under the HCFC guidelines. However, the ExCom decided to consider possible cost-effective options for compensation for HCFC-22 swing plants to allow for compliance with the HFC-23 by-product control obligations of the Kigali Amendment (decision 79/47(c)). The RTF notes that the ExCom has not yet provided any guidance on the possible cost-effective options for compensation it would consider, nor an associated level of funding. It may seem logical for a few swing plants (those not equipped with incineration facilities) to consider the closure option. However, it may be difficult to balance between compensation costs for closure and the installation and operation of an incineration unit. It will depend on how long a country would see its swing plant operate, and also depend on which (so far not agreed) level of compensation costs would be adequate in order to financially balance that with the installation and operation of an incineration unit. The RTF, as mentioned, is not able to take into account all the variables, together with the existing non-decision on the funding of the closure of swing plants to derive any useful recommendation here.
This request may have to be deferred to reporting in a subsequent year, when more data on the various ways of operation of all HCFC-22 production plants might be available. This would include the way of operating HFC-23 incineration facilities, where one should also consider the likely venting of HFC-23 during on/off cycles of the incineration facility. This leads to the conclusion that certain amounts of HFC-23 will be vented (on the order of 0.1-0.2% of HCFC-22 quantities produced, or 3-7% of the HFC-23 generated), provided that no sophisticated collection means are applied during these on/off cycles.
8   
Summary of funding amounts calculated for various items 

Table 8-1 below summarizes the impacts to certain elements of the total funding requirement under the MLF for the triennium 2018-2020 based on the requests from OEWG-39. These are shown compared to the May 2017 RTF Report estimates.
Even when there was no specific request by parties for cumulative impacts of possible measures to be calculated, the RTF used the specific scenarios below, with their impacts on funding, and shows the cumulative impacts to the total funding requirement estimated in the May 2017 RTF report in the table below:
· For HPMPs/HPPMPs:

· Planned versus actual funding reduction

· ExCom-79 decisions

· Planned HPMPs exceeding 35% reduction target cancelled

· For Non-Investment and Supporting Activities:

· Deferring any further HCFC demonstration projects

· Varying CAP increases
Table 8-1 Various components of funding, and funding ranges for various HPMP scenarios plus total funding ranges including all the other elements (compared to the May 2017 report (first column)


[image: image17.emf]HPMP actvts May 2017

Removing 

elements as 

requested

Rescaling 

planned actvts

July 2017 

impact

Certain 

planned  

HPMPs cancl'd

Strict need for 

35% reduction

Total range incl. 

HPMP stage III

391.8-491.9 391.8-421.0

HPMPs I/II value

406.3 406.3 388.4 375.9 341.4 325.0

HPMP I/II range

391.8-420.9 391.8-420.9 376.3-400.4 366.5-385.3 336.6-346.1 322.3-327.6

May 2017If no stage IIIIf no stage IIIIf no stage IIIIf no stage IIIIf no stage III

HPMP stg III

0-70.95 0 0 0 0 0

May 2017 2 tranches 2 tranches 2 tranches 2 tranches 2 tranches

HPPMPs 

(China) 67.2 (65.622)

48.8 (47.154)  

52.6 (51.040)

48.8 (47.154)  

52.6 (51.040)

48.8 (47.154)  

52.6 (51.040)

48.8 (47.154)  

52.6 (51.040)

48.8 (47.154)  

52.6 (51.040)

May 2017

No demo 

HCFC

No demo 

HCFC

No demo 

HCFC

No demo 

HCFC

No demo 

HCFC

Non-inv/sup

114.1-124.1 114.1 114.1 114.1 114.1 114.1

May 2017

HFC enabling

21.5-44.2

no change 

(21.5-44.2)

no change 

(21.5-44.2)

no change 

(21.5-44.2)

no change 

(21.5-44.2)

no change 

(21.5-44.2)

May 2017

HFC-23 mitigation

8.0-21.5

no change      

(8.0-21.5)

no change      

(8.0-21.5)

no change      

(8.0-21.5)

no change      

(8.0-21.5)

no change      

(8.0-21.5)

(CAP 3%)

May 2017 Supplement Supplement Supplement Supplement

(0% CAP change)

(6% CAP change)

CAP increase 0% 3% 4.5% 6%

Total supp (CAP) 112.1 (32.8) 114.1 (34.8) 115.1 (35.8) 116.2 (36.9)

529.0-578.5 514.7-560.0 Total 584.2-653.4



ACTIVITIES (all amounts in US$ million)

US$ 2.0 million lower numbers

US$ 2.1 million higher numbers

602.7-748.9 568.7-632.8 558.9-617.8


[image: image18.png]Total funding ranges based on HPMP scenarios

750 —_
700
§
2 650
€
2 600 —_—
2
500
Mayestim.  May+ExCom  Countries with  Planned up to

appr<3s% 35%

e Planned actvts as in May Rep (upper) === Planned actvts as in May Rep (lower)

e Planned actvts rescaled (upper) e Planned actvts rescaled (lower)




Fig. 8-1 Upper and lower total funding requirement, based on HPMP activities (as given in sections 3.3.1-3.3.4, Figure 3-1) plus all other activities as presented in Table 8-1   

Annex 1

Summary of suggestions for elaboration in the supplementary Technology and Economic Assessment Panel task force report

The Open-ended Working Group at its thirty-ninth meeting agrees to request the Technology and Economic Assessment Panel, in presenting its supplementary report to the Twenty-Ninth Meeting of the Parties:

(a)
To discuss and present results related to the following overall questions: 

18. Elaboration on paragraph 3 of the Terms of Reference as expressed in decision XXVIII/5: “That the Technology and Economic Assessment Panel should provide indicative figures of the resources within the estimated funding required for phasing out HCFCs that could be associated with enabling Article 5 parties to encourage the use of low-GWP or zero-GWP alternatives and indicative figures for any additional resources that would be needed to further encourage the use of low-GWP or zero-GWP alternatives”;

19. To present cost effectiveness figures in MT, ODP-tonnes and CO2 equivalent

20. To give a clearer distinction between costs associated with HCFC-related and HFC-related activities;
21. To present a scenario comparing previously approved projects with business plan estimates on an annual basis in relation to determining uncertainty for planned activities;
22. To account for recent ExCom decisions. 

(b) 
To elaborate on the funding components for HPMPs (Chapter 3):

23. With scenarios considering:
a. HPMP stage III implementation activities in particular according to existing commitments in the servicing sector;
b. The deferring of stage III activities to the next triennium.
24. The deferring to the next triennium of non-LVC and LVC planned activities which are not necessary to meet the 35% phase-out target. 

(c)
To take into account the HCFC production phase-out (chapter 4):

25. Concerning the China HPPMP stage II plan and the related ExCom assumptions in the upcoming ExCom-80 meeting;
26. In case of different scenarios involving 2 tranches in the 2018-2020 triennium.
 (d) 
Regarding the non-investment and supporting activities (chapter 5):

27. To give further thought on how to account for parties with an accelerated phase-out in the HPMP stage II implementation;
28. To give further thought on taking into account HPMPs stage III (for parties wishing to achieve the 67.5% and further reductions steps earlier);
29. To consider a scenario deferring stage III activities to the next triennium;
30. To consider (1) a scenario where there is no annual increase to CAP and (2) a scenario where there is an increase of more than 3% to CAP;
31. To consider a scenario where there are no HCFC demonstration projects;
32. To consider scenarios where HPMP stage III preparation activities in particular are undertaken according to existing commitments in the servicing sector.

(e)
Regarding HFC phase-down enabling activities (chapter 6)

33. To further disaggregate the cost of enabling activities with respect to the different elements addressed.
(f) 
Regarding HFC-23 mitigation (chapter 7)

34. To develop a scenario involving the closure of HCFC-22 production plants to deal with HFC-23, with or without existing incineration facilities, taking into account (closure of) swing plants as one of the possible alternatives to control HFC-23 emissions. 
Annex 2 Calculation of planned amounts up to 35%

Table A2-1 Part of a table in which planned funding, percentages reduction by approved and planned activities are being used for further calculations. Column E shows approved reduction percentages (column F presents approved amounts in ODP tonnes; column S presents the approved reduction percentages after that the planned amounts have been added (column T shows the amounts including the planned amounts in ODP tonnes)   


[image: image19.emf]A B C D E F G H I J K L M N O P Q R S T

ODP tonnes approved all (I and II - ExC 77) Funding planned for HPMP II (all planned) ODP tonnes BP plan (HPMP II planned) Total 01/01/2021

Country  Chem Total Appr Perc app ODP-t 2017 2018 2019 2020 Country  2017 2018 2019 2020App 17-20 App totalPerc appr ODP-t

Madagascar HCFC-22           17.10         6.00

35.09 6.00 0 0 0 193,135

Madagascar

2.45 2.45 8.45 49.42              8.45

Mexico HCFC-123           30.20       10.57

35.00

Mexico

0 10.57 35.00             

Mexico HCFC-22         392.80     130.30

33.17 ``

Mexico

0 130.3 33.17             

Mexico HCFC-124             0.10         0.00

0.00

Mexico

0 0 -                 

Mexico HCFC-142b             1.00         0.00

0.00

Mexico

0 0 -                 

Mexico HCFC-141b         820.60     820.60

100.00

Mexico

0 820.6 100.00           

     1,244.70     961.47

77.25 961.47

      0.00       0.00       0.00        0.00

0 961.47 77.25              961.47

Nigeria HCFC-141b         149.60       79.50

53.14

Nigeria

31.63 8.43 11.58 8.43 60.07 139.57 93.30             

Nigeria HCFC-22         248.50       10.60

4.27 3,313,296 1,238,942 3,099,296 1,199,494

Nigeria

17.1 7.1 17.1 6.7 48 58.6 23.58             

        398.10       79.50

19.97 79.50 48.73 15.53 28.68 15.13 198.17 49.78              198.17

Pakistan HCFC-141b         138.50     130.39

94.14

Pakistan

0 130.39 94.14             

Pakistan HCFC-22         108.90       21.69

19.92

Pakistan

0 21.69 19.92             

        247.40     152.08

61.47 152.08 152.08 61.47              152.08

Qatar HCFC-142b           12.05       12.05

100.00

Qatar

0 12.05 100.00           

Qatar HCFC-22           73.45       45.81

62.37

Qatar

5 5 1.8 11.8 57.61 78.43             

Qatar HCFC-141b             0.57         0.00

0.00 0 477,381 477,381 168,087

Qatar

0 0 -                 

          86.07       57.86

67.22 57.86

      0.00       5.00       5.00        1.80

11.8 69.66 80.93              69.66

0 0 0 569,311

Senegal HCFC-22           20.96         7.34

35.02 7.34

Senegal

5.98 5.98 13.32 63.55              13.32


Table A2-1 gives, for a number of non-LVC countries, the approved percentage reduction (column E), the approved amounts in ODP tonnes (column F, yellow), then the planned amounts (and funding for these), the percentages reduction with the planned amounts included (column S) and the total amounts involved (in ODP tonnes) (column T, yellow).

The request has been to calculate the funding for planned amounts that would only result in a 35% reduction in the next triennium (2018-2020); further reductions (and funding involved) would then be moved to the next triennium.

The procedure applied has been as follows: 

1. For countries that already had an approved percentage of 35% or larger, the planned activities (if there were activities planned in the period 2017-2020) were cancelled.

2. For countries that had an approved percentage smaller than 35%, the planned activities for the period 2017-2020 as a whole were taken into account. This was done under the assumption that the planned activities had to be seen as one package, and could not be split into small parts.
3. In a second instance, for the countries with an approved percentage smaller than 35%, only a portion of the planned activities (in ODP tonnes) was taken, namely, such a part that would result in an exact 35% reduction number by 2020. Funding was then calculated for this part by multiplying the total funding 2017-2020 by the percentage (jn ODP tonnes) required to achieve the exact 35%, even when, in practice, this would not be possible.

In case of the non-LVC countries given in Table A2-1, this would imply the following steps in the process of calculating the 35% reduction in the 2018-2020 triennium:

· Madagascar: approved 35.09%, plus planned activities 49.42%.  Here planned activities were cancelled.

· Mexico: approved 77.25%, planned 0%, nothing was changed

· Nigeria: approved 19.97%, plus planned activities 49.78%. In a first instance all planned activities were accepted. In a second instance only 15.03% was accepted, since that would lead to 35% reduction by 2020 (this would imply that a 15.03/29.81 part of the total planned funding was taken into account). It should be noted that the stage II HPMP has been submitted to ExCom-80.
· Pakistan: approved 61.47%, planned 0%, nothing was changed

· Qatar: approved 67.22%, plus planned activities 80.93%.  Here planned activities were cancelled.

· Senegal: approved 35.02%, plus planned activities 63.55%. Since the approved percentage is 35% (or even a little bit larger) none of the planned activities had to be taken into consideration (The starting point for Senegal has been reduced and thus, the country is now an LVC country. Stage II could be submitted in the next triennium (as for any other LVC country)).

� EMBED Excel.Sheet.8  ���








�  Funding numbers in the text have been rounded up or down to make the text easier to read. Please refer to the tables for the actual numbers.  


� Funding umbers in the text have been rounded up or down to make the text easier to read. Please refer to the tables for the actual numbers.


� “Adjusted business plan of the Multilateral Fund for 2017-2019 after the 77th meeting of the Executive Committee (29 Dec 2016)” (UNEP/OzL.Pro/ExCom/77/76)





vi
Supplement to the May 2017 TEAP Replenishment Task Force Report

ix
Supplement to the May 2017 TEAP Replenishment Task Force Report


[image: image20.emf]Year

Business Plan Approvals Difference %approvals Cumulative

2016 175,906,212 134,886,955 41,019,257 77%

2015 172,925,384 185,521,702 -12,596,318 107%

2014 150,349,262 109,636,438 40,712,824 73% 2014-2016

2014-2016 499,180,858 430,045,095 69,135,763 86.15% 86.15%

2013 163,058,422 143,350,645 19,707,777 88%

2012 158,193,207 118,099,916 40,093,291 75%

2011 251,685,220 227,553,662 24,131,558 90% 2011-2016

2011-2013 572,936,849 489,004,223 83,932,626 85.35% 85.72%

2010 205,296,416 103,360,124 101,936,292 50%

2009 106,014,427 87,689,407 18,325,020 83%

2008 145,296,562 142,226,527 3,070,035 98% 2008-2016

2008-2010 456,607,405 333,276,058 123,331,347 72.99% 81.92%

2007 171,419,512 135,794,742 35,624,770 79%

2006 161,412,541 136,961,591 24,450,950 85%

2005 226,796,158 213,353,085 13,443,073 94% 2005-2016

2005-2007 559,628,211 486,109,418 73,518,793 86.86% 82.33%

2004 221,409,010 186,227,602 35,181,408 84%

2003 226,732,762 173,814,977 52,917,785 77%

2002 195,635,529 185,628,199 10,007,330 95% 2002-2016

2002-2004 643,777,301 545,670,778 98,106,523 84.76% 83.24%

2001 166,859,265 144,052,417 22,806,848 86%

2000 131,542,713 125,740,663 5,802,050 96%

_1569047867.xls
NonLVC

		COST EFFECTIVENESS NON-LVCs (without agency support costs)																								COST EFFECTIVENESS NON-LVCs (with agency support costs included)

		ARGENTINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ARGENTINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		11597593				83.53		1300.9090909091		2118.3127272727		138.843		8.915		5.475								Funding		10775154				83.53		1300.9090909091		2118.3127272727		128.997		8.283		5.087

						Phase II		ODP total		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

				Funding		10652124				115.19		1447.5874125874		1937.0464685315		92.474		7.359		5.499								Funding		9941238				115.19		1447.5874125874		1937.0464685315		86.303		6.867		5.132

		Combined		Funding		22249717		198.72		115.19		2079.82		3528.14		111.965		10.698		6.306						Combined		Funding		20716392		198.72		115.19		2079.82		3528.14		104.249		9.961		5.872		1.075

		BRAZIL				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						BRAZIL				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		21027388				220.3		2470.9090909091		2807.3636363636		95.449		8.510		7.490								Funding		19417866				220.3		2470.9090909091		2807.3636363636		88.143		7.859		6.917

						Phase II		ODP total		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

				Funding		38815539				464.06		5702		7352.6518181818		83.643		6.807		5.279								Funding		35963970				464.06		5702		7352.6518181818		77.499		6.307		4.891

		Combined		Funding		59842927		684.36		464.06		8172.91		10160.02		87.444		7.322		5.890						Combined		Funding		55381836		684.36		464.06		8172.91		10160.02		80.925		6.776		5.451		1.080

		CHINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						CHINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		289831680				3445.6		46463.7412587413		69403.8854895105		84.116		6.238		4.176								Funding		270000000				3445.6		46463.7412587413		69403.8854895105		78.361		5.811		3.890

						Phase II		ODP total		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

				Funding		533883629				8714.65		118662.223776224		178213.726923077		61.263		4.499		2.996								Funding		500100000				8714.65		118662.223776224		178213.726923077		57.386		4.214		2.806

		Combined		Funding		823715309		12161.47				165126.0		247617.6		67.732		4.988		3.327						Combined		Funding		770100000		12161.47				165126.0		247617.6		63.323		4.664		3.110		1.0696

		INDIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						INDIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		22969344				341.77		3391		3074.755		67.207		6.774		7.470								Funding		21294490				341.77		3391		3074.755		62.306		6.280		6.926

						Phase II		ODP total		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

				Funding		48315260				769.49		8190.5454545455		8531.69		62.789		5.899		5.663								Funding		44911459				769.49		8190.5454545455		8531.69		58.365		5.483		5.264

		Combined		Funding		71284604		1111.26				11581.5454545455		11606.445		64.148		6.155		6.142						Combined		Funding		66205949		1111.26				11581.5454545455		11606.445		59.577		5.717		5.704		1.075

		EGYPT				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						EGYPT				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		9164414				174		1637.5454545454		1308.1486363636		52.669		5.596		7.006								Funding		8520815				174		1637.5454545454		1308.1486363636		48.970		5.203		6.514

						Phase II		ODP total		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

				Funding		11786341				146.97		2080.2377622378		3298.4692307692		80.196		5.666		3.573								Funding		10954863				146.97		2080.2377622378		3298.4692307692		74.538		5.266		3.321

		Combined		Funding		20950755		320.97				3717.78		4606.62		65.273		5.635		4.548						Combined		Funding		19475678		320.97				3717.78		4606.62		60.678		5.239		4.228		1.075

		INDONESIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						INDONESIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		13378896				135		1637.2727272727		2076.7227272727		99.103		8.171		6.442								Funding		12745484				135		1637.2727272727		2076.7227272727		94.411		7.785		6.137

						Phase II		ODP total		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

				Funding		8883314				84.33		1145.0909090909		1651.4372727273		105.340		7.758		5.379								Funding		8302163				84.33		1145.0909090909		1651.4372727273		98.449		7.250		5.027

		Combined		Funding		22262210		219.33				2782.36		3728.16		101.501		8.001		5.971						Combined		Funding		21047647		219.33				2782.36		3728.16		95.963		7.565		5.646		1.075

		IRAN				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						IRAN				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		10869327				101.3		1271.8181818182		1683.5409090909		107.298		8.546		6.456				10869327				Funding		9994338				101.3		1271.8181818182		1683.5409090909		98.661		7.858		5.936

						Phase II		ODP total		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

				Funding		12279535				225.47		2697.6363636364		3361.7490909091		54.462		4.552		3.653								Funding		11288177				225.47		2697.6363636364		3361.7490909091		50.065		4.184		3.358

		Combined		Funding		23148862		326.77				3969.45		5045.29		79.271		6.427		4.969						Combined		Funding		21282515		326.77				3969.45		5045.29		65.130		5.362		4.218		1.088

		MEXICO				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						MEXICO				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		19421177				417.3		4019.0909090909		3403.0772727273		46.540		4.832		5.707								Funding		18066211				417.3		4019.0909090909		3403.0772727273		43.293		4.495		5.309

						Phase II		ODP total		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

				Funding		11786341				560.53		6590.1923076923		6915.5810034965		21.027		1.788		1.704								Funding		11087772				560.53		6590.1923076923		6915.5810034965		19.781		1.682		1.603

		Combined		Funding		31207518		977.83				10609.2832167832		10318.6582762238		31.915		2.942		3.024						Combined		Funding		29153983		977.83				10609.2832167832		10318.6582762238		29.815		2.748		2.825		1.787

		LEBANON				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						LEBANON				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		2682242				20		226.3636363636		260.7772727273		134.112		11.849		10.286								Funding		2495109				20		226.3636363636		260.7772727273		124.755		11.023		9.568

						Phase II		ODP total		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

				Funding		4498093				41.16		544.4545454545		764.2213636364		109.283		8.262		5.886								Funding		4203826				41.16		544.4545454545		764.2213636364		102.134		7.721		5.501

		Combined		Funding		7180335		61.16				770.82		1025.00		117.402		9.315		7.005						Combined		Funding		6698935		61.16				770.82		1025.00		109.531		8.691		6.536		1.075

		PERU				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						PERU				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		310111		3.74				51.73		75.97		82.917		5.995		4.082								Funding		282671		3.74				51.73		75.97		75.580		5.465		3.721		1.097

		TOGO				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq												TOGO				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq

				Funding		692650		7				127.27		230.36		98.950		5.442		3.007								Funding		630000		7				127.27		230.36		90.000		4.950		2.735		1.0995

		ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Total						16072.61				208988.940559441		297942.27		67.543		5.215		3.757						Total						16072.61				208988.940559441		297942.26991958		62.901		4.856		3.498

		ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Total						3911.14				43862.9755244755		50324.657506993		66.959		5.918		5.094						Total						3911.14				43862.9755244755		50324.657506993		61.587		5.455		4.706

		ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Total		weighted / ODP-t				16072.61				208988.940559441		297942.26991958		67.543		5.215		3.757						Total		weighted / ODP-t				16072.61				208988.940559441		297942.26991958		62.901		4.856		3.498

				weighted / funding												69.730		5.387		3.843								weighted / funding												64.936		5.017		3.578				1.0323670634		1.0331341429		1.022889544

		ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Total		weighted / ODP-t				3911.14				43862.9755244755		50324.657506993		66.959		5.918		5.094						Total		weighted / ODP-t				3911.14				43862.9755244755		50324.657506993		61.587		5.455		4.706

				weighted / funding												76.219		6.672		5.498								weighted / funding												70.105		6.149		5.079				1.1383024243		1.1272889847		1.0792548979

		ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Total		with support costs				16072.61				208988.940559441		297942.26991958		67.543		5.215		3.757						Total		w/o support costs				16072.61				208988.940559441		297942.26991958		62.901		4.856		3.498

				w/o support costs												62.901		4.856		3.498								with support costs												64.936		5.017		3.578

		ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Total		with support costs				3911.14				43862.9755244755		50324.657506993		66.959		5.918		5.094						Total		w/o support costs				3911.14				43862.9755244755		50324.657506993		61.587		5.455		4.706

				w/o support costs												61.587		5.455		4.706								with support costs												70.105		6.149		5.079





LVC

		COST EFFECTIVENESS LVCs (with agency support costs included)																				COST EFFECTIVENESS LVCs (without agency support costs)

		ANGOLA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ANGOLA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Phase I		191840		1.59		28.91		52.33		120.654		6.636		3.666								Funding		176000		1.59		28.9090909091		52.3254545455		110.692		6.088		3.364

				Funding																						Phase II

		Phase II		967280		9.18		166.91		302.11		105.368		5.795		3.202								Funding		904000		9.18		166.9090909091		302.1054545455		98.475		5.416		2.992

		Combined		1159120		10.77		195.82		354.43		107.898		5.934		3.279		1.075				Combined		Funding		1159120		10.77		195.82		354.43		100.370		5.520		3.050

		ARMENIA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ARMENIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Phase I		649121		2.23		33.00		51.54		291.086		19.670		12.594								Funding		601838		2.23		33		51.5431818182		269.883		18.238		11.676

				Funding																						Phase II

		Phase II		238196		3.26		59.27		107.28		73.066		4.019		2.220								Funding		216000		3.26		59.2727272727		107.2836363636		66.258		3.644		2.013

		Combined		887317		5.49		92.27		158.83		232.559		15.469		9.809		1.086				Combined		Funding		887317		5.49		92.27		158.83		214.143		14.244		9.032

		CAMBODIA				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						CAMBODIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Phase I		1772250		15		272.73		493.64		118.150		6.498		3.590		1.1077						Funding		1600000		15		272.73		493.64		106.662		5.866		3.241

		COSTA RICA																				COSTA RICA				Phase I

		Phase I		1240037		18.93		205.97		214.65		65.506		6.020		5.777		1.075						Funding		1153523		18.93		205.97		214.65		60.936		5.600		5.374

		CUBA																				CUBA				Phase I

		Phase I		1878592		19.26		205.18		214.05		97.539		9.156		8.776		1.075						Funding		1747527		19.26		205.18		214.05		90.734		8.517		8.164

		JAMAICA																				JAMAICA				Phase I

		Phase I		708844		8.13		114.82		172.02		87.189		6.174		4.121		1.0815						Funding		655450		8.13		114.82		172.02		80.618		5.708		3.810

		MALDIVES		Phase I																		MALDIVES				Phase I

		Phase I		1219900		3.7		67.27		121.76		329.703		18.134		10.019		1.109						Funding		1100000		3.7		67.27		121.76		297.297		16.351		9.034

		MONGOLIA		Phase I																		MONGOLIA				Phase I

		Phase I		413580		1		18.18		32.91		413.580		22.747		12.567		1.13						Funding		366000		1		18.18		32.91		366.000		20.130		11.122

		RWANDA		Phase I																		RWANDA				Phase I

		Phase I		312000		1.44		26.27		41.78		216.667		11.875		7.468		1.1143						Funding		280000		1.44		26.27		41.78		194.442		10.657		6.702

		SERBIA		Phase I																		SERBIA				Phase I

		Phase I		1050408		2.94		53.45		96.75		357.282		19.650		10.857		1.0793						Funding		973260		2.94		53.45		96.75		331.031		18.207		10.059

		SWAZILAND		Phase I																		SWAZILAND				Phase I

		Phase I		955344		6.19		61.64		56.33		154.337		15.500		16.961		1.0882						Funding		877948		6.19		61.64		56.33		141.827		14.243		15.586

		UGANDA		Phase I																		UGANDA				Phase I

		Phase I		182685		0.07		1.27		2.30		2609.786		143.538		79.303		1.1105						Funding		164500		0.07		1.27		2.30		2350.100		129.255		71.412

				Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2												ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Total				92.92		1314.88		1959.45		130.999		9.229		7.079						Total						92.92		1314.8811188811		1959.4493581935		120.261		8.489		6.524

		Total		11780077								212.854		13.418		9.107

				11780077								212.854		13.418		9.107

		ALL LVC				ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Total				92.92		1314.8811188811		1959.4493581935		130.999		9.229		7.079

		Total										120.261		8.489		6.524





LVC-Alternative

		Consumption (mt)		Funding total phase-out		Number of countries		Total unding		Total baseline (HCFC-22) (mt)		CE ($/kg)		CE ($/kg odp)

		>0 <15		587,500		21		12,337,500		97.81		126.13		2,293.30

		15 <40		750,000		16		12,000,000		419.44		28.61		520.17

		40 <80		800,000		14		11,200,000		910.91		12.30		223.55

		80 <120		900,000		11		9,900,000		1,100.48		9.00		163.57

		120 <160		950,000		9		8,550,000		1,280.19		6.68		121.43

		160 <200		1,000,000		3		3,000,000		567.21		5.29		96.16

		200 <320		1,600,000		12		19,200,000		3,157.94		6.08		110.54

		320 <360		1,800,000		2		3,600,000		677.71		5.31		96.58

		Total						79,787,500		8,211.71		9.72		176.66






_1569047950.xls
Sheet1

		

				ARGENTINA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ARGENTINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		11597593		83.53		1300.9090909091		2118.3127272727		138.843		8.915		5.475								Funding		10775154				83.53		1300.9090909091		2118.3127272727		128.997		8.283		5.087

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		10652124		115.19		1447.5874125874		1937.0464685315		92.474		7.359		5.499								Funding		9941238				115.19		1447.5874125874		1937.0464685315		86.303		6.867		5.132

				Combined		Funding		22249717		198.72		2079.82		3528.14		111.965		10.698		6.306						Combined		Funding		20716392		198.72		115.19		2079.82		3528.14		104.249		9.961		5.872		1.075

				BRAZIL				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						BRAZIL				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		21027388		220.3		2470.9090909091		2807.3636363636		95.449		8.510		7.490								Funding		19417866				220.3		2470.9090909091		2807.3636363636		88.143		7.859		6.917

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		38815539		464.06		5702		7352.6518181818		83.643		6.807		5.279								Funding		35963970				464.06		5702		7352.6518181818		77.499		6.307		4.891

				Combined		Funding		59842927		684.36		8172.91		10160.02		87.444		7.322		5.890						Combined		Funding		55381836		684.36		464.06		8172.91		10160.02		80.925		6.776		5.451		1.080

				CHINA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						CHINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		289831680		3445.6		46463.7412587413		69403.8854895105		84.116		6.238		4.176								Funding		270000000				3445.6		46463.7412587413		69403.8854895105		78.361		5.811		3.890

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		533883629		8714.65		118662.223776224		178213.726923077		61.263		4.499		2.996								Funding		500100000				8714.65		118662.223776224		178213.726923077		57.386		4.214		2.806

				Combined		Funding		823715309		12161.47		165126.0		247617.6		67.732		4.988		3.327						Combined		Funding		770100000		12161.47				165126.0		247617.6		63.323		4.664		3.110		1.0696

				INDIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						INDIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		22969344		341.77		3391		3074.755		67.207		6.774		7.470								Funding		21294490				341.77		3391		3074.755		62.306		6.280		6.926

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		48315260		769.49		8190.5454545455		8531.69		62.789		5.899		5.663								Funding		44911459				769.49		8190.5454545455		8531.69		58.365		5.483		5.264

				Combined		Funding		71284604		1111.26		11581.5454545455		11606.445		64.148		6.155		6.142						Combined		Funding		66205949		1111.26				11581.5454545455		11606.445		59.577		5.717		5.704		1.075

				EGYPT				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						EGYPT				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		9164414		174		1637.5454545454		1308.1486363636		52.669		5.596		7.006								Funding		8520815				174		1637.5454545454		1308.1486363636		48.970		5.203		6.514

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		11786341		146.97		2080.2377622378		3298.4692307692		80.196		5.666		3.573								Funding		10954863				146.97		2080.2377622378		3298.4692307692		74.538		5.266		3.321

				Combined		Funding		20950755		320.97		3717.78		4606.62		65.273		5.635		4.548						Combined		Funding		19475678		320.97				3717.78		4606.62		60.678		5.239		4.228		1.075

				INDONESIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						INDONESIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		13378896		135		1637.2727272727		2076.7227272727		99.103		8.171		6.442								Funding		12745484				135		1637.2727272727		2076.7227272727		94.411		7.785		6.137

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		8883314		84.33		1145.0909090909		1651.4372727273		105.340		7.758		5.379								Funding		8302163				84.33		1145.0909090909		1651.4372727273		98.449		7.250		5.027

				Combined		Funding		22262210		219.33		2782.36		3728.16		101.501		8.001		5.971						Combined		Funding		21047647		219.33				2782.36		3728.16		95.963		7.565		5.646		1.075

				IRAN				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						IRAN				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		10869327		101.3		1271.8181818182		1683.5409090909		107.298		8.546		6.456				10869327				Funding		9994338				101.3		1271.8181818182		1683.5409090909		98.661		7.858		5.936

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		12279535		225.47		2697.6363636364		3361.7490909091		54.462		4.552		3.653								Funding		11288177				225.47		2697.6363636364		3361.7490909091		50.065		4.184		3.358

				Combined		Funding		23148862		326.77		3969.45		5045.29		70.841		6.427		4.969						Combined		Funding		21282515		326.77				3969.45		5045.29		65.130		5.362		4.218		1.088

				MEXICO				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						MEXICO				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		19421177		417.3		4019.0909090909		3403.0772727273		46.540		4.832		5.707								Funding		18066211				417.3		4019.0909090909		3403.0772727273		43.293		4.495		5.309

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		11786341		560.53		6590.1923076923		6915.5810034965		21.027		1.788		1.704								Funding		11087772				560.53		6590.1923076923		6915.5810034965		19.781		1.682		1.603

				Combined		Funding		31207518		977.83		10609.2832167832		10318.6582762238		31.915		2.942		3.024						Combined		Funding		29153983		977.83				10609.2832167832		10318.6582762238		29.815		2.748		2.825		1.787

				LEBANON				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						LEBANON				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		2682242		20		226.3636363636		260.7772727273		134.112		11.849		10.286								Funding		2495109				20		226.3636363636		260.7772727273		124.755		11.023		9.568

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		4498093		41.16		544.4545454545		764.2213636364		109.283		8.262		5.886								Funding		4203826				41.16		544.4545454545		764.2213636364		102.134		7.721		5.501

				Combined		Funding		7180335		61.16		770.82		1025.00		117.402		9.315		7.005						Combined		Funding		6698935		61.16				770.82		1025.00		109.531		8.691		6.536		1.075

				PERU				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						PERU				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		310111		3.74		51.73		75.97		82.917		5.995		4.082								Funding		282671		3.74				51.73		75.97		75.580		5.465		3.721		1.097

				TOGO				Phase I		ODP-t		tonnes		kt CO2 eq												TOGO				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq

						Funding		692650		7		127.27		230.36		98.950		5.442		3.007								Funding		630000		7				127.27		230.36		90.000		4.950		2.735		1.0995

				ALL COUNTRIES						ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				1082844998		16072.61		208988.940559441		297942.27		69.529		5.387		3.844						Total				1010975606		16072.61				208988.940559441		297942.26991958		64.907		5.015		3.577

				ALL MINUS CHINA						ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				548961369		3911.14		43862.9755244755		50324.657506993		66.254		3.141		2.590						Total				477091977		3911.14				43862.9755244755		50324.657506993		35.328		3.099		2.559

				ALL COUNTRIES								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		weighted / ODP-t						208988.940559441		297942.26991958		67.543		5.215		3.757						Total		weighted / ODP-t				16072.61				208988.940559441		297942.26991958		62.901		4.856		3.498

						weighted / funding										69.730		5.387		3.843								weighted / funding												64.936		5.017		3.578				1.0323670634		1.0331341429		1.022889544

				ALL MINUS CHINA								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		weighted / ODP-t						43862.9755244755		50324.657506993		66.959		5.918		5.094						Total		weighted / ODP-t				3911.14				43862.9755244755		50324.657506993		61.587		5.455		4.706

						weighted / funding										76.219		6.672		5.498								weighted / funding												70.105		6.149		5.079				1.1383024243		1.1272889847		1.0792548979

				ALL COUNTRIES						funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		with support costs				1082844998		208988.940559441		297942.26991958		67.543		5.215		3.757						Total		w/o support costs				16072.61				208988.940559441		297942.26991958		62.901		4.856		3.498

						w/o support costs				1010975606						62.901		4.856		3.498								with support costs												64.936		5.017		3.578

				ALL MINUS CHINA						funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		with support costs				548961369		43862.9755244755		50324.657506993		66.959		5.918		5.094						Total		w/o support costs				3911.14				43862.9755244755		50324.657506993		61.587		5.455		4.706

						w/o support costs				477091977						61.587		5.455		4.706								with support costs												70.105		6.149		5.079





Sheet2

		

				ARGENTINA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		11597593		83.53		1300.91		2118.31		138.843		8.915		5.475

						Funding		ODP-t				kt CO2 eq

				Phase II		10652124		115.19		1447.59		1937.05		92.474		7.359		5.499

				Combined		22249717		198.72		2748.50		4055.36		111.965		8.095		5.486

				BRAZIL		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		21027388		220.3		2470.91		2807.36		95.449		8.510		7.490

						Funding		ODP-t				kt CO2 eq

				Phase II		38815539		464.06		5702.00		7352.65		83.643		6.807		5.279

				Combined		59842927		684.36		8172.91		10160.02		87.444		7.322		5.890

				CHINA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		289831680		3445.6		46463.74		69403.89		84.116		6.238		4.176

						Funding		ODP-t				kt CO2 eq

				Phase II		533883629		8714.65		118662.22		178213.73		61.263		4.499		2.996

				Combined		823715309		12160.25		165125.97		247617.61		67.738		4.988		3.327

				INDIA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		22969344		341.77		3391.00		3074.76		67.207		6.774		7.470

						Funding		ODP-t				kt CO2 eq

				Phase II		48315260		769.49		8190.55		8531.69		62.789		5.899		5.663

				Combined		71284604		1111.26		11581.55		11606.45		64.148		6.155		6.142

				EGYPT		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		9164414		174		1637.55		1308.15		52.669		5.596		7.006

						Funding		ODP-t				kt CO2 eq

				Phase II		11786341		146.97		2080.24		3298.47		80.196		5.666		3.573

				Combined		20950755		320.97		3717.78		4606.62		65.273		5.635		4.548

				INDONESIA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		13378896		135		1637.27		2076.72		99.103		8.171		6.442

						Funding		ODP-t				kt CO2 eq

				Phase II		8883314		84.33		1145.09		1651.44		105.340		7.758		5.379

				Combined		22262210		219.33		2782.36		3728.16		101.501		8.001		5.971

				IRAN		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		10869327		101.3		1271.82		1683.54		107.298		8.546		6.456

						Funding		ODP-t				kt CO2 eq

				Phase II		12279535		225.47		2697.64		3361.75		54.462		4.552		3.653

				Combined		23148862		326.77		3969.45		5045.29		70.841		6.427		4.969

				MEXICO		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		19421177		417.3		4019.09		3403.08		46.540		4.832		5.707

						Phase II		ODP-t				kt CO2 eq

				Phase II		11786341		560.53		6590.19		6915.58		21.027		1.788		1.704

				Combined		31207518		977.83		10609.28		10318.66		31.915		2.942		3.024

				LEBANON		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		2682242		20		226.36		260.78		134.112		11.849		10.286

						Funding		ODP-t				kt CO2 eq

				Phase II		4498093		41.16		544.45		764.22		109.283		8.262		5.886

				Combined		7180335		61.16		770.82		1025.00		117.402		9.315		7.005

				PERU		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						310111		3.74		51.73		75.97		82.917		5.995		4.082

				TOGO		Funding		ODP-t		tonnes		kt CO2 eq

						692650		7		127.27		230.36		98.950		5.442		3.007

				ALL COUNTRIES		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		1082844998		16071.39		209657.62		298469.49		67.377		5.183		3.747

				ALL MINUS CHINA		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		259129689		3911.14		44531.65		50851.88		66.254		5.786		5.053

				ALL COUNTRIES		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total (funds wtd)		1082844998		16071.39		209657.62		298469.49		69.534		5.334		3.827

				ALL MINUS CHINA		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total (funds wtd)		259129689		3911.14		44531.65		50851.88		75.241		6.431		5.417

				ALL COUNTRIES				funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				1082844998		209657.62		298469.49		67.377		5.183		3.747

				Total (funding wtd.)										69.534		5.334		3.827

				ALL MINUS CHINA				funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				259129689		44531.65		50851.88		66.254		5.918		5.094

				Total (funding wtd.)										75.241		6.431		5.417

																				ALL COUNTRIES						funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

																				Total		with support costs				1082844998		208988.940559441		297942.26991958		67.377		5.183		3.747

																						w/o support costs				1010975606						62.741		4.826		3.489

																				ALL MINUS CHINA						funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

																				Total		with support costs				548961369		43862.9755244755		50324.657506993		66.254		5.918		5.094

																						w/o support costs				477091977						61.205		5.467		4.706

				LVC COUNTRIES				funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total     ODP-t wtd						1314.88		1959.45		130.999		9.229		7.079

				Total     Fund wtd				11780077						212.854		13.418		9.107





Sheet3

		COST EFFECTIVENESS LVCs (with agency support costs included)																						COST EFFECTIVENESS LVCs (without agency support costs)

		ANGOLA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ANGOLA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		191840		1.59		28.9090909091		52.3254545455		120.654		6.636		3.666								Funding		176000		1.59		28.9090909091		52.3254545455		110.692		6.088		3.364

						Phase II																						Phase II

				Funding		967280		9.18		166.9090909091		302.1054545455		105.368		5.795		3.202								Funding		904000		9.18		166.9090909091		302.1054545455		98.475		5.416		2.992

		Combined		Funding		1159120		10.77		195.82		354.43		107.898		5.934		3.279		1.075				Combined		Funding		1159120		10.77		195.82		354.43		100.370		5.520		3.050

		ARMENIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ARMENIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		649121		2.23		33		51.5431818182		291.086		19.670		12.594								Funding		601838		2.23		33		51.5431818182		269.883		18.238		11.676

						Phase II																						Phase II

				Funding		238196		3.26		59.2727272727		107.2836363636		73.066		4.019		2.220								Funding		216000		3.26		59.2727272727		107.2836363636		66.258		3.644		2.013

		Combined		Funding		887317		5.49		92.27		158.83		232.559		15.469		9.809		1.086				Combined		Funding		887317		5.49		92.27		158.83		214.143		14.244		9.032

		CAMBODIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						CAMBODIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		1772250		15		272.73		493.64		118.150		6.498		3.590		1.1077						Funding		1600000		15		272.73		493.64		106.662		5.866		3.241

		COSTA RICA				Phase I																		COSTA RICA				Phase I

				Funding		1240037		18.93		205.97		214.65		65.506		6.020		5.777		1.075						Funding		1153523		18.93		205.97		214.65		60.936		5.600		5.374

		CUBA				Phase I																		CUBA				Phase I

				Funding		1878592		19.26		205.18		214.05		97.539		9.156		8.776		1.075						Funding		1747527		19.26		205.18		214.05		90.734		8.517		8.164

		JAMAICA				Phase I																		JAMAICA				Phase I

				Funding		708844		8.13		114.82		172.02		87.189		6.174		4.121		1.0815						Funding		655450		8.13		114.82		172.02		80.618		5.708		3.810

		MALDIVES				Phase I																		MALDIVES				Phase I

				Funding		1219900		3.7		67.27		121.76		329.703		18.134		10.019		1.109						Funding		1100000		3.7		67.27		121.76		297.297		16.351		9.034

		MONGOLIA				Phase I																		MONGOLIA				Phase I

				Funding		413580		1		18.18		32.91		413.580		22.747		12.567		1.13						Funding		366000		1		18.18		32.91		366.000		20.130		11.122

		RWANDA				Phase I																		RWANDA				Phase I

				Funding		312000		1.44		26.27		41.78		216.667		11.875		7.468		1.1143						Funding		280000		1.44		26.27		41.78		194.442		10.657		6.702

		SERBIA				Phase I																		SERBIA				Phase I

				Funding		1050408		2.94		53.45		96.75		357.282		19.650		10.857		1.0793						Funding		973260		2.94		53.45		96.75		331.031		18.207		10.059

		SWAZILAND				Phase I																		SWAZILAND				Phase I

				Funding		955344		6.19		61.64		56.33		154.337		15.500		16.961		1.0882						Funding		877948		6.19		61.64		56.33		141.827		14.243		15.586

		UGANDA				Phase I																		UGANDA				Phase I

				Funding		182685		0.07		1.27		2.30		2609.786		143.538		79.303		1.1105						Funding		164500		0.07		1.27		2.30		2350.100		129.255		71.412

		LVC COUNTRIES				funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2												ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Total		ODP-t wtd				92.92		1314.8811188811		1959.4493581935		130.999		9.229		7.079						Total						92.92		1314.8811188811		1959.4493581935		120.261		8.489		6.524

		Total		Fund wtd		11780077								212.854		13.418		9.107

						11780077								212.854		13.418		9.107

		ALL LVC						ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Total		with support				92.92		1314.88		1959.45		130.999		9.229		7.079

		Total		w/o support										120.261		8.489		6.524






_1569048058.xls
Sheet1

		

				ARGENTINA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ARGENTINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		11597593		83.53		1300.9090909091		2118.3127272727		138.843		8.915		5.475								Funding		10775154				83.53		1300.9090909091		2118.3127272727		128.997		8.283		5.087

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		10652124		115.19		1447.5874125874		1937.0464685315		92.474		7.359		5.499								Funding		9941238				115.19		1447.5874125874		1937.0464685315		86.303		6.867		5.132

				Combined		Funding		22249717		198.72		2079.82		3528.14		111.965		10.698		6.306						Combined		Funding		20716392		198.72		115.19		2079.82		3528.14		104.249		9.961		5.872		1.075

				BRAZIL				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						BRAZIL				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		21027388		220.3		2470.9090909091		2807.3636363636		95.449		8.510		7.490								Funding		19417866				220.3		2470.9090909091		2807.3636363636		88.143		7.859		6.917

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		38815539		464.06		5702		7352.6518181818		83.643		6.807		5.279								Funding		35963970				464.06		5702		7352.6518181818		77.499		6.307		4.891

				Combined		Funding		59842927		684.36		8172.91		10160.02		87.444		7.322		5.890						Combined		Funding		55381836		684.36		464.06		8172.91		10160.02		80.925		6.776		5.451		1.080

				CHINA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						CHINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		289831680		3445.6		46463.7412587413		69403.8854895105		84.116		6.238		4.176								Funding		270000000				3445.6		46463.7412587413		69403.8854895105		78.361		5.811		3.890

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		533883629		8714.65		118662.223776224		178213.726923077		61.263		4.499		2.996								Funding		500100000				8714.65		118662.223776224		178213.726923077		57.386		4.214		2.806

				Combined		Funding		823715309		12161.47		165126.0		247617.6		67.732		4.988		3.327						Combined		Funding		770100000		12161.47				165126.0		247617.6		63.323		4.664		3.110		1.0696

				INDIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						INDIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		22969344		341.77		3391		3074.755		67.207		6.774		7.470								Funding		21294490				341.77		3391		3074.755		62.306		6.280		6.926

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		48315260		769.49		8190.5454545455		8531.69		62.789		5.899		5.663								Funding		44911459				769.49		8190.5454545455		8531.69		58.365		5.483		5.264

				Combined		Funding		71284604		1111.26		11581.5454545455		11606.445		64.148		6.155		6.142						Combined		Funding		66205949		1111.26				11581.5454545455		11606.445		59.577		5.717		5.704		1.075

				EGYPT				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						EGYPT				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		9164414		174		1637.5454545454		1308.1486363636		52.669		5.596		7.006								Funding		8520815				174		1637.5454545454		1308.1486363636		48.970		5.203		6.514

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		11786341		146.97		2080.2377622378		3298.4692307692		80.196		5.666		3.573								Funding		10954863				146.97		2080.2377622378		3298.4692307692		74.538		5.266		3.321

				Combined		Funding		20950755		320.97		3717.78		4606.62		65.273		5.635		4.548						Combined		Funding		19475678		320.97				3717.78		4606.62		60.678		5.239		4.228		1.075

				INDONESIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						INDONESIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		13378896		135		1637.2727272727		2076.7227272727		99.103		8.171		6.442								Funding		12745484				135		1637.2727272727		2076.7227272727		94.411		7.785		6.137

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		8883314		84.33		1145.0909090909		1651.4372727273		105.340		7.758		5.379								Funding		8302163				84.33		1145.0909090909		1651.4372727273		98.449		7.250		5.027

				Combined		Funding		22262210		219.33		2782.36		3728.16		101.501		8.001		5.971						Combined		Funding		21047647		219.33				2782.36		3728.16		95.963		7.565		5.646		1.075

				IRAN				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						IRAN				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		10869327		101.3		1271.8181818182		1683.5409090909		107.298		8.546		6.456				10869327				Funding		9994338				101.3		1271.8181818182		1683.5409090909		98.661		7.858		5.936

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		12279535		225.47		2697.6363636364		3361.7490909091		54.462		4.552		3.653								Funding		11288177				225.47		2697.6363636364		3361.7490909091		50.065		4.184		3.358

				Combined		Funding		23148862		326.77		3969.45		5045.29		70.841		6.427		4.969						Combined		Funding		21282515		326.77				3969.45		5045.29		65.130		5.362		4.218		1.088

				MEXICO				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						MEXICO				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		19421177		417.3		4019.0909090909		3403.0772727273		46.540		4.832		5.707								Funding		18066211				417.3		4019.0909090909		3403.0772727273		43.293		4.495		5.309

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		11786341		560.53		6590.1923076923		6915.5810034965		21.027		1.788		1.704								Funding		11087772				560.53		6590.1923076923		6915.5810034965		19.781		1.682		1.603

				Combined		Funding		31207518		977.83		10609.2832167832		10318.6582762238		31.915		2.942		3.024						Combined		Funding		29153983		977.83				10609.2832167832		10318.6582762238		29.815		2.748		2.825		1.787

				LEBANON				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						LEBANON				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		2682242		20		226.3636363636		260.7772727273		134.112		11.849		10.286								Funding		2495109				20		226.3636363636		260.7772727273		124.755		11.023		9.568

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		4498093		41.16		544.4545454545		764.2213636364		109.283		8.262		5.886								Funding		4203826				41.16		544.4545454545		764.2213636364		102.134		7.721		5.501

				Combined		Funding		7180335		61.16		770.82		1025.00		117.402		9.315		7.005						Combined		Funding		6698935		61.16				770.82		1025.00		109.531		8.691		6.536		1.075

				PERU				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						PERU				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		310111		3.74		51.73		75.97		82.917		5.995		4.082								Funding		282671		3.74				51.73		75.97		75.580		5.465		3.721		1.097

				TOGO				Phase I		ODP-t		tonnes		kt CO2 eq												TOGO				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq

						Funding		692650		7		127.27		230.36		98.950		5.442		3.007								Funding		630000		7				127.27		230.36		90.000		4.950		2.735		1.0995

				ALL COUNTRIES						ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				1082844998		16072.61		208988.940559441		297942.27		69.529		5.387		3.844						Total				1010975606		16072.61				208988.940559441		297942.26991958		64.907		5.015		3.577

				ALL MINUS CHINA						ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				548961369		3911.14		43862.9755244755		50324.657506993		66.254		3.141		2.590						Total				477091977		3911.14				43862.9755244755		50324.657506993		35.328		3.099		2.559

				ALL COUNTRIES								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		weighted / ODP-t						208988.940559441		297942.26991958		67.543		5.215		3.757						Total		weighted / ODP-t				16072.61				208988.940559441		297942.26991958		62.901		4.856		3.498

						weighted / funding										69.730		5.387		3.843								weighted / funding												64.936		5.017		3.578				1.0323670634		1.0331341429		1.022889544

				ALL MINUS CHINA								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		weighted / ODP-t						43862.9755244755		50324.657506993		66.959		5.918		5.094						Total		weighted / ODP-t				3911.14				43862.9755244755		50324.657506993		61.587		5.455		4.706

						weighted / funding										76.219		6.672		5.498								weighted / funding												70.105		6.149		5.079				1.1383024243		1.1272889847		1.0792548979

				ALL COUNTRIES						funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		with support costs				1082844998		208988.940559441		297942.26991958		67.543		5.215		3.757						Total		w/o support costs				16072.61				208988.940559441		297942.26991958		62.901		4.856		3.498

						w/o support costs				1010975606						62.901		4.856		3.498								with support costs												64.936		5.017		3.578

				ALL MINUS CHINA						funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		with support costs				548961369		43862.9755244755		50324.657506993		66.959		5.918		5.094						Total		w/o support costs				3911.14				43862.9755244755		50324.657506993		61.587		5.455		4.706

						w/o support costs				477091977						61.587		5.455		4.706								with support costs												70.105		6.149		5.079





Sheet2

		

				ARGENTINA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		11597593		83.53		1300.91		2118.31		138.843		8.915		5.475

						Funding		ODP-t				kt CO2 eq

				Phase II		10652124		115.19		1447.59		1937.05		92.474		7.359		5.499

				Combined		22249717		198.72		2748.50		4055.36		111.965		8.095		5.486

				BRAZIL		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		21027388		220.3		2470.91		2807.36		95.449		8.510		7.490

						Funding		ODP-t				kt CO2 eq

				Phase II		38815539		464.06		5702.00		7352.65		83.643		6.807		5.279

				Combined		59842927		684.36		8172.91		10160.02		87.444		7.322		5.890

				CHINA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		289831680		3445.6		46463.74		69403.89		84.116		6.238		4.176

						Funding		ODP-t				kt CO2 eq

				Phase II		533883629		8714.65		118662.22		178213.73		61.263		4.499		2.996

				Combined		823715309		12160.25		165125.97		247617.61		67.738		4.988		3.327

				INDIA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		22969344		341.77		3391.00		3074.76		67.207		6.774		7.470

						Funding		ODP-t				kt CO2 eq

				Phase II		48315260		769.49		8190.55		8531.69		62.789		5.899		5.663

				Combined		71284604		1111.26		11581.55		11606.45		64.148		6.155		6.142

				EGYPT		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		9164414		174		1637.55		1308.15		52.669		5.596		7.006

						Funding		ODP-t				kt CO2 eq

				Phase II		11786341		146.97		2080.24		3298.47		80.196		5.666		3.573

				Combined		20950755		320.97		3717.78		4606.62		65.273		5.635		4.548

				INDONESIA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		13378896		135		1637.27		2076.72		99.103		8.171		6.442

						Funding		ODP-t				kt CO2 eq

				Phase II		8883314		84.33		1145.09		1651.44		105.340		7.758		5.379

				Combined		22262210		219.33		2782.36		3728.16		101.501		8.001		5.971

				IRAN		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		10869327		101.3		1271.82		1683.54		107.298		8.546		6.456

						Funding		ODP-t				kt CO2 eq

				Phase II		12279535		225.47		2697.64		3361.75		54.462		4.552		3.653

				Combined		23148862		326.77		3969.45		5045.29		70.841		6.427		4.969

				MEXICO		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		19421177		417.3		4019.09		3403.08		46.540		4.832		5.707

						Phase II		ODP-t				kt CO2 eq

				Phase II		11786341		560.53		6590.19		6915.58		21.027		1.788		1.704

				Combined		31207518		977.83		10609.28		10318.66		31.915		2.942		3.024

				LEBANON		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		2682242		20		226.36		260.78		134.112		11.849		10.286

						Funding		ODP-t				kt CO2 eq

				Phase II		4498093		41.16		544.45		764.22		109.283		8.262		5.886

				Combined		7180335		61.16		770.82		1025.00		117.402		9.315		7.005

				PERU		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						310111		3.74		51.73		75.97		82.917		5.995		4.082

				TOGO		Funding		ODP-t		tonnes		kt CO2 eq

						692650		7		127.27		230.36		98.950		5.442		3.007

				ALL COUNTRIES		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		1082844998		16071.39		209657.62		298469.49		67.377		5.183		3.747

				ALL MINUS CHINA		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		259129689		3911.14		44531.65		50851.88		66.254		5.786		5.053

				ALL COUNTRIES		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total (funds wtd)		1082844998		16071.39		209657.62		298469.49		69.534		5.334		3.827

				ALL MINUS CHINA		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total (funds wtd)		259129689		3911.14		44531.65		50851.88		75.241		6.431		5.417

				ALL COUNTRIES				funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				1082844998		209657.62		298469.49		67.377		5.183		3.747

				Total (funding wtd.)										69.534		5.334		3.827

				ALL MINUS CHINA				funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				259129689		44531.65		50851.88		66.254		5.918		5.094

				Total (funding wtd.)										75.241		6.431		5.417

																				ALL COUNTRIES						funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

																				Total		with support costs				1082844998		208988.940559441		297942.26991958		67.377		5.183		3.747

																						w/o support costs				1010975606						62.741		4.826		3.489

																				ALL MINUS CHINA						funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

																				Total		with support costs				548961369		43862.9755244755		50324.657506993		66.254		5.918		5.094

																						w/o support costs				477091977						61.205		5.467		4.706

				LVC COUNTRIES				funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total     ODP-t wtd						1314.88		1959.45		130.999		9.229		7.079

				Total     Fund wtd				11780077						212.854		13.418		9.107

																				ALL LVC						funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

																				Total		with support				11780077		1314.88		1959.45		130.999		9.229		7.079

																				Total		w/o support				10816046						120.261		8.489		6.524





Sheet3

		COST EFFECTIVENESS LVCs (with agency support costs included)																						COST EFFECTIVENESS LVCs (without agency support costs)

		ANGOLA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ANGOLA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		191840		1.59		28.9090909091		52.3254545455		120.654		6.636		3.666								Funding		176000		1.59		28.9090909091		52.3254545455		110.692		6.088		3.364

						Phase II																						Phase II

				Funding		967280		9.18		166.9090909091		302.1054545455		105.368		5.795		3.202								Funding		904000		9.18		166.9090909091		302.1054545455		98.475		5.416		2.992

		Combined		Funding		1159120		10.77		195.82		354.43		107.898		5.934		3.279		1.075				Combined		Funding		1080000		10.77		195.82		354.43		100.370		5.520		3.050

		ARMENIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ARMENIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		649121		2.23		33		51.5431818182		291.086		19.670		12.594								Funding		601838		2.23		33		51.5431818182		269.883		18.238		11.676

						Phase II																						Phase II

				Funding		238196		3.26		59.2727272727		107.2836363636		73.066		4.019		2.220								Funding		216000		3.26		59.2727272727		107.2836363636		66.258		3.644		2.013

		Combined		Funding		887317		5.49		92.27		158.83		232.559		15.469		9.809		1.086				Combined		Funding		817838		5.49		92.27		158.83		214.143		14.244		9.032

		CAMBODIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						CAMBODIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Funding		1772250		15		272.73		493.64		118.150		6.498		3.590		1.1077						Funding		1600000		15		272.73		493.64		106.662		5.866		3.241

		COSTA RICA				Phase I																		COSTA RICA				Phase I

				Funding		1240037		18.93		205.97		214.65		65.506		6.020		5.777		1.075						Funding		1153523		18.93		205.97		214.65		60.936		5.600		5.374

		CUBA				Phase I																		CUBA				Phase I

				Funding		1878592		19.26		205.18		214.05		97.539		9.156		8.776		1.075						Funding		1747527		19.26		205.18		214.05		90.734		8.517		8.164

		JAMAICA				Phase I																		JAMAICA				Phase I

				Funding		708844		8.13		114.82		172.02		87.189		6.174		4.121		1.0815						Funding		655450		8.13		114.82		172.02		80.618		5.708		3.810

		MALDIVES				Phase I																		MALDIVES				Phase I

				Funding		1219900		3.7		67.27		121.76		329.703		18.134		10.019		1.109						Funding		1100000		3.7		67.27		121.76		297.297		16.351		9.034

		MONGOLIA				Phase I																		MONGOLIA				Phase I

				Funding		413580		1		18.18		32.91		413.580		22.747		12.567		1.13						Funding		366000		1		18.18		32.91		366.000		20.130		11.122

		RWANDA				Phase I																		RWANDA				Phase I

				Funding		312000		1.44		26.27		41.78		216.667		11.875		7.468		1.1143						Funding		280000		1.44		26.27		41.78		194.442		10.657		6.702

		SERBIA				Phase I																		SERBIA				Phase I

				Funding		1050408		2.94		53.45		96.75		357.282		19.650		10.857		1.0793						Funding		973260		2.94		53.45		96.75		331.031		18.207		10.059

		SWAZILAND				Phase I																		SWAZILAND				Phase I

				Funding		955344		6.19		61.64		56.33		154.337		15.500		16.961		1.0882						Funding		877948		6.19		61.64		56.33		141.827		14.243		15.586

		UGANDA				Phase I																		UGANDA				Phase I

				Funding		182685		0.07		1.27		2.30		2609.786		143.538		79.303		1.1105						Funding		164500		0.07		1.27		2.30		2350.100		129.255		71.412

		LVC COUNTRIES				funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2												ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Total		ODP-t wtd				92.92		1314.8811188811		1959.4493581935		130.999		9.229		7.079						Total						92.92		1314.8811188811		1959.4493581935		120.261		8.489		6.524

		Total		Fund wtd		11780077								212.854		13.418		9.107

																												10816046

						11780077								212.854		13.418		9.107

		ALL LVC						ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

		Total		with support				92.92		1314.88		1959.45		130.999		9.229		7.079

		Total		w/o support										120.261		8.489		6.524






_1569142644.xls
Sheet1

		ACTIVITIES (all amounts in US$ million)

		HPMP actvts		May 2017		Removing elements as requested		Rescaling planned actvts		July 2017 impact		Certain planned  HPMPs cancl'd		Strict need for 35% reduction

		Total range incl. HPMP stage III		391.8-491.9		391.8-421.0

		HPMPs I/II value		406.3		406.3		388.4		375.9		341.4		325.0

		HPMP I/II range		391.8-420.9		391.8-420.9		376.3-400.4		366.5-385.3		336.6-346.1		322.3-327.6

				May 2017		If no stage III		If no stage III		If no stage III		If no stage III		If no stage III

		HPMP stg III		0-70.95		0		0		0		0		0

				May 2017		2 tranches		2 tranches		2 tranches		2 tranches		2 tranches

		HPPMPs (China)		67.2 (65.622)		48.8 (47.154)  52.6 (51.040)		48.8 (47.154)  52.6 (51.040)		48.8 (47.154)  52.6 (51.040)		48.8 (47.154)  52.6 (51.040)		48.8 (47.154)  52.6 (51.040)

				May 2017		No demo HCFC		No demo HCFC		No demo HCFC		No demo HCFC		No demo HCFC

		Non-inv/sup		114.1-124.1		114.1		114.1		114.1		114.1		114.1

				May 2017

		HFC enabling		21.5-44.2		no change 
(21.5-44.2)		no change 
(21.5-44.2)		no change 
(21.5-44.2)		no change 
(21.5-44.2)		no change 
(21.5-44.2)

				May 2017

		HFC-23 mitigation		8.0-21.5		no change      (8.0-21.5)		no change      (8.0-21.5)		no change      (8.0-21.5)		no change      (8.0-21.5)		no change      (8.0-21.5)

		(CAP 3%)		May 2017				Supplement		Supplement		Supplement		Supplement

		Total		602.7-748.9		584.2-653.4		568.7-632.8		558.9-617.8		529.0-578.5		514.7-560.0

		(0% CAP change)		US$ 2.0 million lower numbers

		(6% CAP change)		US$ 2.1 million higher numbers

		CAP increase						0%		3%		4.5%		6%

		Total supp (CAP)						112.1 (32.8)		114.1 (34.8)		115.1 (35.8)		116.2 (36.9)






_1569048038.xls
Sheet1

		

				ARGENTINA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ARGENTINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		11597593		83.53		1300.9090909091		2118.3127272727		138.843		8.915		5.475								Funding		10775154				83.53		1300.9090909091		2118.3127272727		128.997		8.283		5.087

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		10652124		115.19		1447.5874125874		1937.0464685315		92.474		7.359		5.499								Funding		9941238				115.19		1447.5874125874		1937.0464685315		86.303		6.867		5.132

				Combined		Funding		22249717		198.72		2079.82		3528.14		111.965		10.698		6.306						Combined		Funding		20716392		198.72		115.19		2079.82		3528.14		104.249		9.961		5.872		1.075

				BRAZIL				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						BRAZIL				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		21027388		220.3		2470.9090909091		2807.3636363636		95.449		8.510		7.490								Funding		19417866				220.3		2470.9090909091		2807.3636363636		88.143		7.859		6.917

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		38815539		464.06		5702		7352.6518181818		83.643		6.807		5.279								Funding		35963970				464.06		5702		7352.6518181818		77.499		6.307		4.891

				Combined		Funding		59842927		684.36		8172.91		10160.02		87.444		7.322		5.890						Combined		Funding		55381836		684.36		464.06		8172.91		10160.02		80.925		6.776		5.451		1.080

				CHINA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						CHINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		289831680		3445.6		46463.7412587413		69403.8854895105		84.116		6.238		4.176								Funding		270000000				3445.6		46463.7412587413		69403.8854895105		78.361		5.811		3.890

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		533883629		8714.65		118662.223776224		178213.726923077		61.263		4.499		2.996								Funding		500100000				8714.65		118662.223776224		178213.726923077		57.386		4.214		2.806

				Combined		Funding		823715309		12161.47		165126.0		247617.6		67.732		4.988		3.327						Combined		Funding		770100000		12161.47				165126.0		247617.6		63.323		4.664		3.110		1.0696

				INDIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						INDIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		22969344		341.77		3391		3074.755		67.207		6.774		7.470								Funding		21294490				341.77		3391		3074.755		62.306		6.280		6.926

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		48315260		769.49		8190.5454545455		8531.69		62.789		5.899		5.663								Funding		44911459				769.49		8190.5454545455		8531.69		58.365		5.483		5.264

				Combined		Funding		71284604		1111.26		11581.5454545455		11606.445		64.148		6.155		6.142						Combined		Funding		66205949		1111.26				11581.5454545455		11606.445		59.577		5.717		5.704		1.075

				EGYPT				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						EGYPT				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		9164414		174		1637.5454545454		1308.1486363636		52.669		5.596		7.006								Funding		8520815				174		1637.5454545454		1308.1486363636		48.970		5.203		6.514

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		11786341		146.97		2080.2377622378		3298.4692307692		80.196		5.666		3.573								Funding		10954863				146.97		2080.2377622378		3298.4692307692		74.538		5.266		3.321

				Combined		Funding		20950755		320.97		3717.78		4606.62		65.273		5.635		4.548						Combined		Funding		19475678		320.97				3717.78		4606.62		60.678		5.239		4.228		1.075

				INDONESIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						INDONESIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		13378896		135		1637.2727272727		2076.7227272727		99.103		8.171		6.442								Funding		12745484				135		1637.2727272727		2076.7227272727		94.411		7.785		6.137

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		8883314		84.33		1145.0909090909		1651.4372727273		105.340		7.758		5.379								Funding		8302163				84.33		1145.0909090909		1651.4372727273		98.449		7.250		5.027

				Combined		Funding		22262210		219.33		2782.36		3728.16		101.501		8.001		5.971						Combined		Funding		21047647		219.33				2782.36		3728.16		95.963		7.565		5.646		1.075

				IRAN				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						IRAN				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		10869327		101.3		1271.8181818182		1683.5409090909		107.298		8.546		6.456				10869327				Funding		9994338				101.3		1271.8181818182		1683.5409090909		98.661		7.858		5.936

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		12279535		225.47		2697.6363636364		3361.7490909091		54.462		4.552		3.653								Funding		11288177				225.47		2697.6363636364		3361.7490909091		50.065		4.184		3.358

				Combined		Funding		23148862		326.77		3969.45		5045.29		70.841		6.427		4.969						Combined		Funding		21282515		326.77				3969.45		5045.29		65.130		5.362		4.218		1.088

				MEXICO				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						MEXICO				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		19421177		417.3		4019.0909090909		3403.0772727273		46.540		4.832		5.707								Funding		18066211				417.3		4019.0909090909		3403.0772727273		43.293		4.495		5.309

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		11786341		560.53		6590.1923076923		6915.5810034965		21.027		1.788		1.704								Funding		11087772				560.53		6590.1923076923		6915.5810034965		19.781		1.682		1.603

				Combined		Funding		31207518		977.83		10609.2832167832		10318.6582762238		31.915		2.942		3.024						Combined		Funding		29153983		977.83				10609.2832167832		10318.6582762238		29.815		2.748		2.825		1.787

				LEBANON				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						LEBANON				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		2682242		20		226.3636363636		260.7772727273		134.112		11.849		10.286								Funding		2495109				20		226.3636363636		260.7772727273		124.755		11.023		9.568

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		4498093		41.16		544.4545454545		764.2213636364		109.283		8.262		5.886								Funding		4203826				41.16		544.4545454545		764.2213636364		102.134		7.721		5.501

				Combined		Funding		7180335		61.16		770.82		1025.00		117.402		9.315		7.005						Combined		Funding		6698935		61.16				770.82		1025.00		109.531		8.691		6.536		1.075

				PERU				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						PERU				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		310111		3.74		51.73		75.97		82.917		5.995		4.082								Funding		282671		3.74				51.73		75.97		75.580		5.465		3.721		1.097

				TOGO				Phase I		ODP-t		tonnes		kt CO2 eq												TOGO				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq

						Funding		692650		7		127.27		230.36		98.950		5.442		3.007								Funding		630000		7				127.27		230.36		90.000		4.950		2.735		1.0995

				ALL COUNTRIES						ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				1082844998		16072.61		208988.940559441		297942.27		69.529		5.387		3.844						Total				1010975606		16072.61				208988.940559441		297942.26991958		64.907		5.015		3.577

				ALL MINUS CHINA						ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				548961369		3911.14		43862.9755244755		50324.657506993		66.254		3.141		2.590						Total				477091977		3911.14				43862.9755244755		50324.657506993		35.328		3.099		2.559

				ALL COUNTRIES								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		weighted / ODP-t						208988.940559441		297942.26991958		67.543		5.215		3.757						Total		weighted / ODP-t				16072.61				208988.940559441		297942.26991958		62.901		4.856		3.498

						weighted / funding										69.730		5.387		3.843								weighted / funding												64.936		5.017		3.578				1.0323670634		1.0331341429		1.022889544

				ALL MINUS CHINA								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		weighted / ODP-t						43862.9755244755		50324.657506993		66.959		5.918		5.094						Total		weighted / ODP-t				3911.14				43862.9755244755		50324.657506993		61.587		5.455		4.706

						weighted / funding										76.219		6.672		5.498								weighted / funding												70.105		6.149		5.079				1.1383024243		1.1272889847		1.0792548979

				ALL COUNTRIES						funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		with support costs				1082844998		208988.940559441		297942.26991958		67.543		5.215		3.757						Total		w/o support costs				16072.61				208988.940559441		297942.26991958		62.901		4.856		3.498

						w/o support costs				1010975606						62.901		4.856		3.498								with support costs												64.936		5.017		3.578

				ALL MINUS CHINA						funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		with support costs				548961369		43862.9755244755		50324.657506993		66.959		5.918		5.094						Total		w/o support costs				3911.14				43862.9755244755		50324.657506993		61.587		5.455		4.706

						w/o support costs				477091977						61.587		5.455		4.706								with support costs												70.105		6.149		5.079





Sheet2

		

				ARGENTINA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		11597593		83.53		1300.91		2118.31		138.843		8.915		5.475

						Funding		ODP-t				kt CO2 eq

				Phase II		10652124		115.19		1447.59		1937.05		92.474		7.359		5.499

				Combined		22249717		198.72		2748.50		4055.36		111.965		8.095		5.486

				BRAZIL		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		21027388		220.3		2470.91		2807.36		95.449		8.510		7.490

						Funding		ODP-t				kt CO2 eq

				Phase II		38815539		464.06		5702.00		7352.65		83.643		6.807		5.279

				Combined		59842927		684.36		8172.91		10160.02		87.444		7.322		5.890

				CHINA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		289831680		3445.6		46463.74		69403.89		84.116		6.238		4.176

						Funding		ODP-t				kt CO2 eq

				Phase II		533883629		8714.65		118662.22		178213.73		61.263		4.499		2.996

				Combined		823715309		12160.25		165125.97		247617.61		67.738		4.988		3.327

				INDIA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		22969344		341.77		3391.00		3074.76		67.207		6.774		7.470

						Funding		ODP-t				kt CO2 eq

				Phase II		48315260		769.49		8190.55		8531.69		62.789		5.899		5.663

				Combined		71284604		1111.26		11581.55		11606.45		64.148		6.155		6.142

				EGYPT		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		9164414		174		1637.55		1308.15		52.669		5.596		7.006

						Funding		ODP-t				kt CO2 eq

				Phase II		11786341		146.97		2080.24		3298.47		80.196		5.666		3.573

				Combined		20950755		320.97		3717.78		4606.62		65.273		5.635		4.548

				INDONESIA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		13378896		135		1637.27		2076.72		99.103		8.171		6.442

						Funding		ODP-t				kt CO2 eq

				Phase II		8883314		84.33		1145.09		1651.44		105.340		7.758		5.379

				Combined		22262210		219.33		2782.36		3728.16		101.501		8.001		5.971

				IRAN		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		10869327		101.3		1271.82		1683.54		107.298		8.546		6.456

						Funding		ODP-t				kt CO2 eq

				Phase II		12279535		225.47		2697.64		3361.75		54.462		4.552		3.653

				Combined		23148862		326.77		3969.45		5045.29		70.841		6.427		4.969

				MEXICO		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		19421177		417.3		4019.09		3403.08		46.540		4.832		5.707

						Phase II		ODP-t				kt CO2 eq

				Phase II		11786341		560.53		6590.19		6915.58		21.027		1.788		1.704

				Combined		31207518		977.83		10609.28		10318.66		31.915		2.942		3.024

				LEBANON		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		2682242		20		226.36		260.78		134.112		11.849		10.286

						Funding		ODP-t				kt CO2 eq

				Phase II		4498093		41.16		544.45		764.22		109.283		8.262		5.886

				Combined		7180335		61.16		770.82		1025.00		117.402		9.315		7.005

				PERU		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						310111		3.74		51.73		75.97		82.917		5.995		4.082

				TOGO		Funding		ODP-t		tonnes		kt CO2 eq

						692650		7		127.27		230.36		98.950		5.442		3.007

				ALL COUNTRIES		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		1082844998		16071.39		209657.62		298469.49		67.377		5.183		3.747

				ALL MINUS CHINA		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		259129689		3911.14		44531.65		50851.88		66.254		5.786		5.053

				ALL COUNTRIES		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total (funds wtd)		1082844998		16071.39		209657.62		298469.49		69.534		5.334		3.827

				ALL MINUS CHINA		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total (funds wtd)		259129689		3911.14		44531.65		50851.88		75.241		6.431		5.417

				ALL COUNTRIES				funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				1082844998		209657.62		298469.49		67.377		5.183		3.747

				Total (funding wtd.)										69.534		5.334		3.827

				ALL MINUS CHINA				funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				259129689		44531.65		50851.88		66.254		5.918		5.094

				Total (funding wtd.)										75.241		6.431		5.417

																				ALL NON-LVC COUNTRIES						funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

																				Total		with support costs				1082844998		208988.940559441		297942.26991958		67.377		5.183		3.747

																						w/o support costs				1010975606						62.741		4.826		3.489

																				ALL NON LVC MINUS CHINA						funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

																				Total		with support costs				548961369		43862.9755244755		50324.657506993		66.254		5.918		5.094

																						w/o support costs				477091977						61.205		5.467		4.706






_1569047939.xls
Sheet1

		

				ARGENTINA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ARGENTINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		11597593		83.53		1300.9090909091		2118.3127272727		138.843		8.915		5.475								Funding		10775154				83.53		1300.9090909091		2118.3127272727		128.997		8.283		5.087

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		10652124		115.19		1447.5874125874		1937.0464685315		92.474		7.359		5.499								Funding		9941238				115.19		1447.5874125874		1937.0464685315		86.303		6.867		5.132

				Combined		Funding		22249717		198.72		2079.82		3528.14		111.965		10.698		6.306						Combined		Funding		20716392		198.72		115.19		2079.82		3528.14		104.249		9.961		5.872		1.075

				BRAZIL				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						BRAZIL				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		21027388		220.3		2470.9090909091		2807.3636363636		95.449		8.510		7.490								Funding		19417866				220.3		2470.9090909091		2807.3636363636		88.143		7.859		6.917

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		38815539		464.06		5702		7352.6518181818		83.643		6.807		5.279								Funding		35963970				464.06		5702		7352.6518181818		77.499		6.307		4.891

				Combined		Funding		59842927		684.36		8172.91		10160.02		87.444		7.322		5.890						Combined		Funding		55381836		684.36		464.06		8172.91		10160.02		80.925		6.776		5.451		1.080

				CHINA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						CHINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		289831680		3445.6		46463.7412587413		69403.8854895105		84.116		6.238		4.176								Funding		270000000				3445.6		46463.7412587413		69403.8854895105		78.361		5.811		3.890

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		533883629		8714.65		118662.223776224		178213.726923077		61.263		4.499		2.996								Funding		500100000				8714.65		118662.223776224		178213.726923077		57.386		4.214		2.806

				Combined		Funding		823715309		12161.47		165126.0		247617.6		67.732		4.988		3.327						Combined		Funding		770100000		12161.47				165126.0		247617.6		63.323		4.664		3.110		1.0696

				INDIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						INDIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		22969344		341.77		3391		3074.755		67.207		6.774		7.470								Funding		21294490				341.77		3391		3074.755		62.306		6.280		6.926

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		48315260		769.49		8190.5454545455		8531.69		62.789		5.899		5.663								Funding		44911459				769.49		8190.5454545455		8531.69		58.365		5.483		5.264

				Combined		Funding		71284604		1111.26		11581.5454545455		11606.445		64.148		6.155		6.142						Combined		Funding		66205949		1111.26				11581.5454545455		11606.445		59.577		5.717		5.704		1.075

				EGYPT				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						EGYPT				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		9164414		174		1637.5454545454		1308.1486363636		52.669		5.596		7.006								Funding		8520815				174		1637.5454545454		1308.1486363636		48.970		5.203		6.514

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		11786341		146.97		2080.2377622378		3298.4692307692		80.196		5.666		3.573								Funding		10954863				146.97		2080.2377622378		3298.4692307692		74.538		5.266		3.321

				Combined		Funding		20950755		320.97		3717.78		4606.62		65.273		5.635		4.548						Combined		Funding		19475678		320.97				3717.78		4606.62		60.678		5.239		4.228		1.075

				INDONESIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						INDONESIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		13378896		135		1637.2727272727		2076.7227272727		99.103		8.171		6.442								Funding		12745484				135		1637.2727272727		2076.7227272727		94.411		7.785		6.137

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		8883314		84.33		1145.0909090909		1651.4372727273		105.340		7.758		5.379								Funding		8302163				84.33		1145.0909090909		1651.4372727273		98.449		7.250		5.027

				Combined		Funding		22262210		219.33		2782.36		3728.16		101.501		8.001		5.971						Combined		Funding		21047647		219.33				2782.36		3728.16		95.963		7.565		5.646		1.075

				IRAN				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						IRAN				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		10869327		101.3		1271.8181818182		1683.5409090909		107.298		8.546		6.456				10869327				Funding		9994338				101.3		1271.8181818182		1683.5409090909		98.661		7.858		5.936

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		12279535		225.47		2697.6363636364		3361.7490909091		54.462		4.552		3.653								Funding		11288177				225.47		2697.6363636364		3361.7490909091		50.065		4.184		3.358

				Combined		Funding		23148862		326.77		3969.45		5045.29		70.841		6.427		4.969						Combined		Funding		21282515		326.77				3969.45		5045.29		65.130		5.362		4.218		1.088

				MEXICO				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						MEXICO				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		19421177		417.3		4019.0909090909		3403.0772727273		46.540		4.832		5.707								Funding		18066211				417.3		4019.0909090909		3403.0772727273		43.293		4.495		5.309

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		11786341		560.53		6590.1923076923		6915.5810034965		21.027		1.788		1.704								Funding		11087772				560.53		6590.1923076923		6915.5810034965		19.781		1.682		1.603

				Combined		Funding		31207518		977.83		10609.2832167832		10318.6582762238		31.915		2.942		3.024						Combined		Funding		29153983		977.83				10609.2832167832		10318.6582762238		29.815		2.748		2.825		1.787

				LEBANON				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						LEBANON				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		2682242		20		226.3636363636		260.7772727273		134.112		11.849		10.286								Funding		2495109				20		226.3636363636		260.7772727273		124.755		11.023		9.568

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		4498093		41.16		544.4545454545		764.2213636364		109.283		8.262		5.886								Funding		4203826				41.16		544.4545454545		764.2213636364		102.134		7.721		5.501

				Combined		Funding		7180335		61.16		770.82		1025.00		117.402		9.315		7.005						Combined		Funding		6698935		61.16				770.82		1025.00		109.531		8.691		6.536		1.075

				PERU				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						PERU				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		310111		3.74		51.73		75.97		82.917		5.995		4.082								Funding		282671		3.74				51.73		75.97		75.580		5.465		3.721		1.097

				TOGO				Phase I		ODP-t		tonnes		kt CO2 eq												TOGO				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq

						Funding		692650		7		127.27		230.36		98.950		5.442		3.007								Funding		630000		7				127.27		230.36		90.000		4.950		2.735		1.0995

				ALL COUNTRIES						ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				1082844998		16072.61		208988.940559441		297942.27		69.529		5.387		3.844						Total						16072.61				208988.940559441		297942.26991958		0.000		0.000		0.000

				ALL MINUS CHINA						ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				548961369		3911.14		43862.9755244755		50324.657506993		66.254		3.141		2.590						Total						3911.14				43862.9755244755		50324.657506993		0.000		0.000		0.000

				ALL COUNTRIES								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		weighted / ODP-t						208988.940559441		297942.26991958		67.543		5.215		3.757						Total		weighted / ODP-t				16072.61				208988.940559441		297942.26991958		62.901		4.856		3.498

						weighted / funding										69.730		5.387		3.843								weighted / funding												64.936		5.017		3.578				1.0323670634		1.0331341429		1.022889544

				ALL MINUS CHINA								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		weighted / ODP-t						43862.9755244755		50324.657506993		66.959		5.918		5.094						Total		weighted / ODP-t				3911.14				43862.9755244755		50324.657506993		61.587		5.455		4.706

						weighted / funding										76.219		6.672		5.498								weighted / funding												70.105		6.149		5.079				1.1383024243		1.1272889847		1.0792548979

				ALL COUNTRIES								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		with support costs						208988.940559441		297942.26991958		67.543		5.215		3.757						Total		w/o support costs				16072.61				208988.940559441		297942.26991958		62.901		4.856		3.498

						w/o support costs										62.901		4.856		3.498								with support costs												64.936		5.017		3.578

				ALL MINUS CHINA								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		with support costs						43862.9755244755		50324.657506993		66.959		5.918		5.094						Total		w/o support costs				3911.14				43862.9755244755		50324.657506993		61.587		5.455		4.706

						w/o support costs										61.587		5.455		4.706								with support costs												70.105		6.149		5.079





Sheet2

		

				ARGENTINA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		11597593		83.53		1300.91		2118.31		138.843		8.915		5.475

						Funding		ODP-t				kt CO2 eq

				Phase II		10652124		115.19		1447.59		1937.05		92.474		7.359		5.499

				Combined		22249717		198.72		2748.50		4055.36		111.965		8.095		5.486

				BRAZIL		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		21027388		220.3		2470.91		2807.36		95.449		8.510		7.490

						Funding		ODP-t				kt CO2 eq

				Phase II		38815539		464.06		5702.00		7352.65		83.643		6.807		5.279

				Combined		59842927		684.36		8172.91		10160.02		87.444		7.322		5.890

				CHINA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		289831680		3445.6		46463.74		69403.89		84.116		6.238		4.176

						Funding		ODP-t				kt CO2 eq

				Phase II		533883629		8714.65		118662.22		178213.73		61.263		4.499		2.996

				Combined		823715309		12160.25		165125.97		247617.61		67.738		4.988		3.327

				INDIA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		22969344		341.77		3391.00		3074.76		67.207		6.774		7.470

						Funding		ODP-t				kt CO2 eq

				Phase II		48315260		769.49		8190.55		8531.69		62.789		5.899		5.663

				Combined		71284604		1111.26		11581.55		11606.45		64.148		6.155		6.142

				EGYPT		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		9164414		174		1637.55		1308.15		52.669		5.596		7.006

						Funding		ODP-t				kt CO2 eq

				Phase II		11786341		146.97		2080.24		3298.47		80.196		5.666		3.573

				Combined		20950755		320.97		3717.78		4606.62		65.273		5.635		4.548

				INDONESIA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		13378896		135		1637.27		2076.72		99.103		8.171		6.442

						Funding		ODP-t				kt CO2 eq

				Phase II		8883314		84.33		1145.09		1651.44		105.340		7.758		5.379

				Combined		22262210		219.33		2782.36		3728.16		101.501		8.001		5.971

				IRAN		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		10869327		101.3		1271.82		1683.54		107.298		8.546		6.456

						Funding		ODP-t				kt CO2 eq

				Phase II		12279535		225.47		2697.64		3361.75		54.462		4.552		3.653

				Combined		23148862		326.77		3969.45		5045.29		70.841		6.427		4.969

				MEXICO		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		19421177		417.3		4019.09		3403.08		46.540		4.832		5.707

						Phase II		ODP-t				kt CO2 eq

				Phase II		11786341		560.53		6590.19		6915.58		21.027		1.788		1.704

				Combined		31207518		977.83		10609.28		10318.66		31.915		2.942		3.024

				LEBANON		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		2682242		20		226.36		260.78		134.112		11.849		10.286

						Funding		ODP-t				kt CO2 eq

				Phase II		4498093		41.16		544.45		764.22		109.283		8.262		5.886

				Combined		7180335		61.16		770.82		1025.00		117.402		9.315		7.005

				PERU		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						310111		3.74		51.73		75.97		82.917		5.995		4.082

				TOGO		Funding		ODP-t		tonnes		kt CO2 eq

						692650		7		127.27		230.36		98.950		5.442		3.007

				ALL COUNTRIES		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		1082844998		16071.39		209657.62		298469.49		67.377		5.183		3.747

				ALL MINUS CHINA		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		259129689		3911.14		44531.65		50851.88		66.254		5.786		5.053

				ALL COUNTRIES		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total (funds wtd)		1082844998		16071.39		209657.62		298469.49		69.534		5.334		3.827

				ALL MINUS CHINA		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total (funds wtd)		259129689		3911.14		44531.65		50851.88		75.241		6.431		5.417

				ALL NON-LVC COUNTRIES				funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				1082844998		209657.62		298469.49		67.377		5.183		3.747

				Total (funding wtd.)										69.534		5.334		3.827

				ALL NON-LVC MINUS CHINA				funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				259129689		44531.65		50851.88		66.254		5.918		5.094

				Total (funding wtd.)										75.241		6.431		5.417






_1568975036.xls
TablesforHPMPfunding

		Status May 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				82,534		97,099		111,664		13,507

		Non-LVCs		total				371,942		386,507		401,072		97,510

		LVCs		approved						6,132				2,727

		LVCs		planned						10,023				0.890

		LVCs		total						16,155				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						391,767		406,332		420,897		101,127

		14,565

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,239				91,046

		Non-LVCs		planned				63,007		74,126		85,245		9,439

		Non-LVCs		total				359,246		370,365		381,484		100,485

		LVCs		approved						6,132				3,209

		LVCs		planned						9,797				0.649

		LVCs		total						15,929				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						378,845		389,964		401,083		101,127

		11,119

		May 2017 with difference approach for planned funding

		(US$ million)								2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				69,911		80,835		91,758		11,245

		Non-LVCs		total				359,319		370,243		381,166		95,248

		LVCs		approved						6,132				2,727

		LVCs		planned				7,217		8,345		9,472		0.741

		LVCs		total				13,349		14,477		15,604		3,468

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						376,338		388,389		400,440		98,716

		12,051

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,238				91,046

		Non-LVCs		planned				53,370		61,710		70,049		7,858

		Non-LVCs		total				349,608		357,948		366,287		98,904

		LVCs		approved						6,132				3,209

		LVCs		planned				7,054		8,157		9,258		0.540

		LVCs		total				13,186		14,289		15,390		3,749

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						366,465		375,906		385,347		102,653

		9,441

		Status after ExCom July 2017 - only for proj <35% set of actvts (US$ million)																				Status after ExcCom July 2017

																						Only for Plans with <35% reduction, sets of activities (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min				max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				23,703		27,407		31,110		6,235								Non-LVCs		planned				23,703		27,407		31,110

		Non-LVCs		total				319,941		323,645		327,348		97,281								Non-LVCs		total				319,941		323,645		327,348

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				7,054		7,922		0		0.203								LVCs		planned				7,054		7,922		8,992

		LVCs		total				13,186		14,054		0		3,412								LVCs		total				13,186		14,054		15,124

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		341,368		0		100,693								Total (range)						336,594		341,368		346,142

																						4,774

		Status after ExCom July 2017 - only proj <35% done until 35% (US$ million)																				Status after ExCom July 2017

																						Only for Plans with <35% reduction, activities up to 35% (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min		avrg		max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				16,249		18,788		21,327		6,235								Non-LVCs		planned				16,249		18,788		21,327

		Non-LVCs		total				312,487		315,026		317,565		97,281								Non-LVCs		total				312,487		315,026		317,565

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				0.051		0.164		0.277		0.203								LVCs		planned				0.051		0.164		0.277

		LVCs		total				6,183		6,296		0		3,412								LVCs		total				6,183		6,296		6,409

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		324,992		0		100,693								Total (range)						322,340		324,992		327,644

																						2,652





Sheet1

		OLD												Analysis of the approved projects versus the projects in the business planning gives a variety of percentages per year.

														There are percentages per year from 2016 to 2002. The integrated 2002-16 value is 83.25%, i.e., approvals are 83.25% lower than planned.

														One can also look at the uncertainty in this value (STDV), and that is 11.25%, this implies that the uncertainty in the planned activities is 72%-94.5%.

		Status June 2017																Status June 2017																SUMMARY																				Status May 2017 (US$ million)

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				289408170				84003454						Non-LVCs		approved				289,408				84,003						a		391.77-420.90																		Non-LVCs

		Non-LVCs		planned				97098689				13506804						Non-LVCs		planned				69,911		91,758		9,725		12,764				b		378.84-401.08																		Non-LVCs

		Non-LVCs		total				386506859				97510294						Non-LVCs		total				359,319		381,166								c		343.46-353.42																		Non-LVCs

																																		d		325.56-332.34

		LVCs		approved				6132231				2727688						LVCs		approved				6,132				2,728																										LVCs

		LVCs		planned				10023178				889657						LVCs		planned				7,217		9,472		0.641		0.841				aa		376.34-400.44																		LVCs

		LVCs		total				16155409				3617345						LVCs		total				13,349		15,604								bb		366.46-385.35																		LVCs

																																		cc		356.59-346.14

		Extra amount countries						1903507										Extra amount countries						1,904										dd		322.34-327.64																		Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766										bbb		373.72-394.88																		HPMP verification

																																		ccc		343.16-354.45

		Total						406,331,575										Total (average)						388,389																														Total

		Uncertainty						14564803										Uncertainty (+/-)						12,051																														Uncertainty (+/-)

		Range						391.77-420.90										Range						376,338		400,440																												Range

		b																bb																		bbb																		b

		Status after ExCom July 2017																Status after ExCom July 2017																		Status after ExCom July 2017																		Status after ExCom July 2017

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046								Non-LVCs

		Non-LVCs		planned				74125647				9439215						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs

		Non-LVCs		total				370364581				100485322						Non-LVCs		total				349,608		366,287										Non-LVCs		total				349,608		366,287										Non-LVCs

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209								LVCs

		LVCs		planned				9797194				648919						LVCs		planned				7,054		9,258		0.467		0.613						LVCs		planned				7,054		9,258		0.467		0.613						LVCs

		LVCs		total				15929425				3617345						LVCs		total				13,186		15,390										LVCs		total				13,186		15,390										LVCs

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904												Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766												HPMP verification

																																				PLANNED 2017 ONES ARE ADDED						7,263		9,533

		Total						389,963,313										Total						375,906												Total						384,304												Total

		Uncertainty						11118847										Uncertainty						9,441												Uncertainty						10,576												Uncertainty

		Range						378.84-401.08										Range						366,464		385,347										Range						373,728		394,888										Range

		c																cc																		ccc

		Status after ExCom July 2017 - only proj< 35% filled up - prgm																Status after ExCom July 2017 - only proj< 35% filled up - prgm																		Status after ExCom July 2017 - only proj< 35% filled up - prgm

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				32920585				7489407						Non-LVCs		planned				23,703		31,110		5,392		7,077						Non-LVCs		planned				23,703		31,110		5,392		7,077

		Non-LVCs		total				329159519				98535514						Non-LVCs		total				319,941		327,348										Non-LVCs		total				319,941		327,348

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209

		LVCs		planned				9514894				243500						LVCs		planned				6,851		8,992		0.175		0.230						LVCs		planned				6,851		8,992		0.175		0.230

		LVCs		total				15647125				3617345						LVCs		total				12,983		15,124										LVCs		total				12,983		15,124

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766

								348475951																												PLANNED 2017 ONES ARE ADDED						5,567		7,307

		Total						348,475,951										Total						341,368												Total						348,805

		Uncertainty						4938088										Uncertainty						4,774												Uncertainty						5,644

		Range						343.46-353.42										Range						336,594		346,142										Range						343,161		354,449

		d																dd

		Status after ExCom July 2017 - only proj< 35% done until 35%																Status after ExCom July 2017 - only proj< 35% done until 35%

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				22568707				0						Non-LVCs		planned				16,249		21,327		0

		Non-LVCs		total				318807641				91046107						Non-LVCs		total				312,487		317,565		91,046

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209

		LVCs		planned				1001751				0						LVCs		planned				0.721		0.947		0

		LVCs		total				7133982				3209188						LVCs		total				6,853		7,079		3,209

		Extra amount countries						1239169										Extra amount countries						1,234

		HPMP verification						1765800										HPMP verification						1,766

								328946592

		Total						328,946,592										Total						324,992

		Uncertainty						3385306										Uncertainty						2,652

		Range						325.56-332.34										Range						322,340		327,644






_1568975279.xls
TablesforHPMPfunding

		Status May 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				82,534		97,099		111,664		13,507

		Non-LVCs		total				371,942		386,507		401,072		97,510

		LVCs		approved						6,132				2,727

		LVCs		planned						10,023				0.890

		LVCs		total						16,155				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						391,767		406,332		420,897		101,127

		14,565

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,239				91,046

		Non-LVCs		planned				63,007		74,126		85,245		9,439

		Non-LVCs		total				359,246		370,365		381,484		100,485

		LVCs		approved						6,132				3,209

		LVCs		planned						9,797				0.649

		LVCs		total						15,929				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						378,845		389,964		401,083		101,127

		11,119

		May 2017 with difference approach for planned funding

		(US$ million)								2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				69,911		80,835		91,758		11,245

		Non-LVCs		total				359,319		370,243		381,166		95,248

		LVCs		approved						6,132				2,727

		LVCs		planned				7,217		8,345		9,472		0.741

		LVCs		total				13,349		14,477		15,604		3,468

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						376,338		388,389		400,440		98,716

		12,051

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,238				91,046

		Non-LVCs		planned				53,370		61,710		70,049		7,858

		Non-LVCs		total				349,608		357,948		366,287		98,904

		LVCs		approved						6,132				3,209

		LVCs		planned				7,054		8,157		9,258		0.540

		LVCs		total				13,186		14,289		15,390		3,749

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						366,465		375,906		385,347		102,653

		9,441

		Status after ExCom July 2017 - only for proj <35% set of actvts (US$ million)																				Status after ExcCom July 2017

																						Only for Plans with <35% reduction, sets of activities (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min				max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				23,703		27,407		31,110		6,235								Non-LVCs		planned				23,703		27,407		31,110

		Non-LVCs		total				319,941		323,645		327,348		97,281								Non-LVCs		total				319,941		323,645		327,348

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				7,054		7,922		0		0.203								LVCs		planned				7,054		7,922		8,992

		LVCs		total				13,186		14,054		0		3,412								LVCs		total				13,186		14,054		15,124

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		341,368		0		100,693								Total (range)						336,594		341,368		346,142

																						4,774

		Status after ExCom July 2017 - only proj <35% done until 35% (US$ million)																				Status after ExCom July 2017

																						Only for Plans with <35% reduction, activities up to 35% (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min		avrg		max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				16,249		18,788		21,327		6,235								Non-LVCs		planned				16,249		18,788		21,327

		Non-LVCs		total				312,487		315,026		317,565		97,281								Non-LVCs		total				312,487		315,026		317,565

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				0.051		0.164		0.277		0.203								LVCs		planned				0.051		0.164		0.277

		LVCs		total				6,183		6,296		0		3,412								LVCs		total				6,183		6,296		6,409

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		324,992		0		100,693								Total (range)						322,340		324,992		327,644

																						2,652





Sheet1

		OLD												Analysis of the approved projects versus the projects in the business planning gives a variety of percentages per year.

														There are percentages per year from 2016 to 2002. The integrated 2002-16 value is 83.25%, i.e., approvals are 83.25% lower than planned.

														One can also look at the uncertainty in this value (STDV), and that is 11.25%, this implies that the uncertainty in the planned activities is 72%-94.5%.

		Status June 2017																Status June 2017																SUMMARY																				Status May 2017 (US$ million)

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				289408170				84003454						Non-LVCs		approved				289,408				84,003						a		391.77-420.90																		Non-LVCs

		Non-LVCs		planned				97098689				13506804						Non-LVCs		planned				69,911		91,758		9,725		12,764				b		378.84-401.08																		Non-LVCs

		Non-LVCs		total				386506859				97510294						Non-LVCs		total				359,319		381,166								c		343.46-353.42																		Non-LVCs

																																		d		325.56-332.34

		LVCs		approved				6132231				2727688						LVCs		approved				6,132				2,728																										LVCs

		LVCs		planned				10023178				889657						LVCs		planned				7,217		9,472		0.641		0.841				aa		376.34-400.44																		LVCs

		LVCs		total				16155409				3617345						LVCs		total				13,349		15,604								bb		366.46-385.35																		LVCs

																																		cc		356.59-346.14

		Extra amount countries						1903507										Extra amount countries						1,904										dd		322.34-327.64																		Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766										bbb		373.72-394.88																		HPMP verification

																																		ccc		343.16-354.45

		Total						406,331,575										Total (average)						388,389																														Total

		Uncertainty						14564803										Uncertainty (+/-)						12,051																														Uncertainty (+/-)

		Range						391.77-420.90										Range						376,338		400,440																												Range

		b																bb																		bbb																		b

		Status after ExCom July 2017																Status after ExCom July 2017																		Status after ExCom July 2017																		Status after ExCom July 2017

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046								Non-LVCs

		Non-LVCs		planned				74125647				9439215						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs

		Non-LVCs		total				370364581				100485322						Non-LVCs		total				349,608		366,287										Non-LVCs		total				349,608		366,287										Non-LVCs

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209								LVCs

		LVCs		planned				9797194				648919						LVCs		planned				7,054		9,258		0.467		0.613						LVCs		planned				7,054		9,258		0.467		0.613						LVCs

		LVCs		total				15929425				3617345						LVCs		total				13,186		15,390										LVCs		total				13,186		15,390										LVCs

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904												Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766												HPMP verification

																																				PLANNED 2017 ONES ARE ADDED						7,263		9,533

		Total						389,963,313										Total						375,906												Total						384,304												Total

		Uncertainty						11118847										Uncertainty						9,441												Uncertainty						10,576												Uncertainty

		Range						378.84-401.08										Range						366,464		385,347										Range						373,728		394,888										Range

		c																cc																		ccc

		Status after ExCom July 2017 - only proj< 35% filled up - prgm																Status after ExCom July 2017 - only proj< 35% filled up - prgm																		Status after ExCom July 2017 - only proj< 35% filled up - prgm

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				32920585				7489407						Non-LVCs		planned				23,703		31,110		5,392		7,077						Non-LVCs		planned				23,703		31,110		5,392		7,077

		Non-LVCs		total				329159519				98535514						Non-LVCs		total				319,941		327,348										Non-LVCs		total				319,941		327,348

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209

		LVCs		planned				9514894				243500						LVCs		planned				6,851		8,992		0.175		0.230						LVCs		planned				6,851		8,992		0.175		0.230

		LVCs		total				15647125				3617345						LVCs		total				12,983		15,124										LVCs		total				12,983		15,124

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766

								348475951																												PLANNED 2017 ONES ARE ADDED						5,567		7,307

		Total						348,475,951										Total						341,368												Total						348,805

		Uncertainty						4938088										Uncertainty						4,774												Uncertainty						5,644

		Range						343.46-353.42										Range						336,594		346,142										Range						343,161		354,449

		d																dd

		Status after ExCom July 2017 - only proj< 35% done until 35%																Status after ExCom July 2017 - only proj< 35% done until 35%

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				22568707				0						Non-LVCs		planned				16,249		21,327		0

		Non-LVCs		total				318807641				91046107						Non-LVCs		total				312,487		317,565		91,046

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209

		LVCs		planned				1001751				0						LVCs		planned				0.721		0.947		0

		LVCs		total				7133982				3209188						LVCs		total				6,853		7,079		3,209

		Extra amount countries						1239169										Extra amount countries						1,234

		HPMP verification						1765800										HPMP verification						1,766

								328946592

		Total						328,946,592										Total						324,992

		Uncertainty						3385306										Uncertainty						2,652

		Range						325.56-332.34										Range						322,340		327,644






_1568975543.xls
TablesforHPMPfunding

		Status May 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				82,534		97,099		111,664		13,507

		Non-LVCs		total				371,942		386,507		401,072		97,510

		LVCs		approved						6,132				2,727

		LVCs		planned						10,023				0.890

		LVCs		total						16,155				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						391,767		406,332		420,897		101,127

		14,565

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,239				91,046

		Non-LVCs		planned				63,007		74,126		85,245		9,439

		Non-LVCs		total				359,246		370,365		381,484		100,485

		LVCs		approved						6,132				3,209

		LVCs		planned						9,797				0.649

		LVCs		total						15,929				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						378,845		389,964		401,083		101,127

		11,119

		May 2017 with difference approach for planned funding

		(US$ million)								2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				69,911		80,835		91,758		11,245

		Non-LVCs		total				359,319		370,243		381,166		95,248

		LVCs		approved						6,132				2,727

		LVCs		planned				7,217		8,345		9,472		0.741

		LVCs		total				13,349		14,477		15,604		3,468

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						376,338		388,389		400,440		98,716

		12,051

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,238				91,046

		Non-LVCs		planned				53,370		61,710		70,049		7,858

		Non-LVCs		total				349,608		357,948		366,287		98,904

		LVCs		approved						6,132				3,209

		LVCs		planned				7,054		8,157		9,258		0.540

		LVCs		total				13,186		14,289		15,390		3,749

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						366,465		375,906		385,347		102,653

		9,441

		Status after ExCom July 2017 - only for proj <35% set of actvts (US$ million)																				Status after ExcCom July 2017

																						Only for Plans with <35% reduction, sets of activities (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min				max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				23,703		27,407		31,110		6,235								Non-LVCs		planned				23,703		27,407		31,110

		Non-LVCs		total				319,941		323,645		327,348		97,281								Non-LVCs		total				319,941		323,645		327,348

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				7,054		7,922		0		0.203								LVCs		planned				7,054		7,922		8,992

		LVCs		total				13,186		14,054		0		3,412								LVCs		total				13,186		14,054		15,124

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		341,368		0		100,693								Total (range)						336,594		341,368		346,142

																						4,774

		Status after ExCom July 2017 - only proj <35% done until 35% (US$ million)																				Status after ExCom July 2017

																						Only for Plans with <35% reduction, activities up to 35% (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min		avrg		max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				16,249		18,788		21,327		6,235								Non-LVCs		planned				16,249		18,788		21,327

		Non-LVCs		total				312,487		315,026		317,565		97,281								Non-LVCs		total				312,487		315,026		317,565

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				0.051		0.164		0.277		0.203								LVCs		planned				0.051		0.164		0.277

		LVCs		total				6,183		6,296		0		3,412								LVCs		total				6,183		6,296		6,409

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		324,992		0		100,693								Total (range)						322,340		324,992		327,644

																						2,652





Sheet1

		OLD												Analysis of the approved projects versus the projects in the business planning gives a variety of percentages per year.

														There are percentages per year from 2016 to 2002. The integrated 2002-16 value is 83.25%, i.e., approvals are 83.25% lower than planned.

														One can also look at the uncertainty in this value (STDV), and that is 11.25%, this implies that the uncertainty in the planned activities is 72%-94.5%.

		Status June 2017																Status June 2017																SUMMARY																				Status May 2017 (US$ million)

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				289408170				84003454						Non-LVCs		approved				289,408				84,003						a		391.77-420.90																		Non-LVCs

		Non-LVCs		planned				97098689				13506804						Non-LVCs		planned				69,911		91,758		9,725		12,764				b		378.84-401.08																		Non-LVCs

		Non-LVCs		total				386506859				97510294						Non-LVCs		total				359,319		381,166								c		343.46-353.42																		Non-LVCs

																																		d		325.56-332.34

		LVCs		approved				6132231				2727688						LVCs		approved				6,132				2,728																										LVCs

		LVCs		planned				10023178				889657						LVCs		planned				7,217		9,472		0.641		0.841				aa		376.34-400.44																		LVCs

		LVCs		total				16155409				3617345						LVCs		total				13,349		15,604								bb		366.46-385.35																		LVCs

																																		cc		356.59-346.14

		Extra amount countries						1903507										Extra amount countries						1,904										dd		322.34-327.64																		Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766										bbb		373.72-394.88																		HPMP verification

																																		ccc		343.16-354.45

		Total						406,331,575										Total (average)						388,389																														Total

		Uncertainty						14564803										Uncertainty (+/-)						12,051																														Uncertainty (+/-)

		Range						391.77-420.90										Range						376,338		400,440																												Range

		b																bb																		bbb																		b

		Status after ExCom July 2017																Status after ExCom July 2017																		Status after ExCom July 2017																		Status after ExCom July 2017

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046								Non-LVCs

		Non-LVCs		planned				74125647				9439215						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs

		Non-LVCs		total				370364581				100485322						Non-LVCs		total				349,608		366,287										Non-LVCs		total				349,608		366,287										Non-LVCs

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209								LVCs

		LVCs		planned				9797194				648919						LVCs		planned				7,054		9,258		0.467		0.613						LVCs		planned				7,054		9,258		0.467		0.613						LVCs

		LVCs		total				15929425				3617345						LVCs		total				13,186		15,390										LVCs		total				13,186		15,390										LVCs

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904												Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766												HPMP verification

																																				PLANNED 2017 ONES ARE ADDED						7,263		9,533

		Total						389,963,313										Total						375,906												Total						384,304												Total

		Uncertainty						11118847										Uncertainty						9,441												Uncertainty						10,576												Uncertainty

		Range						378.84-401.08										Range						366,464		385,347										Range						373,728		394,888										Range

		c																cc																		ccc

		Status after ExCom July 2017 - only proj< 35% filled up - prgm																Status after ExCom July 2017 - only proj< 35% filled up - prgm																		Status after ExCom July 2017 - only proj< 35% filled up - prgm

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				32920585				7489407						Non-LVCs		planned				23,703		31,110		5,392		7,077						Non-LVCs		planned				23,703		31,110		5,392		7,077

		Non-LVCs		total				329159519				98535514						Non-LVCs		total				319,941		327,348										Non-LVCs		total				319,941		327,348

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209

		LVCs		planned				9514894				243500						LVCs		planned				6,851		8,992		0.175		0.230						LVCs		planned				6,851		8,992		0.175		0.230

		LVCs		total				15647125				3617345						LVCs		total				12,983		15,124										LVCs		total				12,983		15,124

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766

								348475951																												PLANNED 2017 ONES ARE ADDED						5,567		7,307

		Total						348,475,951										Total						341,368												Total						348,805

		Uncertainty						4938088										Uncertainty						4,774												Uncertainty						5,644

		Range						343.46-353.42										Range						336,594		346,142										Range						343,161		354,449

		d																dd

		Status after ExCom July 2017 - only proj< 35% done until 35%																Status after ExCom July 2017 - only proj< 35% done until 35%

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				22568707				0						Non-LVCs		planned				16,249		21,327		0

		Non-LVCs		total				318807641				91046107						Non-LVCs		total				312,487		317,565		91,046

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209

		LVCs		planned				1001751				0						LVCs		planned				0.721		0.947		0

		LVCs		total				7133982				3209188						LVCs		total				6,853		7,079		3,209

		Extra amount countries						1239169										Extra amount countries						1,234

		HPMP verification						1765800										HPMP verification						1,766

								328946592

		Total						328,946,592										Total						324,992

		Uncertainty						3385306										Uncertainty						2,652

		Range						325.56-332.34										Range						322,340		327,644






_1569047779.xls
Sheet1

		

				ARGENTINA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ARGENTINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		11597593		83.53		1300.9090909091		2118.3127272727		138.843		8.915		5.475								Funding		10775154				83.53		1300.9090909091		2118.3127272727		128.997		8.283		5.087

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		10652124		115.19		1447.5874125874		1937.0464685315		92.474		7.359		5.499								Funding		9941238				115.19		1447.5874125874		1937.0464685315		86.303		6.867		5.132

				Combined		Funding		22249717		198.72		2079.82		3528.14		111.965		10.698		6.306						Combined		Funding		20716392		198.72		115.19		2079.82		3528.14		104.249		9.961		5.872		1.075

				BRAZIL				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						BRAZIL				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		21027388		220.3		2470.9090909091		2807.3636363636		95.449		8.510		7.490								Funding		19417866				220.3		2470.9090909091		2807.3636363636		88.143		7.859		6.917

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		38815539		464.06		5702		7352.6518181818		83.643		6.807		5.279								Funding		35963970				464.06		5702		7352.6518181818		77.499		6.307		4.891

				Combined		Funding		59842927		684.36		8172.91		10160.02		87.444		7.322		5.890						Combined		Funding		55381836		684.36		464.06		8172.91		10160.02		80.925		6.776		5.451		1.080

				CHINA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						CHINA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		289831680		3445.6		46463.7412587413		69403.8854895105		84.116		6.238		4.176								Funding		270000000				3445.6		46463.7412587413		69403.8854895105		78.361		5.811		3.890

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		533883629		8714.65		118662.223776224		178213.726923077		61.263		4.499		2.996								Funding		500100000				8714.65		118662.223776224		178213.726923077		57.386		4.214		2.806

				Combined		Funding		823715309		12161.47		165126.0		247617.6		67.732		4.988		3.327						Combined		Funding		770100000		12161.47				165126.0		247617.6		63.323		4.664		3.110		1.0696

				INDIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						INDIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		22969344		341.77		3391		3074.755		67.207		6.774		7.470								Funding		21294490				341.77		3391		3074.755		62.306		6.280		6.926

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		48315260		769.49		8190.5454545455		8531.69		62.789		5.899		5.663								Funding		44911459				769.49		8190.5454545455		8531.69		58.365		5.483		5.264

				Combined		Funding		71284604		1111.26		11581.5454545455		11606.445		64.148		6.155		6.142						Combined		Funding		66205949		1111.26				11581.5454545455		11606.445		59.577		5.717		5.704		1.075

				EGYPT				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						EGYPT				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		9164414		174		1637.5454545454		1308.1486363636		52.669		5.596		7.006								Funding		8520815				174		1637.5454545454		1308.1486363636		48.970		5.203		6.514

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		11786341		146.97		2080.2377622378		3298.4692307692		80.196		5.666		3.573								Funding		10954863				146.97		2080.2377622378		3298.4692307692		74.538		5.266		3.321

				Combined		Funding		20950755		320.97		3717.78		4606.62		65.273		5.635		4.548						Combined		Funding		19475678		320.97				3717.78		4606.62		60.678		5.239		4.228		1.075

				INDONESIA				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						INDONESIA				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		13378896		135		1637.2727272727		2076.7227272727		99.103		8.171		6.442								Funding		12745484				135		1637.2727272727		2076.7227272727		94.411		7.785		6.137

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		8883314		84.33		1145.0909090909		1651.4372727273		105.340		7.758		5.379								Funding		8302163				84.33		1145.0909090909		1651.4372727273		98.449		7.250		5.027

				Combined		Funding		22262210		219.33		2782.36		3728.16		101.501		8.001		5.971						Combined		Funding		21047647		219.33				2782.36		3728.16		95.963		7.565		5.646		1.075

				IRAN				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						IRAN				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		10869327		101.3		1271.8181818182		1683.5409090909		107.298		8.546		6.456				10869327				Funding		9994338				101.3		1271.8181818182		1683.5409090909		98.661		7.858		5.936

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		12279535		225.47		2697.6363636364		3361.7490909091		54.462		4.552		3.653								Funding		11288177				225.47		2697.6363636364		3361.7490909091		50.065		4.184		3.358

				Combined		Funding		23148862		326.77		3969.45		5045.29		70.841		6.427		4.969						Combined		Funding		21282515		326.77				3969.45		5045.29		65.130		5.362		4.218		1.088

				MEXICO				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						MEXICO				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		19421177		417.3		4019.0909090909		3403.0772727273		46.540		4.832		5.707								Funding		18066211				417.3		4019.0909090909		3403.0772727273		43.293		4.495		5.309

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		11786341		560.53		6590.1923076923		6915.5810034965		21.027		1.788		1.704								Funding		11087772				560.53		6590.1923076923		6915.5810034965		19.781		1.682		1.603

				Combined		Funding		31207518		977.83		10609.2832167832		10318.6582762238		31.915		2.942		3.024						Combined		Funding		29153983		977.83				10609.2832167832		10318.6582762238		29.815		2.748		2.825		1.787

				LEBANON				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						LEBANON				Phase I				ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		2682242		20		226.3636363636		260.7772727273		134.112		11.849		10.286								Funding		2495109				20		226.3636363636		260.7772727273		124.755		11.023		9.568

								Phase II		ODP-t				kt CO2 eq																Phase II		ODP total		ODP-t				kt CO2 eq

						Funding		4498093		41.16		544.4545454545		764.2213636364		109.283		8.262		5.886								Funding		4203826				41.16		544.4545454545		764.2213636364		102.134		7.721		5.501

				Combined		Funding		7180335		61.16		770.82		1025.00		117.402		9.315		7.005						Combined		Funding		6698935		61.16				770.82		1025.00		109.531		8.691		6.536		1.075

				PERU				Phase I		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						PERU				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						Funding		310111		3.74		51.73		75.97		82.917		5.995		4.082								Funding		282671		3.74				51.73		75.97		75.580		5.465		3.721		1.097

				TOGO				Phase I		ODP-t		tonnes		kt CO2 eq												TOGO				Phase I		ODP total		ODP-t		tonnes		kt CO2 eq

						Funding		692650		7		127.27		230.36		98.950		5.442		3.007								Funding		630000		7				127.27		230.36		90.000		4.950		2.735		1.0995

				ALL COUNTRIES						ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				1082844998		16072.61		208988.940559441		297942.27		69.529		5.387		3.844						Total						16072.61				208988.940559441		297942.26991958		0.000		0.000		0.000

				ALL MINUS CHINA						ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				548961369		3911.14		43862.9755244755		50324.657506993		66.254		3.141		2.590						Total						3911.14				43862.9755244755		50324.657506993		0.000		0.000		0.000

				ALL COUNTRIES								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		weighted / ODP-t						208988.940559441		297942.26991958		67.543		5.215		3.757						Total		weighted / ODP-t				16072.61				208988.940559441		297942.26991958		62.901		4.856		3.498

						weighted / funding										69.730		5.387		3.843								weighted / funding												64.936		5.017		3.578				1.0323670634		1.0331341429		1.022889544

				ALL MINUS CHINA								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		weighted / ODP-t						43862.9755244755		50324.657506993		66.959		5.918		5.094						Total		weighted / ODP-t				3911.14				43862.9755244755		50324.657506993		61.587		5.455		4.706

						weighted / funding										76.219		6.672		5.498								weighted / funding												70.105		6.149		5.079				1.1383024243		1.1272889847		1.0792548979

				ALL COUNTRIES								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL COUNTRIES						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		with support costs						208988.940559441		297942.26991958		67.543		5.215		3.757						Total		w/o support costs				16072.61				208988.940559441		297942.26991958		62.901		4.856		3.498

						w/o support costs										62.901		4.856		3.498								with support costs												64.936		5.017		3.578

				ALL MINUS CHINA								tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2						ALL MINUS CHINA						ODP-tonnes				tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		with support costs						43862.9755244755		50324.657506993		66.959		5.918		5.094						Total		w/o support costs				3911.14				43862.9755244755		50324.657506993		61.587		5.455		4.706

						w/o support costs										61.587		5.455		4.706								with support costs												70.105		6.149		5.079





Sheet2

		

				ARGENTINA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		11597593		83.53		1300.91		2118.31		138.843		8.915		5.475

						Funding		ODP-t				kt CO2 eq

				Phase II		10652124		115.19		1447.59		1937.05		92.474		7.359		5.499

				Combined		22249717		198.72		2748.50		4055.36		111.965		8.095		5.486

				BRAZIL		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		21027388		220.3		2470.91		2807.36		95.449		8.510		7.490

						Funding		ODP-t				kt CO2 eq

				Phase II		38815539		464.06		5702.00		7352.65		83.643		6.807		5.279

				Combined		59842927		684.36		8172.91		10160.02		87.444		7.322		5.890

				CHINA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		289831680		3445.6		46463.74		69403.89		84.116		6.238		4.176

						Funding		ODP-t				kt CO2 eq

				Phase II		533883629		8714.65		118662.22		178213.73		61.263		4.499		2.996

				Combined		823715309		12160.25		165125.97		247617.61		67.738		4.988		3.327

				INDIA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		22969344		341.77		3391.00		3074.76		67.207		6.774		7.470

						Funding		ODP-t				kt CO2 eq

				Phase II		48315260		769.49		8190.55		8531.69		62.789		5.899		5.663

				Combined		71284604		1111.26		11581.55		11606.45		64.148		6.155		6.142

				EGYPT		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		9164414		174		1637.55		1308.15		52.669		5.596		7.006

						Funding		ODP-t				kt CO2 eq

				Phase II		11786341		146.97		2080.24		3298.47		80.196		5.666		3.573

				Combined		20950755		320.97		3717.78		4606.62		65.273		5.635		4.548

				INDONESIA		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		13378896		135		1637.27		2076.72		99.103		8.171		6.442

						Funding		ODP-t				kt CO2 eq

				Phase II		8883314		84.33		1145.09		1651.44		105.340		7.758		5.379

				Combined		22262210		219.33		2782.36		3728.16		101.501		8.001		5.971

				IRAN		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		10869327		101.3		1271.82		1683.54		107.298		8.546		6.456

						Funding		ODP-t				kt CO2 eq

				Phase II		12279535		225.47		2697.64		3361.75		54.462		4.552		3.653

				Combined		23148862		326.77		3969.45		5045.29		70.841		6.427		4.969

				MEXICO		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		19421177		417.3		4019.09		3403.08		46.540		4.832		5.707

						Phase II		ODP-t				kt CO2 eq

				Phase II		11786341		560.53		6590.19		6915.58		21.027		1.788		1.704

				Combined		31207518		977.83		10609.28		10318.66		31.915		2.942		3.024

				LEBANON		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Phase I		2682242		20		226.36		260.78		134.112		11.849		10.286

						Funding		ODP-t				kt CO2 eq

				Phase II		4498093		41.16		544.45		764.22		109.283		8.262		5.886

				Combined		7180335		61.16		770.82		1025.00		117.402		9.315		7.005

				PERU		Funding		ODP-t		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

						310111		3.74		51.73		75.97		82.917		5.995		4.082

				TOGO		Funding		ODP-t		tonnes		kt CO2 eq

						692650		7		127.27		230.36		98.950		5.442		3.007

				ALL NON-LVC CTRS		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		1082844998		16071.39		209657.62		298469.49		67.377		5.183		3.747

				ALL MINUS CHINA		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		259129689		3911.14		44531.65		50851.88		66.254		5.786		5.053

				ALL COUNTRIES		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		1082844998		16071.39		209657.62		298469.49		69.534		5.334		3.827

				ALL MINUS CHINA		funding		ODP-tonnes		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total		259129689		3911.14		44531.65		50851.88		75.241		6.431		5.417

				ALL COUNTRIES				funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				1082844998		209657.62		298469.49		67.377		5.183		3.747

														69.534		5.334		3.827

				ALL MINUS CHINA				funding		tonnes		kt CO2 eq		US$/ODP-kg		US$/kg		US$/t CO2

				Total				259129689		44531.65		50851.88		66.254		5.918		5.094

														75.241		6.431		5.417






_1568975393.xls
TablesforHPMPfunding

		Status May 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				82,534		97,099		111,664		13,507

		Non-LVCs		total				371,942		386,507		401,072		97,510

		LVCs		approved						6,132				2,727

		LVCs		planned						10,023				0.890

		LVCs		total						16,155				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						391,767		406,332		420,897		101,127

		14,565

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,239				91,046

		Non-LVCs		planned				63,007		74,126		85,245		9,439

		Non-LVCs		total				359,246		370,365		381,484		100,485

		LVCs		approved						6,132				3,209

		LVCs		planned						9,797				0.649

		LVCs		total						15,929				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						378,845		389,964		401,083		101,127

		11,119

		May 2017 with difference approach for planned funding

		(US$ million)								2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				69,911		80,835		91,758		11,245

		Non-LVCs		total				359,319		370,243		381,166		95,248

		LVCs		approved						6,132				2,727

		LVCs		planned				7,217		8,345		9,472		0.741

		LVCs		total				13,349		14,477		15,604		3,468

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						376,338		388,389		400,440		98,716

		12,051

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,238				91,046

		Non-LVCs		planned				53,370		61,710		70,049		7,858

		Non-LVCs		total				349,608		357,948		366,287		98,904

		LVCs		approved						6,132				3,209

		LVCs		planned				7,054		8,157		9,258		0.540

		LVCs		total				13,186		14,289		15,390		3,749

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						366,465		375,906		385,347		102,653

		9,441

		Status after ExCom July 2017 - only for proj <35% set of actvts (US$ million)																				Status after ExcCom July 2017

																						Only for Plans with <35% reduction, sets of activities (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min				max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				23,703		27,407		31,110		6,235								Non-LVCs		planned				23,703		27,407		31,110

		Non-LVCs		total				319,941		323,645		327,348		97,281								Non-LVCs		total				319,941		323,645		327,348

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				7,054		7,922		0		0.203								LVCs		planned				7,054		7,922		8,992

		LVCs		total				13,186		14,054		0		3,412								LVCs		total				13,186		14,054		15,124

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		341,368		0		100,693								Total (range)						336,594		341,368		346,142

																						4,774

		Status after ExCom July 2017 - only proj <35% done until 35% (US$ million)																				Status after ExCom July 2017

																						Only for Plans with <35% reduction, activities up to 35% (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min		avrg		max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				16,249		18,788		21,327		6,235								Non-LVCs		planned				16,249		18,788		21,327

		Non-LVCs		total				312,487		315,026		317,565		97,281								Non-LVCs		total				312,487		315,026		317,565

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				0.051		0.164		0.277		0.203								LVCs		planned				0.051		0.164		0.277

		LVCs		total				6,183		6,296		0		3,412								LVCs		total				6,183		6,296		6,409

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		324,992		0		100,693								Total (range)						322,340		324,992		327,644

																						2,652





Sheet1

		OLD												Analysis of the approved projects versus the projects in the business planning gives a variety of percentages per year.

														There are percentages per year from 2016 to 2002. The integrated 2002-16 value is 83.25%, i.e., approvals are 83.25% lower than planned.

														One can also look at the uncertainty in this value (STDV), and that is 11.25%, this implies that the uncertainty in the planned activities is 72%-94.5%.

		Status June 2017																Status June 2017																SUMMARY																				Status May 2017 (US$ million)

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				289408170				84003454						Non-LVCs		approved				289,408				84,003						a		391.77-420.90																		Non-LVCs

		Non-LVCs		planned				97098689				13506804						Non-LVCs		planned				69,911		91,758		9,725		12,764				b		378.84-401.08																		Non-LVCs

		Non-LVCs		total				386506859				97510294						Non-LVCs		total				359,319		381,166								c		343.46-353.42																		Non-LVCs

																																		d		325.56-332.34

		LVCs		approved				6132231				2727688						LVCs		approved				6,132				2,728																										LVCs

		LVCs		planned				10023178				889657						LVCs		planned				7,217		9,472		0.641		0.841				aa		376.34-400.44																		LVCs

		LVCs		total				16155409				3617345						LVCs		total				13,349		15,604								bb		366.46-385.35																		LVCs

																																		cc		356.59-346.14

		Extra amount countries						1903507										Extra amount countries						1,904										dd		322.34-327.64																		Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766										bbb		373.72-394.88																		HPMP verification

																																		ccc		343.16-354.45

		Total						406,331,575										Total (average)						388,389																														Total

		Uncertainty						14564803										Uncertainty (+/-)						12,051																														Uncertainty (+/-)

		Range						391.77-420.90										Range						376,338		400,440																												Range

		b																bb																		bbb																		b

		Status after ExCom July 2017																Status after ExCom July 2017																		Status after ExCom July 2017																		Status after ExCom July 2017

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046								Non-LVCs

		Non-LVCs		planned				74125647				9439215						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs

		Non-LVCs		total				370364581				100485322						Non-LVCs		total				349,608		366,287										Non-LVCs		total				349,608		366,287										Non-LVCs

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209								LVCs

		LVCs		planned				9797194				648919						LVCs		planned				7,054		9,258		0.467		0.613						LVCs		planned				7,054		9,258		0.467		0.613						LVCs

		LVCs		total				15929425				3617345						LVCs		total				13,186		15,390										LVCs		total				13,186		15,390										LVCs

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904												Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766												HPMP verification

																																				PLANNED 2017 ONES ARE ADDED						7,263		9,533

		Total						389,963,313										Total						375,906												Total						384,304												Total

		Uncertainty						11118847										Uncertainty						9,441												Uncertainty						10,576												Uncertainty

		Range						378.84-401.08										Range						366,464		385,347										Range						373,728		394,888										Range

		c																cc																		ccc

		Status after ExCom July 2017 - only proj< 35% filled up - prgm																Status after ExCom July 2017 - only proj< 35% filled up - prgm																		Status after ExCom July 2017 - only proj< 35% filled up - prgm

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				32920585				7489407						Non-LVCs		planned				23,703		31,110		5,392		7,077						Non-LVCs		planned				23,703		31,110		5,392		7,077

		Non-LVCs		total				329159519				98535514						Non-LVCs		total				319,941		327,348										Non-LVCs		total				319,941		327,348

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209

		LVCs		planned				9514894				243500						LVCs		planned				6,851		8,992		0.175		0.230						LVCs		planned				6,851		8,992		0.175		0.230

		LVCs		total				15647125				3617345						LVCs		total				12,983		15,124										LVCs		total				12,983		15,124

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766

								348475951																												PLANNED 2017 ONES ARE ADDED						5,567		7,307

		Total						348,475,951										Total						341,368												Total						348,805

		Uncertainty						4938088										Uncertainty						4,774												Uncertainty						5,644

		Range						343.46-353.42										Range						336,594		346,142										Range						343,161		354,449

		d																dd

		Status after ExCom July 2017 - only proj< 35% done until 35%																Status after ExCom July 2017 - only proj< 35% done until 35%

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				22568707				0						Non-LVCs		planned				16,249		21,327		0

		Non-LVCs		total				318807641				91046107						Non-LVCs		total				312,487		317,565		91,046

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209

		LVCs		planned				1001751				0						LVCs		planned				0.721		0.947		0

		LVCs		total				7133982				3209188						LVCs		total				6,853		7,079		3,209

		Extra amount countries						1239169										Extra amount countries						1,234

		HPMP verification						1765800										HPMP verification						1,766

								328946592

		Total						328,946,592										Total						324,992

		Uncertainty						3385306										Uncertainty						2,652

		Range						325.56-332.34										Range						322,340		327,644






_1568975171.xls
TablesforHPMPfunding

		Status May 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				82,534		97,099		111,664		13,507

		Non-LVCs		total				371,942		386,507		401,072		97,510

		LVCs		approved						6,132				2,727

		LVCs		planned						10,023				0.890

		LVCs		total						16,155				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						391,767		406,332		420,897		101,127

		14,565

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,239				91,046

		Non-LVCs		planned				63,007		74,126		85,245		9,439

		Non-LVCs		total				359,246		370,365		381,484		100,485

		LVCs		approved						6,132				3,209

		LVCs		planned						9,797				0.649

		LVCs		total						15,929				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						378,845		389,964		401,083		101,127

		11,119

		May 2017 with difference approach for planned funding

		(US$ million)								2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				69,911		80,835		91,758		11,245

		Non-LVCs		total				359,319		370,243		381,166		95,248

		LVCs		approved						6,132				2,727

		LVCs		planned				7,217		8,345		9,472		0.741

		LVCs		total				13,349		14,477		15,604		3,468

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						376,338		388,389		400,440		98,716

		12,051

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,238				91,046

		Non-LVCs		planned				53,370		61,710		70,049		7,858

		Non-LVCs		total				349,608		357,948		366,287		98,904

		LVCs		approved						6,132				3,209

		LVCs		planned				7,054		8,157		9,258		0.540

		LVCs		total				13,186		14,289		15,390		3,749

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						366,465		375,906		385,347		102,653

		9,441

		Status after ExCom July 2017 - only for proj <35% set of actvts (US$ million)																				Status after ExcCom July 2017

																						Only for Plans with <35% reduction, sets of activities (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min				max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				23,703		27,407		31,110		6,235								Non-LVCs		planned				23,703		27,407		31,110

		Non-LVCs		total				319,941		323,645		327,348		97,281								Non-LVCs		total				319,941		323,645		327,348

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				7,054		7,922		0		0.203								LVCs		planned				7,054		7,922		8,992

		LVCs		total				13,186		14,054		0		3,412								LVCs		total				13,186		14,054		15,124

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		341,368		0		100,693								Total (range)						336,594		341,368		346,142

																						4,774

		Status after ExCom July 2017 - only proj <35% done until 35% (US$ million)																				Status after ExCom July 2017

																						Only for Plans with <35% reduction, activities up to 35% (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min		avrg		max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				16,249		18,788		21,327		6,235								Non-LVCs		planned				16,249		18,788		21,327

		Non-LVCs		total				312,487		315,026		317,565		97,281								Non-LVCs		total				312,487		315,026		317,565

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				0.051		0.164		0.277		0.203								LVCs		planned				0.051		0.164		0.277

		LVCs		total				6,183		6,296		0		3,412								LVCs		total				6,183		6,296		6,409

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		324,992		0		100,693								Total (range)						322,340		324,992		327,644

																						2,652





Sheet1

		OLD												Analysis of the approved projects versus the projects in the business planning gives a variety of percentages per year.

														There are percentages per year from 2016 to 2002. The integrated 2002-16 value is 83.25%, i.e., approvals are 83.25% lower than planned.

														One can also look at the uncertainty in this value (STDV), and that is 11.25%, this implies that the uncertainty in the planned activities is 72%-94.5%.

		Status June 2017																Status June 2017																SUMMARY																				Status May 2017 (US$ million)

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				289408170				84003454						Non-LVCs		approved				289,408				84,003						a		391.77-420.90																		Non-LVCs

		Non-LVCs		planned				97098689				13506804						Non-LVCs		planned				69,911		91,758		9,725		12,764				b		378.84-401.08																		Non-LVCs

		Non-LVCs		total				386506859				97510294						Non-LVCs		total				359,319		381,166								c		343.46-353.42																		Non-LVCs

																																		d		325.56-332.34

		LVCs		approved				6132231				2727688						LVCs		approved				6,132				2,728																										LVCs

		LVCs		planned				10023178				889657						LVCs		planned				7,217		9,472		0.641		0.841				aa		376.34-400.44																		LVCs

		LVCs		total				16155409				3617345						LVCs		total				13,349		15,604								bb		366.46-385.35																		LVCs

																																		cc		356.59-346.14

		Extra amount countries						1903507										Extra amount countries						1,904										dd		322.34-327.64																		Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766										bbb		373.72-394.88																		HPMP verification

																																		ccc		343.16-354.45

		Total						406,331,575										Total (average)						388,389																														Total

		Uncertainty						14564803										Uncertainty (+/-)						12,051																														Uncertainty (+/-)

		Range						391.77-420.90										Range						376,338		400,440																												Range

		b																bb																		bbb																		b

		Status after ExCom July 2017																Status after ExCom July 2017																		Status after ExCom July 2017																		Status after ExCom July 2017

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046								Non-LVCs

		Non-LVCs		planned				74125647				9439215						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs

		Non-LVCs		total				370364581				100485322						Non-LVCs		total				349,608		366,287										Non-LVCs		total				349,608		366,287										Non-LVCs

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209								LVCs

		LVCs		planned				9797194				648919						LVCs		planned				7,054		9,258		0.467		0.613						LVCs		planned				7,054		9,258		0.467		0.613						LVCs

		LVCs		total				15929425				3617345						LVCs		total				13,186		15,390										LVCs		total				13,186		15,390										LVCs

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904												Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766												HPMP verification

																																				PLANNED 2017 ONES ARE ADDED						7,263		9,533

		Total						389,963,313										Total						375,906												Total						384,304												Total

		Uncertainty						11118847										Uncertainty						9,441												Uncertainty						10,576												Uncertainty

		Range						378.84-401.08										Range						366,464		385,347										Range						373,728		394,888										Range

		c																cc																		ccc

		Status after ExCom July 2017 - only proj< 35% filled up - prgm																Status after ExCom July 2017 - only proj< 35% filled up - prgm																		Status after ExCom July 2017 - only proj< 35% filled up - prgm

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				32920585				7489407						Non-LVCs		planned				23,703		31,110		5,392		7,077						Non-LVCs		planned				23,703		31,110		5,392		7,077

		Non-LVCs		total				329159519				98535514						Non-LVCs		total				319,941		327,348										Non-LVCs		total				319,941		327,348

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209

		LVCs		planned				9514894				243500						LVCs		planned				6,851		8,992		0.175		0.230						LVCs		planned				6,851		8,992		0.175		0.230

		LVCs		total				15647125				3617345						LVCs		total				12,983		15,124										LVCs		total				12,983		15,124

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766

								348475951																												PLANNED 2017 ONES ARE ADDED						5,567		7,307

		Total						348,475,951										Total						341,368												Total						348,805

		Uncertainty						4938088										Uncertainty						4,774												Uncertainty						5,644

		Range						343.46-353.42										Range						336,594		346,142										Range						343,161		354,449

		d																dd

		Status after ExCom July 2017 - only proj< 35% done until 35%																Status after ExCom July 2017 - only proj< 35% done until 35%

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				22568707				0						Non-LVCs		planned				16,249		21,327		0

		Non-LVCs		total				318807641				91046107						Non-LVCs		total				312,487		317,565		91,046

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209

		LVCs		planned				1001751				0						LVCs		planned				0.721		0.947		0

		LVCs		total				7133982				3209188						LVCs		total				6,853		7,079		3,209

		Extra amount countries						1239169										Extra amount countries						1,234

		HPMP verification						1765800										HPMP verification						1,766

								328946592

		Total						328,946,592										Total						324,992

		Uncertainty						3385306										Uncertainty						2,652

		Range						325.56-332.34										Range						322,340		327,644






_1568974736.xls
TablesforHPMPfunding

		Status May 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				82,534		97,099		111,664		13,507

		Non-LVCs		total				371,942		386,507		401,072		97,510

		LVCs		approved						6,132				2,727

		LVCs		planned						10,023				0.890

		LVCs		total						16,155				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						391,767		406,332		420,897		101,127

		14,565

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,239				91,046

		Non-LVCs		planned				63,007		74,126		85,245		9,439

		Non-LVCs		total				359,246		370,365		381,484		100,485

		LVCs		approved						6,132				3,209

		LVCs		planned						9,797				0.649

		LVCs		total						15,929				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						378,845		389,964		401,083		101,127

		11,119

		May 2017 with difference approach for planned funding

		(US$ million)								2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				69,911		80,835		91,758		11,245

		Non-LVCs		total				359,319		370,243		381,166		95,248

		LVCs		approved						6,132				2,727

		LVCs		planned				7,217		8,345		9,472		0.741

		LVCs		total				13,349		14,477		15,604		3,468

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						376,338		388,389		400,440		98,716

		12,051

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,238				91,046

		Non-LVCs		planned				53,370		61,710		70,049		7,858

		Non-LVCs		total				349,608		357,948		366,287		98,904

		LVCs		approved						6,132				3,209

		LVCs		planned				7,054		8,157		9,258		0.540

		LVCs		total				13,186		14,289		15,390		3,749

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						366,465		375,906		385,347		102,653

		9,441

		Status after ExCom July 2017 - only for proj <35% set of actvts (US$ million)																				Status after ExcCom July 2017

																						Only for Plans with <35% reduction, sets of activities (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min				max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				23,703		27,407		31,110		6,235								Non-LVCs		planned				23,703		27,407		31,110

		Non-LVCs		total				319,941		323,645		327,348		97,281								Non-LVCs		total				319,941		323,645		327,348

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				7,054		7,922		0		0.203								LVCs		planned				7,054		7,922		8,992

		LVCs		total				13,186		14,054		0		3,412								LVCs		total				13,186		14,054		15,124

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		341,368		0		100,693								Total (range)						336,594		341,368		346,142

																						4,774

		Status after ExCom July 2017 - only proj <35% done until 35% (US$ million)																				Status after ExCom July 2017

																						Only for Plans with <35% reduction, activities up to 35% (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min		avrg		max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				16,249		18,788		21,327		6,235								Non-LVCs		planned				16,249		18,788		21,327

		Non-LVCs		total				312,487		315,026		317,565		97,281								Non-LVCs		total				312,487		315,026		317,565

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				0.051		0.164		0.277		0.203								LVCs		planned				0.051		0.164		0.277

		LVCs		total				6,183		6,296		0		3,412								LVCs		total				6,183		6,296		6,409

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		324,992		0		100,693								Total (range)						322,340		324,992		327,644

																						2,652





Sheet1

		OLD												Analysis of the approved projects versus the projects in the business planning gives a variety of percentages per year.

														There are percentages per year from 2016 to 2002. The integrated 2002-16 value is 83.25%, i.e., approvals are 83.25% lower than planned.

														One can also look at the uncertainty in this value (STDV), and that is 11.25%, this implies that the uncertainty in the planned activities is 72%-94.5%.

		Status June 2017																Status June 2017																SUMMARY																				Status May 2017 (US$ million)

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				289408170				84003454						Non-LVCs		approved				289,408				84,003						a		391.77-420.90																		Non-LVCs

		Non-LVCs		planned				97098689				13506804						Non-LVCs		planned				69,911		91,758		9,725		12,764				b		378.84-401.08																		Non-LVCs

		Non-LVCs		total				386506859				97510294						Non-LVCs		total				359,319		381,166								c		343.46-353.42																		Non-LVCs

																																		d		325.56-332.34

		LVCs		approved				6132231				2727688						LVCs		approved				6,132				2,728																										LVCs

		LVCs		planned				10023178				889657						LVCs		planned				7,217		9,472		0.641		0.841				aa		376.34-400.44																		LVCs

		LVCs		total				16155409				3617345						LVCs		total				13,349		15,604								bb		366.46-385.35																		LVCs

																																		cc		356.59-346.14

		Extra amount countries						1903507										Extra amount countries						1,904										dd		322.34-327.64																		Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766										bbb		373.72-394.88																		HPMP verification

																																		ccc		343.16-354.45

		Total						406,331,575										Total (average)						388,389																														Total

		Uncertainty						14564803										Uncertainty (+/-)						12,051																														Uncertainty (+/-)

		Range						391.77-420.90										Range						376,338		400,440																												Range

		b																bb																		bbb																		b

		Status after ExCom July 2017																Status after ExCom July 2017																		Status after ExCom July 2017																		Status after ExCom July 2017

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046								Non-LVCs

		Non-LVCs		planned				74125647				9439215						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs

		Non-LVCs		total				370364581				100485322						Non-LVCs		total				349,608		366,287										Non-LVCs		total				349,608		366,287										Non-LVCs

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209								LVCs

		LVCs		planned				9797194				648919						LVCs		planned				7,054		9,258		0.467		0.613						LVCs		planned				7,054		9,258		0.467		0.613						LVCs

		LVCs		total				15929425				3617345						LVCs		total				13,186		15,390										LVCs		total				13,186		15,390										LVCs

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904												Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766												HPMP verification

																																				PLANNED 2017 ONES ARE ADDED						7,263		9,533

		Total						389,963,313										Total						375,906												Total						384,304												Total

		Uncertainty						11118847										Uncertainty						9,441												Uncertainty						10,576												Uncertainty

		Range						378.84-401.08										Range						366,464		385,347										Range						373,728		394,888										Range

		c																cc																		ccc

		Status after ExCom July 2017 - only proj< 35% filled up - prgm																Status after ExCom July 2017 - only proj< 35% filled up - prgm																		Status after ExCom July 2017 - only proj< 35% filled up - prgm

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				32920585				7489407						Non-LVCs		planned				23,703		31,110		5,392		7,077						Non-LVCs		planned				23,703		31,110		5,392		7,077

		Non-LVCs		total				329159519				98535514						Non-LVCs		total				319,941		327,348										Non-LVCs		total				319,941		327,348

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209

		LVCs		planned				9514894				243500						LVCs		planned				6,851		8,992		0.175		0.230						LVCs		planned				6,851		8,992		0.175		0.230

		LVCs		total				15647125				3617345						LVCs		total				12,983		15,124										LVCs		total				12,983		15,124

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766

								348475951																												PLANNED 2017 ONES ARE ADDED						5,567		7,307

		Total						348,475,951										Total						341,368												Total						348,805

		Uncertainty						4938088										Uncertainty						4,774												Uncertainty						5,644

		Range						343.46-353.42										Range						336,594		346,142										Range						343,161		354,449

		d																dd

		Status after ExCom July 2017 - only proj< 35% done until 35%																Status after ExCom July 2017 - only proj< 35% done until 35%

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				22568707				0						Non-LVCs		planned				16,249		21,327		0

		Non-LVCs		total				318807641				91046107						Non-LVCs		total				312,487		317,565		91,046

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209

		LVCs		planned				1001751				0						LVCs		planned				0.721		0.947		0

		LVCs		total				7133982				3209188						LVCs		total				6,853		7,079		3,209

		Extra amount countries						1239169										Extra amount countries						1,234

		HPMP verification						1765800										HPMP verification						1,766

								328946592

		Total						328,946,592										Total						324,992

		Uncertainty						3385306										Uncertainty						2,652

		Range						325.56-332.34										Range						322,340		327,644






_1568974865.xls
TablesforHPMPfunding

		Status May 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				82,534		97,099		111,664		13,507

		Non-LVCs		total				371,942		386,507		401,072		97,510

		LVCs		approved						6,132				2,727

		LVCs		planned						10,023				0.890

		LVCs		total						16,155				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						391,767		406,332		420,897		101,127

		14,565

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,239				91,046

		Non-LVCs		planned				63,007		74,126		85,245		9,439

		Non-LVCs		total				359,246		370,365		381,484		100,485

		LVCs		approved						6,132				3,209

		LVCs		planned						9,797				0.649

		LVCs		total						15,929				3,617

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						378,845		389,964		401,083		101,127

		11,119

		May 2017 with difference approach for planned funding

		(US$ million)								2018-20				2017

								min				max

		Non-LVCs		approved						289,408				84,003

		Non-LVCs		planned				69,911		80,835		91,758		11,245

		Non-LVCs		total				359,319		370,243		381,166		95,248

		LVCs		approved						6,132				2,727

		LVCs		planned				7,217		8,345		9,472		0.741

		LVCs		total				13,349		14,477		15,604		3,468

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						376,338		388,389		400,440		98,716

		12,051

		Status after ExCom July 2017 (US$ million)

										2018-20				2017

								min				max

		Non-LVCs		approved						296,238				91,046

		Non-LVCs		planned				53,370		61,710		70,049		7,858

		Non-LVCs		total				349,608		357,948		366,287		98,904

		LVCs		approved						6,132				3,209

		LVCs		planned				7,054		8,157		9,258		0.540

		LVCs		total				13,186		14,289		15,390		3,749

		Extra amount countries								1,904

		HPMP verification								1,766

		Total (range)						366,465		375,906		385,347		102,653

		9,441

		Status after ExCom July 2017 - only for proj <35% set of actvts (US$ million)																				Status after ExcCom July 2017

																						Only for Plans with <35% reduction, sets of activities (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min				max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				23,703		27,407		31,110		6,235								Non-LVCs		planned				23,703		27,407		31,110

		Non-LVCs		total				319,941		323,645		327,348		97,281								Non-LVCs		total				319,941		323,645		327,348

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				7,054		7,922		0		0.203								LVCs		planned				7,054		7,922		8,992

		LVCs		total				13,186		14,054		0		3,412								LVCs		total				13,186		14,054		15,124

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		341,368		0		100,693								Total (range)						336,594		341,368		346,142

																						4,774

		Status after ExCom July 2017 - only proj <35% done until 35% (US$ million)																				Status after ExCom July 2017

																						Only for Plans with <35% reduction, activities up to 35% (US$ million)

										2018-20																				2018-20

								min		avrg		max		avrg														min		avrg		max

		Non-LVCs		approved						296,238				91,046								Non-LVCs		approved						296,238

		Non-LVCs		planned				16,249		18,788		21,327		6,235								Non-LVCs		planned				16,249		18,788		21,327

		Non-LVCs		total				312,487		315,026		317,565		97,281								Non-LVCs		total				312,487		315,026		317,565

		LVCs		approved						6,132				3,209								LVCs		approved						6,132

		LVCs		planned				0.051		0.164		0.277		0.203								LVCs		planned				0.051		0.164		0.277

		LVCs		total				6,183		6,296		0		3,412								LVCs		total				6,183		6,296		6,409

		Extra amount countries								1,904												Extra amount countries								1,904

		HPMP verification								1,766												HPMP verification								1,766

		Total (range)						0		324,992		0		100,693								Total (range)						322,340		324,992		327,644

																						2,652





Sheet1

		OLD												Analysis of the approved projects versus the projects in the business planning gives a variety of percentages per year.

														There are percentages per year from 2016 to 2002. The integrated 2002-16 value is 83.25%, i.e., approvals are 83.25% lower than planned.

														One can also look at the uncertainty in this value (STDV), and that is 11.25%, this implies that the uncertainty in the planned activities is 72%-94.5%.

		Status June 2017																Status June 2017																SUMMARY																				Status May 2017 (US$ million)

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				289408170				84003454						Non-LVCs		approved				289,408				84,003						a		391.77-420.90																		Non-LVCs

		Non-LVCs		planned				97098689				13506804						Non-LVCs		planned				69,911		91,758		9,725		12,764				b		378.84-401.08																		Non-LVCs

		Non-LVCs		total				386506859				97510294						Non-LVCs		total				359,319		381,166								c		343.46-353.42																		Non-LVCs

																																		d		325.56-332.34

		LVCs		approved				6132231				2727688						LVCs		approved				6,132				2,728																										LVCs

		LVCs		planned				10023178				889657						LVCs		planned				7,217		9,472		0.641		0.841				aa		376.34-400.44																		LVCs

		LVCs		total				16155409				3617345						LVCs		total				13,349		15,604								bb		366.46-385.35																		LVCs

																																		cc		356.59-346.14

		Extra amount countries						1903507										Extra amount countries						1,904										dd		322.34-327.64																		Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766										bbb		373.72-394.88																		HPMP verification

																																		ccc		343.16-354.45

		Total						406,331,575										Total (average)						388,389																														Total

		Uncertainty						14564803										Uncertainty (+/-)						12,051																														Uncertainty (+/-)

		Range						391.77-420.90										Range						376,338		400,440																												Range

		b																bb																		bbb																		b

		Status after ExCom July 2017																Status after ExCom July 2017																		Status after ExCom July 2017																		Status after ExCom July 2017

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046								Non-LVCs

		Non-LVCs		planned				74125647				9439215						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs		planned				53,370		70,049		6,796		8,920						Non-LVCs

		Non-LVCs		total				370364581				100485322						Non-LVCs		total				349,608		366,287										Non-LVCs		total				349,608		366,287										Non-LVCs

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209								LVCs

		LVCs		planned				9797194				648919						LVCs		planned				7,054		9,258		0.467		0.613						LVCs		planned				7,054		9,258		0.467		0.613						LVCs

		LVCs		total				15929425				3617345						LVCs		total				13,186		15,390										LVCs		total				13,186		15,390										LVCs

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904												Extra amount countries

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766												HPMP verification

																																				PLANNED 2017 ONES ARE ADDED						7,263		9,533

		Total						389,963,313										Total						375,906												Total						384,304												Total

		Uncertainty						11118847										Uncertainty						9,441												Uncertainty						10,576												Uncertainty

		Range						378.84-401.08										Range						366,464		385,347										Range						373,728		394,888										Range

		c																cc																		ccc

		Status after ExCom July 2017 - only proj< 35% filled up - prgm																Status after ExCom July 2017 - only proj< 35% filled up - prgm																		Status after ExCom July 2017 - only proj< 35% filled up - prgm

								2018-20				2017												2018-20				2017														2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046								Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				32920585				7489407						Non-LVCs		planned				23,703		31,110		5,392		7,077						Non-LVCs		planned				23,703		31,110		5,392		7,077

		Non-LVCs		total				329159519				98535514						Non-LVCs		total				319,941		327,348										Non-LVCs		total				319,941		327,348

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209								LVCs		approved				6,132				3,209

		LVCs		planned				9514894				243500						LVCs		planned				6,851		8,992		0.175		0.230						LVCs		planned				6,851		8,992		0.175		0.230

		LVCs		total				15647125				3617345						LVCs		total				12,983		15,124										LVCs		total				12,983		15,124

		Extra amount countries						1903507										Extra amount countries						1,904												Extra amount countries						1,904

		HPMP verification						1765800										HPMP verification						1,766												HPMP verification						1,766

								348475951																												PLANNED 2017 ONES ARE ADDED						5,567		7,307

		Total						348,475,951										Total						341,368												Total						348,805

		Uncertainty						4938088										Uncertainty						4,774												Uncertainty						5,644

		Range						343.46-353.42										Range						336,594		346,142										Range						343,161		354,449

		d																dd

		Status after ExCom July 2017 - only proj< 35% done until 35%																Status after ExCom July 2017 - only proj< 35% done until 35%

								2018-20				2017												2018-20				2017

		Non-LVCs		approved				296238934				91046107						Non-LVCs		approved				296,238				91,046

		Non-LVCs		planned				22568707				0						Non-LVCs		planned				16,249		21,327		0

		Non-LVCs		total				318807641				91046107						Non-LVCs		total				312,487		317,565		91,046

		LVCs		approved				6132231				3209188						LVCs		approved				6,132				3,209

		LVCs		planned				1001751				0						LVCs		planned				0.721		0.947		0

		LVCs		total				7133982				3209188						LVCs		total				6,853		7,079		3,209

		Extra amount countries						1239169										Extra amount countries						1,234

		HPMP verification						1765800										HPMP verification						1,766

								328946592

		Total						328,946,592										Total						324,992

		Uncertainty						3385306										Uncertainty						2,652

		Range						325.56-332.34										Range						322,340		327,644






_1567707200.xls
BPvsApprovalsAnalysis

		Year		Business Plan		Approvals		Difference		%approvals		Cumulative		STDEV		Year		Business Plan		Approvals		Difference		%approvals

		2016		175,906,212		134,886,955		41,019,257		77%				0.0039		2015		172,925,384		185,521,702		-12,596,318		107%

		2015		172,925,384		185,521,702		-12,596,318		107%				0.0564		2014		150,349,262		109,636,438		40,712,824		73%

		2014		150,349,262		109,636,438		40,712,824		73%		2014-2016		0.0105		2013		163,058,422		143,350,645		19,707,777		88%

		2014-2016		499,180,858		430,045,095		69,135,763		86.15%		86.15%		0.0008		2013-2015		486,333,068		438,508,785		47,824,283		90%		0.901663518

		2013		163,058,422		143,350,645		19,707,777		88%				0.0023		2012		158,193,207		118,099,916		40,093,291		75%

		2012		158,193,207		118,099,916		40,093,291		75%				0.0068		2011		251,685,220		227,553,662		24,131,558		90%

		2011		251,685,220		227,553,662		24,131,558		90%		2011-2016		0.0046		2010		205,296,416		103,360,124		101,936,292		50%

		2011-2013		572,936,849		489,004,223		83,932,626		85.35%		85.72%		0.0003		2010-2012		615,174,843		449,013,702		166,161,141		73%		0.8057341015

		2010		205,296,416		103,360,124		101,936,292		50%				0.1105		2009		106,014,427		87,689,407		18,325,020		83%

		2009		106,014,427		87,689,407		18,325,020		83%				0.0000		2008		145,296,562		142,226,527		3,070,035		98%

		2008		145,296,562		142,226,527		3,070,035		98%		2008-2016		0.0218		2007		171,419,512		135,794,742		35,624,770		79%

		2008-2010		456,607,405		333,276,058		123,331,347		72.99%		81.92%		0.0105		2007-2009		422,730,501		365,710,676		57,019,825		87%		0.8222028478

		2007		171,419,512		135,794,742		35,624,770		79%				0.0018		2006		161,412,541		136,961,591		24,450,950		85%

		2006		161,412,541		136,961,591		24,450,950		85%				0.0003		2005		226,796,158		213,353,085		13,443,073		94%

		2005		226,796,158		213,353,085		13,443,073		94%		2005-2016		0.0116		2004		221,409,010		186,227,602		35,181,408		84%

		2005-2007		559,628,211		486,109,418		73,518,793		86.86%		82.33%		0.0014		2004-2006		609,617,709		536,542,278		73,075,431		88%		0.8201807274

		2004		221,409,010		186,227,602		35,181,408		84%				0.0001		2003		226,732,762		173,814,977		52,917,785		77%

		2003		226,732,762		173,814,977		52,917,785		77%				0.0039		2002		195,635,529		185,628,199		10,007,330		95%

		2002		195,635,529		185,628,199		10,007,330		95%		2002-2016		0.0138		2001		166,859,265		144,052,417		22,806,848		86%

		2002-2004		643,777,301		545,670,778		98,106,523		84.76%		83.24%		0.0003		2001-2003		589,227,556		503,495,593		85,731,963		85%		0.832442851

		2001		166,859,265		144,052,417		22,806,848		86%				0.0008		2000		131,542,713		125,740,663		5,802,050		96%

		2000		131,542,713		125,740,663		5,802,050		96%				0.0163

														0.0127

														0.1125

														11.25%





BPvsApprovals

		Year		Business Plan		Approvals		Difference		%approvals

		2016		175,906,212		134,886,955		41,019,257		77%

		2015		172,925,384		185,521,702		-12,596,318		107%

		2014		150,349,262		109,636,438		40,712,824		73%

		2013		163,058,422		143,350,645		19,707,777		88%

		2012		158,193,207		118,099,916		40,093,291		75%

		2011		251,685,220		227,553,662		24,131,558		90%

		2010		205,296,416		103,360,124		101,936,292		50%

		2009		106,014,427		87,689,407		18,325,020		83%

		2008		145,296,562		142,226,527		3,070,035		98%

		2007		171,419,512		135,794,742		35,624,770		79%

		2006		161,412,541		136,961,591		24,450,950		85%

		2005		226,796,158		213,353,085		13,443,073		94%

		2004		221,409,010		186,227,602		35,181,408		84%

		2003		226,732,762		173,814,977		52,917,785		77%

		2002		195,635,529		185,628,199		10,007,330		95%

		2001		166,859,265		144,052,417		22,806,848		86%

		2000		131,542,713		125,740,663		5,802,050		96%





Approval

		Year		Meeting		Funds Approved including Support Costs

		2016		77		104,726,939

		2016		76		30,160,016		134,886,955

		2015		75		126,121,207

		2015		74		59,400,495		185,521,702

		2014		73		68,784,379

		2014		72		40,852,059		109,636,438

		2013		71		95,333,593

		2013		70		7,857,212

		2013		69		40,159,840		143,350,645

		2012		68		74,447,698

		2012		67		10,574,357

		2012		66		33,077,861		118,099,916

		2011		65		38,790,483

		2011		64		166,021,012

		2011		63		22,742,167		227,553,662

		2010		62		46,914,661

		2010		61		22,966,668

		2010		60		33,478,795		103,360,124

		2009		59		40,819,478

		2009		58		19,350,768

		2009		57		27,519,161		87,689,407

		2008		56		67,303,847

		2008		55		39,156,073

		2008		54		35,766,607		142,226,527

		2007		53		45,176,282

		2007		52		36,077,737

		2007		51		54,540,723		135,794,742

		2006		50		47,903,970

		2006		49		21,114,112

		2006		48		67,943,509		136,961,591

		2005		47		122,936,898

		2005		46		23,687,965

		2005		45		66,728,222		213,353,085

		2004		44		75,405,907

		2004		43		31,268,226

		2004		42		79,553,469		186,227,602

		2003		41		96,402,466

		2003		40		25,266,370

		2003		39		52,146,141		173,814,977

		2002		38		87,030,559

		2002		37		44,841,524

		2002		36		53,756,116		185,628,199

		2001		35		58,674,811

		2001		34		55,892,032

		2001		33		29,485,574		144,052,417

		2000		32		50,993,256

		2000		31		40,503,684

		2000		30		34,243,723		125,740,663






_1567707514.xls
Sheet1

		A		B		C		D		E		F		G		H		I		J		K		L		M		N		O		P						Q		R		S		T

						ODP tonnes approved all (I and II - ExC 77)								Funding planned for HPMP II (all planned)										ODP tonnes BP plan (HPMP II planned)																Total		1/1/21

		Country		Chem		Total		Appr		Perc app		ODP-t		2017		2018		2019		2020				Country		2017		2018		2019		2020						App 17-20		App total		Perc appr		ODP-t

		Madagascar		HCFC-22		17.10		6.00		35.09		6.00		0		0		0		193,135				Madagascar								2.45						2.45		8.45		49.42		8.45

		Mexico		HCFC-123		30.20		10.57		35.00														Mexico														0		10.57		35.00

		Mexico		HCFC-22		392.80		130.30		33.17								``						Mexico														0		130.3		33.17

		Mexico		HCFC-124		0.10		0.00		0.00														Mexico														0		0		- 0

		Mexico		HCFC-142b		1.00		0.00		0.00														Mexico														0		0		- 0

		Mexico		HCFC-141b		820.60		820.60		100.00														Mexico														0		820.6		100.00

						1,244.70		961.47		77.25		961.47														0.00		0.00		0.00		0.00						0		961.47		77.25		961.47

		Nigeria		HCFC-141b		149.60		79.50		53.14														Nigeria		31.63		8.43		11.58		8.43						60.07		139.57		93.30

		Nigeria		HCFC-22		248.50		10.60		4.27				3,313,296		1,238,942		3,099,296		1,199,494				Nigeria		17.1		7.1		17.1		6.7						48		58.6		23.58

						398.10		79.50		19.97		79.50														48.73		15.53		28.68		15.13								198.17		49.78		198.17

		Pakistan		HCFC-141b		138.50		130.39		94.14														Pakistan														0		130.39		94.14

		Pakistan		HCFC-22		108.90		21.69		19.92														Pakistan														0		21.69		19.92

						247.40		152.08		61.47		152.08																												152.08		61.47		152.08

		Qatar		HCFC-142b		12.05		12.05		100.00														Qatar														0		12.05		100.00

		Qatar		HCFC-22		73.45		45.81		62.37														Qatar				5		5		1.8						11.8		57.61		78.43

		Qatar		HCFC-141b		0.57		0.00		0.00				0		477,381		477,381		168,087				Qatar														0		0		- 0

						86.07		57.86		67.22		57.86														0.00		5.00		5.00		1.80						11.8		69.66		80.93		69.66

														0		0		0		569,311

		Senegal		HCFC-22		20.96		7.34		35.02		7.34												Senegal								5.98						5.98		13.32		63.55		13.32





Sheet2

		






_1567707007.xls
NonLVC

		Cost effectiveness non-LVCs

		ARGENTINA

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		123-

		Chemical		141b						23.96				0.11		217.8181818182				725		157.9181818182

		Chemical		141b polyol

		Chemical		142b										0.065						2310

		Chemical		22-						59.57				0.055		1083.0909090909				1810		1960.3945454546

				Funding		11597593				83.53						1300.9090909091						2118.3127272727						138.843		8.915		5.475

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		123-

		Chemical		141b				94.57		70.61				0.11		641.9090909091				725		465.3840909091

		Chemical		141b polyol

		Chemical		142b				1.74		1.74				0.065		26.7692307692				2310		61.8369230769

		Chemical		22-				102.41		42.84				0.055		778.9090909091				1810		1409.8254545454

				Funding		10652124				115.19						1447.5874125874						1937.0464685315						92.474		7.359		5.499

		Overall		Funding		22249717		198.72																				116.644		8.170		5.487

		BRAZIL

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b						168.8				0.11		1534.5454545454				725		1112.5454545454

		Chemical		141b polyol

		Chemical		142b

		Chemical		22-						51.5				0.055		936.3636363636				1810		1694.8181818182

				Funding		21027388				220.3						2470.9090909091						2807.3636363636						95.449		8.510		7.490

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				469.7		300.9				0.11		2735.4545454546				725		1983.2045454546

		Chemical		141b polyol

		Chemical		142b

		Chemical		22-				214.66		163.16				0.055		2966.5454545454				1810		5369.4472727273

				Funding		38815539				464.06						5702						7352.6518181818						83.643		6.807		5.279

		Overall		Funding		59842927		684.36																				87.792		7.406		6.056

		INDIA

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b						310.53				0.11		2823				725		2046.675

		Chemical		141b polyol

		Chemical		142b

		Chemical		22-						31.24				0.055		568				1810		1028.08

				Funding		21294490				341.77						3391						3074.755						62.306		6.280		6.926

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				865.5		554.97				0.11		5045.1818181818				725		3657.7568181818

		Chemical		141b polyol				83.05		83.05				0.11		755				725		547.375

		Chemical		142b

		Chemical		22-				162.71		131.47				0.055		2390.3636363636				1810		4326.5581818182

				Funding		48315260				769.49						8190.5454545455						8531.69						62.789		5.899		5.663

		Overall		Funding		69609750		1111.26																				72.865		6.997		7.037

		EGYPT

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				95.69		95.69				0.11		869.9090909091				725		630.6840909091

		Chemical		141b polyol				72.18		72.18				0.11		656.1818181818				725		475.7318181818

		Chemical		142b										0.065		0				2310		0

		Chemical		22-						6.13				0.055		111.4545454545				1810		201.7327272727

				Funding		9164414				174						1637.5454545454						1308.1486363636						52.669		5.596		7.006

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				129.61		33.92				0.11		308.3636363636				725		223.5636363636

		Chemical		141b polyol				98.34		26.16				0.11		237.8181818182				725		172.4181818182

		Chemical		142b				16.36		16.36				0.065		251.6923076923				2310		581.4092307692

		Chemical		22-				76.66		70.53				0.055		1282.3636363636				1810		2321.0781818182

				Funding		11786341				146.97						2080.2377622378						3298.4692307692						80.196		5.666		3.573

		Overall		Funding		20950755		320.97																				68.155		5.635		5.075

		MEXICO

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Cemical		123-

		Chemical		141b				392.5		392.5				0.11		3568.1818181818				725		2586.9318181818

		Chemical		141b polyol										0.11		0				725		0

		Chemical		142b										0.065		0				2310		0

		Chemical		22-				24.8		24.8				0.055		450.9090909091				1810		816.1454545455

				Funding		19421177				417.3						4019.0909090909						3403.0772727273						46.540		4.832		5.707

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		123-				10.57		10.57				0.02		528.5				77		40.6945

		Chemical		141b				820.6		428.1				0.11		3891.8181818182				725		2821.5681818182

		Chemical		141b polyol						0				0.11		0				725		0

		Chemical		142b				16.36		16.36				0.065		251.6923076923				2310		581.4092307692

		Chemical		22-				130.3		105.5				0.055		1918.1818181818				1810		3471.9090909091

				Funding		11786341				560.53						6590.1923076923						6915.5810034965						21.027		1.788		1.704

		Overall		Funding		31207518		977.83																				36.904		3.683		4.195

		LEBANON

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				15.1		15.1				0.11		137.2727272727				725		99.5227272727

		Chemical		141b polyol										0.11		0				725		0

		Chemical		142b										0.065		0				2310		0

		Chemical		22-				4.9		4.9				0.055		89.0909090909				1810		161.2545454545

				Funding		2682242				20						226.3636363636						260.7772727273						134.112		11.849		10.286

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				37.53		22.43				0.11		203.9090909091				725		147.8340909091

		Chemical		141b polyol						0				0.11		0				725		0

		Chemical		142b						0				0.065		0				2310		0

		Chemical		22-				23.63		18.73				0.055		340.5454545455				1810		616.3872727273

				Funding		4498093				41.16						544.4545454545						764.2213636364						109.283		8.262		5.886

		Overall		Funding		7180335		61.16																				118.558		9.602		7.529

		PERU

						Phase I		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				1.79		1.79				0.11		16.2727272727				725		11.7977272727

		Chemical		141b polyol										0.11						725

		Chemical		142b										0.065		0				2310		0

		Chemical		22-				1.95		1.95				0.055		35.4545454545				1810		64.1727272727

				Funding		310111				3.74						51.7272727273						75.9704545455						82.917		5.995		4.082

		Overall		Funding		310111		3.74																				82.917		5.995		4.082

		TOGO

						Phase I		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b										0.11		0				725		0

		Chemical		141b polyol										0.11						725

		Chemical		142b										0.065		0				2310		0

		Chemical		22-				7		7				0.055		127.2727272727				1810		230.3636363636

				Funding		692650				7						127.2727272727						230.3636363636						98.950		5.442		3.007

		Overall		Funding		692650		7																				98.950		5.442		3.007

		SAUDI

						Phase I		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				341		341				0.11		3100				725		2247.5

		Chemical		141b polyol										0.11						725

		Chemical		142b				115.86		115.86				0.065		1782.4615384615				2310		4117.4861538462

		Chemical		22-				246.43		246.43				0.055		4480.5454545455				1810		8109.7872727273

				Funding		14421066				703.29						9363.006993007						14474.7734265734						20.505		1.540		0.996

		Overall		Funding		14421066		703.29																				20.505		1.540		0.996

		CHINA

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Cemical		123-

		Cemical		124-

		Cemical		141b				1698.05		1698.05				0.11		15436.8181818182				725		11191.6931818182

		Cemical		141b polyol										0.11		0				725		0

		Cemical		142b				266.95		266.95				0.065		4106.9230769231				2310		9486.9923076923

		Cemical		22-				1480.6		1480.6				0.055		26920				1810		48725.2

		Cemical		225ca-										0.025						122

				Funding		289831680				3445.6						46463.7412587413						69403.8854895105						84.116		6.238		4.176

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		123-				2.7		2.7				0.02		135				77		10.395

		Chemical		124-

		Chemical		141b				5885.18		4187.13				0.11		38064.8181818182				725		27596.9931818182

		Chemical		141b polyol						0				0.11		0				725		0

		Chemical		142b				912.97		646.02				0.065		9938.7692307692				2310		22958.5569230769

		Chemical		22-				5359.4		3878.8				0.055		70523.6363636364				1810		127647.781818182

		Chemical		225ca-				1.22		1.22				0.025		48.8				122		5.9536

				Funding		533883629				8714.65						118662.223776224						178213.726923077						61.263		4.499		2.996

		Overall		Funding		823715309		12161.47																				69.304		5.111		3.411

								ODP total																				CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Total																										weighted		weighted		weighted

		Average						16229.8																				62.123		4.709		3.344





NonLVCNoChina

		Cost effectiveness non-LVCs

		ARGENTINA

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		123-

		Chemical		141b						23.96				0.11		217.8181818182				725		157.9181818182

		Chemical		141b polyol

		Chemical		142b										0.065						2310

		Chemical		22-						59.57				0.055		1083.0909090909				1810		1960.3945454546

				Funding		11597593				83.53						1300.9090909091						2118.3127272727						138.843		8.915		5.475

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		123-

		Chemical		141b				94.57		70.61				0.11		641.9090909091				725		465.3840909091

		Chemical		141b polyol

		Chemical		142b				1.74		1.74				0.065		26.7692307692				2310		61.8369230769

		Chemical		22-				102.41		42.84				0.055		778.9090909091				1810		1409.8254545454

				Funding		10652124				115.19						1447.5874125874						1937.0464685315						92.474		7.359		5.499

		Overall		Funding		22249717		198.72																				116.644		8.170		5.487

		BRAZIL

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b						168.8				0.11		1534.5454545454				725		1112.5454545454

		Chemical		141b polyol

		Chemical		142b

		Chemical		22-						51.5				0.055		936.3636363636				1810		1694.8181818182

				Funding		21027388				220.3						2470.9090909091						2807.3636363636						95.449		8.510		7.490

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				469.7		300.9				0.11		2735.4545454546				725		1983.2045454546

		Chemical		141b polyol

		Chemical		142b

		Chemical		22-				214.66		163.16				0.055		2966.5454545454				1810		5369.4472727273

				Funding		38815539				464.06						5702						7352.6518181818						83.643		6.807		5.279

		Overall		Funding		59842927		684.36																				87.792		7.406		6.056

		INDIA

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b						310.53				0.11		2823				725		2046.675

		Chemical		141b polyol

		Chemical		142b

		Chemical		22-						31.24				0.055		568				1810		1028.08

				Funding		21294490				341.77						3391						3074.755						62.306		6.280		6.926

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				865.5		554.97				0.11		5045.1818181818				725		3657.7568181818

		Chemical		141b polyol				83.05		83.05				0.11		755				725		547.375

		Chemical		142b

		Chemical		22-				162.71		131.47				0.055		2390.3636363636				1810		4326.5581818182

				Funding		44911459				769.49						8190.5454545455						8531.69						58.365		5.483		5.264

		Overall		Funding		66205949		1111.26																				65.974		6.350		6.415

		EGYPT

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				95.69		95.69				0.11		869.9090909091				725		630.6840909091

		Chemical		141b polyol				72.18		72.18				0.11		656.1818181818				725		475.7318181818

		Chemical		142b										0.065		0				2310		0

		Chemical		22-						6.13				0.055		111.4545454545				1810		201.7327272727

				Funding		9164414				174						1637.5454545454						1308.1486363636						52.669		5.596		7.006

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				129.61		33.92				0.11		308.3636363636				725		223.5636363636

		Chemical		141b polyol				98.34		26.16				0.11		237.8181818182				725		172.4181818182

		Chemical		142b				16.36		16.36				0.065		251.6923076923				2310		581.4092307692

		Chemical		22-				76.66		70.53				0.055		1282.3636363636				1810		2321.0781818182

				Funding		11786341				146.97						2080.2377622378						3298.4692307692						80.196		5.666		3.573

		Overall		Funding		20950755		320.97																				68.155		5.635		5.075

		MEXICO

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Cemical		123-

		Chemical		141b				392.5		392.5				0.11		3568.1818181818				725		2586.9318181818

		Chemical		141b polyol										0.11		0				725		0

		Chemical		142b						10.01				0.065		154.000				2310		355.74

		Chemical		22-				24.8		24.8				0.055		450.9090909091				1810		816.1454545455

				Funding		18,066,211				427.31						4173.0909090909						3758.8172727273						42.279		4.329		4.806

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		123-						0				0.02		0				77		0

		Chemical		141b						428.1				0.11		3891.8181818182				725		2821.5681818182

		Chemical		141b polyol						0				0.11		0				725		0

		Chemical		142b						0				0.065		0				2310		0

		Chemical		22-						105.5				0.055		1918.1818181818				1810		3471.9090909091

				Funding		11,087,772				533.6						5810						6293.4772727273						20.779		1.908		1.762

		Overall		Funding		29153983		0																				34.102		3.409		3.648

		LEBANON

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				15.1		15.1				0.11		137.2727272727				725		99.5227272727

		Chemical		141b polyol										0.11		0				725		0

		Chemical		142b										0.065		0				2310		0

		Chemical		22-				4.9		4.9				0.055		89.0909090909				1810		161.2545454545

				Funding		2682242				20						226.3636363636						260.7772727273						134.112		11.849		10.286

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				37.53		22.43				0.11		203.9090909091				725		147.8340909091

		Chemical		141b polyol						0				0.11		0				725		0

		Chemical		142b						0				0.065		0				2310		0

		Chemical		22-				23.63		18.73				0.055		340.5454545455				1810		616.3872727273

				Funding		4498093				41.16						544.4545454545						764.2213636364						109.283		8.262		5.886

		Overall		Funding		7180335		61.16																				118.558		9.602		7.529

		PERU

						Phase I		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				1.79		1.79				0.11		16.2727272727				725		11.7977272727

		Chemical		141b polyol										0.11						725

		Chemical		142b										0.065		0				2310		0

		Chemical		22-				1.95		1.95				0.055		35.4545454545				1810		64.1727272727

				Funding		310111				3.74						51.7272727273						75.9704545455						82.917		5.995		4.082

		Overall		Funding		310111		3.74																				82.917		5.995		4.082

		TOGO

						Phase I		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b										0.11		0				725		0

		Chemical		141b polyol										0.11						725

		Chemical		142b										0.065		0				2310		0

		Chemical		22-				7		7				0.055		127.2727272727				1810		230.3636363636

				Funding		692650				7						127.2727272727						230.3636363636						98.950		5.442		3.007

		Overall		Funding		692650		7																				98.950		5.442		3.007

		SAUDI

						Phase I		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				341		341				0.11		3100				725		2247.5

		Chemical		141b polyol										0.11						725

		Chemical		142b				115.86		115.86				0.065		1782.4615384615				2310		4117.4861538462

		Chemical		22-				246.43		246.43				0.055		4480.5454545455				1810		8109.7872727273

				Funding		14421066				703.29						9363.006993007						14474.7734265734						20.505		1.540		0.996

		Overall		Funding		14421066		703.29																				20.505		1.540		0.996

		CHINA

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Cemical		123-

		Cemical		124-

		Cemical		141b				1698.05		1698.05				0.11		15436.8181818182				725		11191.6931818182

		Cemical		141b polyol										0.11		0				725		0

		Cemical		142b				266.95		266.95				0.065		4106.9230769231				2310		9486.9923076923

		Cemical		22-				1480.6		1480.6				0.055		26920				1810		48725.2

		Cemical		225ca-										0.025						122

				Funding		289831680				3445.6						46463.7412587413						69403.8854895105						84.116		6.238		4.176

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		123-				2.7		2.7				0.02		135				77		10.395

		Chemical		124-

		Chemical		141b				5885.18		4187.13				0.11		38064.8181818182				725		27596.9931818182

		Chemical		141b polyol						0				0.11		0				725		0

		Chemical		142b				912.97		646.02				0.065		9938.7692307692				2310		22958.5569230769

		Chemical		22-				5359.4		3878.8				0.055		70523.6363636364				1810		127647.781818182

		Chemical		225ca-				1.22		1.22				0.025		48.8				122		5.9536

				Funding		533883629				8714.65						118662.223776224						178213.726923077						61.263		4.499		2.996

		Overall		Funding		823715309		12161.47																				69.304		5.111		3.411

								ODP total																				CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Total																										weighted		weighted		weighted

		Average						3090.5																				41.130		3.385		2.748





LVC

		Cost effectiveness LVCs

		ANGOLA

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b

		Chemical		141b polyol

		Chemical		142b

		Chemical		22-						1.59				0.055		28.9090909091				1810		52.3254545455

				Funding		191840				1.59						28.9090909091						52.3254545455						120.654		6.636		3.666

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b

		Chemical		141b polyol

		Chemical		142b

		Chemical		22-				10.77		9.18				0.055		166.9090909091				1810		302.1054545455

				Funding		967280				9.18						166.9090909091						302.1054545455						105.368		5.795		3.202

		Overall		Funding		1159120		10.77																				107.898		5.934		3.279

		ARMENIA

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				0		0				0.11		0				725		0

		Chemical		141b polyol				0.83		0.83				0.11		7.5454545455				725		5.4704545455

		Chemical		22-				1.4		1.4				0.055		25.4545454545				1810		46.0727272727

				Funding		649121				2.23						33						51.5431818182						291.086		19.670		12.594

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b

		Chemical		141b polyol				0.83

		Chemical		142b

		Chemical		22-				4.66		3.26				0.055		59.2727272727				1810		107.2836363636

				Funding		238196				3.26						59.2727272727						107.2836363636						73.066		4.019		2.220

		Overall		Funding		887317		5.49																				232.559		15.469		9.809

		CAMBODIA

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				0		0				0.11		0				725		0

		Chemical		141b polyol				0		0				0.11		0				725		0

		Chemical		22-				15		15				0.055		272.7272727273				1810		493.6363636364

				Funding		1772250				15						272.7272727273						493.6363636364						118.150		6.498		3.590

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b

		Chemical		141b polyol				0

		Chemical		142b

		Chemical		22-				15		0				0.055		0				1810		0

				Funding		0				0						0						0

		Overall		Funding		1772250		15																				235.983		12.979		7.171

		COSTA RICA

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Cemical		123-				0.01		0.01				0.02		0.5				77		0.0064935065

		Cemical		124-				0.09		0.09				0.02		4.5				609		0.0073891626

		Cemical		141b				1.43		1.43				0.11		13				725		9.425

		Cemical		141b polyol				14		14				0.11		127.2727272727				725		92.2727272727

		Cemical		142b				0.4		0.4				0.065		6.1538461538				2310		14.2153846154

		Cemical		22-				3		3				0.055		54.5454545455				1810		98.7272727273

		Cemical		225ca-										0.025						122

				Funding		1240037				18.93						205.972027972						214.6542672844						65.506		6.020		5.777

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		123-				0.01		0				0.02		0				77		0

		Chemical		124-				0.09

		Chemical		141b				1.43		0				0.11		0				725		0

		Chemical		141b polyol				14		0				0.11		0				725		0

		Chemical		142b				0.4		0				0.065		0				2310		0

		Chemical		22-				3		0				0.055		0				1810		0

		Chemical		225ca-				0		0				0.025		0				122		0

				Funding		0				0						0						0						0.000		0.000		0.000

		Overall		Funding		1240037		18.93																				65.506		6.020		5.777

		MALDIVES

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				0		0				0.11		0				725		0

		Chemical		141b polyol				0		0				0.11		0				725		0

		Chemical		22-				3.7		3.7				0.055		67.2727272727				1810		121.7636363636

				Funding		1219900				3.7						67.2727272727						121.7636363636						329.703		18.134		10.019

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b

		Chemical		141b polyol

		Chemical		142b

		Chemical		22-				3.7		0				0.055		0				1810		0

				Funding						0						0						0

		Overall		Funding		1219900		3.7																				329.703		18.134		10.019

		MONGOLIA

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				0		0				0.11		0				725		0

		Chemical		141b polyol				0		0				0.11		0				725		0

		Chemical		22-				1		1				0.055		18.1818181818				1810		32.9090909091

				Funding		413580				1						18.1818181818						32.9090909091						413.580		22.747		12.567

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b

		Chemical		141b polyol

		Chemical		142b

		Chemical		22-				1		0				0.055		0				1810		0

				Funding						0						0						0

		Overall		Funding		413580		1																				413.580		22.747		12.567

		UGANDA

						Phase I				ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b				0		0				0.11		0				725		0

		Chemical		141b polyol				0		0				0.11		0				725		0

		Chemical		22-				0.07		0.07				0.055		1.2727272727				1810		2.3036363636

				Funding		182685				0.07						1.2727272727						2.3036363636						2609.786		143.538		79.303

						Phase II		ODP total		ODP-t						Tonnes				GWP		kt CO2 eq						CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Chemical		141b

		Chemical		141b polyol				0

		Chemical		142b

		Chemical		22-				0.07		0				0.055		0				1810		0

				Funding		0				0						0						0						0.000		0.000		0.000

		Overall		Funding		182685		0.07																				537.315		29.552		16.327

								ODP total																				CE/ODP-kg		CE/kg		CE/kt CO2-eq

		Total																										weighted		weighted		weighted

		Average						54.96																				161.748		9.996		6.493





LVC-Alternative

		Consumption (mt)		Funding total phase-out		Number of countries		Total funding		Total baseline (HCFC-22) (mt)		CE ($/kg)		CE ($/ODP kg

		>0 <15		587,500		21		12,337,500		97.81		126.13		2,293.30

		15 <40		750,000		16		12,000,000		419.44		28.61		520.17

		40 <80		800,000		14		11,200,000		910.91		12.30		223.55

		80 <120		900,000		11		9,900,000		1,100.48		9.00		163.57

		120 <160		950,000		9		8,550,000		1,280.19		6.68		121.43

		160 <200		1,000,000		3		3,000,000		567.21		5.29		96.16

		200 <320		1,600,000		12		19,200,000		3,157.94		6.08		110.54

		320 <360		1,800,000		2		3,600,000		677.71		5.31		96.58

		Total						79,787,500		8,211.71		9.72		176.66






